## MTEP_AppA_Status
MTEP Approved Plan (Appendix A) Quarterly Status Report through 6/30/2017
Target Appendix | Planning Region | Geographic Location by TO Member System | PrjID | Prj Rec Date | Facility ID | Record Date | Facility Type | Expected ISD | From Sub | To Sub | Ckt | Max kV | Min kV | Description | Plan Status | Estimated Cost | Estimate Type | Est. Year Dollars | State | Miles Upgrade | Miles New | Facility Rating | Emerg. Rating | Allocation_FF | ShareStatus | Other Type | Cost Shared | Postage Stamp | MISO Facility | Transmission Project Type | App AB | MTEP16 Expected ISD | MTEP16 Planning Status | MTEP16 Estimated Cost | Facility Cost Change % | Cost Variance Documentation | In Service Date Change (Months)
A in MTEP16 | South | AECC | 9662 | 2017-01-09 | 20987 | 2016-05-09 | TX | 2017-01-01 | Harrison South |  |  | 161 |  | Upgrade transformer at Harrison South. | Planned | 600000 | Planning Preliminary |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 600000 | 0% |  | 0
A in MTEP16 | South | AECC | 9663 | 2017-01-09 | 20988 | 2016-05-09 | SUB | 2017-07-01 | Newport East |  |  | 161 | 13.2 | Construct 20 MVA, 161/13.2 kV substation. | Planned | 500000 | Planning Preliminary |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-07-01 | Planned | 500000 | 0% |  | 0
A in MTEP16 | South | AECC | 10204 | 2017-01-09 | 21491 | 2016-05-06 | SUB | 2018-06-01 | Hunter North 161/13.2kV Substation |  |  | 161 |  | 161/13.2kV Hunter North substation | Planned | 500000 | Planning Preliminary |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 500000 | 0% |  | 0
A in MTEP16 | South | AECC | 10205 | 2017-01-09 | 21492 | 2017-01-09 | SwSta | 2018-03-01 | AECC Bee Branch |  |  | 161 |  | 161kV Tap Breaker | Planned | 500000 |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-02-28 | Planned | 500000 | 0% |  | 13
A in MTEP16 | South | AECC | 10205 | 2017-01-09 | 21493 | 2017-01-09 | LN | 2017-08-01 | AECC Bee Branch | AECC Damascus | 1 | 161 |  | 6.8 mile 161kV line from the existing AECC Bee Branch substation to the proposed Damascus substation | Planned | 5500000 |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-02-28 | Planned | 5500000 | 0% |  | 6
A in MTEP16 | South | AECC | 10205 | 2017-01-09 | 21494 | 2017-01-09 | SUB | 2017-08-01 | Damascus |  |  | 161 |  | 161/13.2kV substation | Planned | 2000000 |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-02-28 | Planned | 2000000 | 0% |  | 6
A in MTEP16 | South | AECC | 10206 | 2017-01-09 | 21495 | 2016-05-06 | SwSta | 2020-12-01 | Clinton West |  |  | 161 |  | 5 position ring bus | Planned | 5000000 |  |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 5000000 | 0% |  | 0
A in MTEP16 | South | AECC | 10206 | 2017-01-09 | 21496 | 2016-05-06 | LN | 2020-12-01 | Clinton West | Partain |  | 161 |  | 14.0 mile line from the existing Clinton West to the proposed Partain substation | Planned | 18000000 | Planning Preliminary |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 18000000 | 0% |  | 0
A in MTEP16 | South | AECC | 10206 | 2017-01-09 | 21497 | 2016-05-06 | SUB | 2020-12-01 | Partain |  |  | 161 | 69 | build 3 position ring bus and 100MVA 161/69kV stepdown station with 2 69kV breakers | Planned | 4000000 | Planning Preliminary |  | AR |  |  | 100MVA |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2020-12-01 | Planned | 4000000 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 3005 | 2017-02-23 | 8614 | 2017-06-29 | LN | 2017-06-01 | Baldwin | Baldwin Tap | 1526 | 138 |  | Build a 138 kV double-circuit line between Baldwin Substation and the tap to the South Belleville-Tilden 1526 138 kV line by rebuilding 2 miles of existing single-circuit 138 kV line to double-circuit capability, both circuits to have 2000 A summer emergency capability. | M5_In Service | 6103146 | Planning | 2016 | IL |  | 2 | 399 | 478 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 2400000 | 154.3% | Originally specified as single circuit. | 0
A in MTEP16 | Central | AmerenIL | 3005 | 2017-02-23 | 8615 | 2017-06-29 | CB | 2017-06-01 | Baldwin | Install 138 kV Breakers |  | 138 |  | Construct a 5 position 138 kV ring bus at Baldwin Substation (5 - 3000 A, 40 kA PCBs) | M5_In Service | 10346470 | Planning | 2016 | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1000000 | 934.6% | Original project estimate was based on only replacing two breakers rather than constructing an entire ring bus. | 0
A in MTEP16 | Central | AmerenIL | 7820 | 2017-04-11 | 20090 | 2016-10-19 | LNrc | 2017-06-01 | Hennepin | Kewanee | 6101 | 138 |  | Upgrade terminal equipment at Hennepin terminal. | Planned | 104691 | Engineering | 2016 | IL |  |  | 214 | 255 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 300000 | -65.1% |  | 0
A in MTEP16 | Central | AmerenIL | 7860 | 2017-01-09 | 20100 | 2016-09-09 | LNrb | 2016-06-01 | Effingham 138 | Effingham NW | 1 | 138 |  | Elevate 2.72 miles of 954 kcmil ACSR conductor to permit operation at 120 degrees C. Verify line hardware, splices, etc. will permit operations at 120 degrees C. Upgrade terminal equipment at Effingham 138 Substation. | M5_In Service | 2000000 |  |  | IL | 2.72 |  | 240 | 304 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-01 | M5_In Service | 2000000 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 7869 | 2017-01-09 | 20107 | 2016-05-23 | SUB | 2016-05-01 | Alsey Tap |  |  | 138 |  | Install 138 kV breaker station near tap to the PPI Alsey Plant on the Jersesyville, Northwest-Meredosia-1 138 kV line. May be an ultimate 6-breaker ring bus. | M5_In Service | 6626495 |  |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-05-01 | M5_In Service | 6626495 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9261 | 2017-01-09 | 20851 | 2017-06-29 | SUB | 2017-12-01 | Searitt |  |  | 138 |  | Build a 3-breaker 138 kV ring bus adjacent to the North Decatur-Latham-1566 138 kV line near the planned Enbridge Pumping Station. Re-route the North Decatur-Latham-1566 138 kV line into and out of the new breaker station. | Under Construction | 5912747 | Engineering | 2016 | IL |  |  | 287 | 287 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 4119500 | 43.53% | N/A | 0
A in MTEP16 | Central | AmerenIL | 9261 | 2017-01-09 | 20852 | 2016-10-19 | LN | 2016-06-01 | Searitt | Enbridge | 1 | 138 |  | Construct radial 138 kV line from Searitt Breaker Station to Enbridge Pumping Station to supply customer load. Line conductor to have a minimum summer normal rating of at least 600 A. | M5_In Service | 276034 | Engineering | 2016 | IL |  | 0.5 | 143 | 143 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 444167 | -37.85% |  | 0
A in MTEP16 | Central | AmerenIL | 9722 | 2017-01-09 | 21106 | 2016-05-23 | TX | 2016-10-03 | Frederick, North |  |  | 138 | 69 | Replace exsisting 138-69 kV transformer bank with 112 MVA unit. | Planned |  |  |  | IL |  |  | 112 | 112 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-10-03 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9726 | 2017-01-09 | 21110 | 2016-10-19 | SUB | 2018-06-01 | Fogarty |  |  | 138 | 34.5 | Provide 138 kV connection to supply 138-34.5 kV transformer. | Planned | 1727563 | Planning | 2016 | IL |  |  | 112 | 112 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1726448 | 0.06458% | N/A | 0
A in MTEP16 | Central | AmerenIL | 9727 | 2017-01-09 | 21111 | 2016-10-19 | SUB | 2019-06-01 | Wakefield |  |  | 138 | 34.5 | Establish 138 kV ring bus; connect ot South Bloomington-Clinton-1372 line. | Planned | 7360755 | Planning | 2016 | IL |  |  | 112 | 112 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 7430056 | -0.9327% |  | 0
A in MTEP16 | Central | AmerenIL | 9736 | 2017-01-09 | 21123 | 2016-05-16 | LNrc | 2016-05-01 | East Quincy | Hamilton | 4 | 138 | 138 | Replace existing conductor. | M5_In Service | 8315916 |  |  | IL | 30.61 |  | 159 | 174 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-05-01 | M5_In Service | 8315916 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9741 | 2017-01-09 | 21128 | 2016-06-01 | TEQ | 2016-05-24 | Porter Road | East Collinsville | 1 | 138 | 138 | Upgrade terminal equipment at Porter Road. | M5_In Service | 50000 |  |  | IL |  |  | 160 | 202 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-05-24 | M5_In Service | 50000 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9845 | 2017-04-03 | 21222 | 2017-06-29 | SUB | 2017-05-01 | Gallatin |  |  | 138 | 69 | Construct 138 kV ring bus in Kansas-Hutsonville 138 kV line | M5_In Service | 5261718 | Engineering | 2016 | IL |  |  | 159 | 174 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-05-01 | Planned | 5621250 | -6.396% |  | 0
A in MTEP16 | Central | AmerenIL | 9853 | 2017-01-09 | 21230 | 2015-09-14 | TEQ | 2017-06-01 | Prairie State | Mt. Vernon, West | 1 | 345 | 345 | Upgrade terminal equipment at Mt. Vernon, West | Planned |  |  |  | IL |  |  | 1401 | 1793 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9869 | 2017-01-09 | 21251 | 2015-09-14 | TEQ | 2017-06-01 | Havana | Elkhart | 1 | 138 | 138 | Upgrade terminal equipment | Planned |  |  |  | IL |  |  | 160 | 165 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 9873 | 2017-01-09 | 21256 | 2017-06-29 | TX | 2016-12-01 | Edwards Plant |  |  | 138 | 69 | Install 138-69 kV transformer | Planned | 2198618 |  |  | IL |  |  | 150 | 150 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-01 | Planned | 0 | 0% | No cost had been entered previously. | 0
A in MTEP16 | Central | AmerenIL | 10884 | 2017-01-09 | 21681 | 2016-06-01 | TX | 2016-05-23 | Roxford |  |  | 345 | 138 | Replace 345/138 kV, 560 MVA transformer with a 700 MVA unit. | M5_In Service | 3611589 |  |  | IL |  |  | 700 | 700 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-05-23 | M5_In Service | 3611589 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 10884 | 2017-01-09 | 21682 | 2016-06-01 | TEQ | 2016-05-23 | Roxford |  |  | 345 |  | Install a 3000 A, 50 kA PCB to place the Roxford 345/138 kV transformer on its own position at Roxford Substation. | M5_In Service |  |  |  | IL |  |  | 1793 | 1793 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-05-23 | M5_In Service | 0 | 0% |  | 0
A in MTEP16 | Central | AmerenIL | 10904 | 2017-01-09 | 21688 | 2017-06-29 | LNrb | 2016-12-01 | Brokaw | Gibson City South | 1 | 138 |  | Rebuild to 1200 A summer emergency capability. | Planned | 14399011 | Planning | 2016 | IL | 28.5 |  | 255 | 325 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 10218299 | 40.91% | Originally proposed as a reconductoring project. Due to age and poor condition, the line will be rebuilt. | 0
A in MTEP16 | Central | AmerenIL | 10904 | 2017-01-09 | 21689 | 2016-10-19 | TEQ | 2016-12-01 | Gibson City South |  |  | 138 |  | Upgrade terminal equipment | Planned | 176846 | Planning Preliminary | 2016 | IL |  |  | 478 | 478 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 100000 | 76.85% | N/A | 0
A in MTEP16 | Central | AmerenIL | 11063 | 2017-01-09 | 21713 | 2017-06-29 | TEQ | 2016-12-01 | Rising | North Champaign | 1592 | 138 |  | Upgrade terminal equipment at Rising Substation terminal | M5_In Service | 1989033 | Engineering | 2016 | IL |  |  | 399 | 478 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 1747553 | 13.82% | N/A | 0
A in MTEP16 | Central | AmerenMO | 10483 | 2017-01-09 | 21586 | 2017-06-29 | LNup | 2016-12-01 | Cape | Kelso | 2 | 161 | 161 | Increase ground clearance, upgrade terminal equipment at Cape and Kelso. | Planned | 615719 |  |  | MO | 5.99 |  | 280 | 355 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 0 | 0% | No cost had been entered previously. | 0
A in MTEP16 | Central | AmerenMO | 10483 | 2017-01-09 | 21587 | 2016-10-19 | LNup | 2016-12-01 | Kelso | Miner | 2 | 161 | 161 | Increase ground clearance, upgrade terminal equipment at Kelso and Miner. | Planned | 6726347 | Planning | 2016 | MO | 19.85 |  | 280 | 355 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 5586082 | 20.41% | N/A | 0
A in MTEP16 | Central | AmerenMO | 10604 | 2017-01-09 | 21624 | 2017-06-29 | LNrc | 2016-12-01 | Page | Sioux | 1 | 138 |  | Replace conductor to match capability of the rest of the line | M5_In Service |  |  |  | MO | 14.28 |  | 241 | 286 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 3190 | 2017-01-09 | 5631 | 2017-03-31 | LN | 2016-06-01 | Sunset Point | Winneconne | 1 | 69 |  | Rebuild line Y-103 from Sunset Point to Winneconne to SN/SE = 200/300 deg F | M5_In Service | 492000 | Engineering |  | WI | 10.5 |  | 70 | 94 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-04-29 | Planned | 3868404 | -87.28% | Updated schedule | 2
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20011 | 2017-03-30 | LNrb | 2020-01-13 | Lone Rock | Richland | 1 | 69 |  | Rebuild Y-78 Lone Rock - Richmond 69 kV | Planned | 32400000 | Engineering |  | WI | 11.28 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 41848961 | -22.58% |  | 13
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20012 | 2017-03-30 | LNrb | 2020-01-13 | Lone Rock | Avoca Tap | 1 | 69 |  | Rebuild Y-124 Lone Rock - Avoca Tap 69 kV | Planned |  | Engineering |  | WI | 7.93 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 13
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20013 | 2017-03-30 | LNrb | 2020-01-13 | Avoca Tap | Avoca | 1 | 69 |  | Rebuild Y-124 Avoca Tap - Avoca 69 KV | Planned |  | Engineering |  | WI | 0.87 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 13
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20014 | 2017-03-30 | LNrb | 2020-01-13 | Muscoda Ind. Park | Muscoda | 1 | 69 |  | Rebuild Y-124 Muscoda Ind. Park - Muscoda 69 kV | Planned |  | Engineering |  | WI | 0.33 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 13
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20015 | 2017-03-30 | LNrb | 2020-01-13 | Avoca Tap | Muscoda Ind. Park | 1 | 69 |  | Rebuild Y-124 Avoca Tap - Muscoda Ind. Park 69 kV | Planned |  | Engineering |  | WI | 4.32 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 0 | 0% |  | 49
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20016 | 2017-03-30 | LNrb | 2020-01-13 | Muscoda | Blue River Tap | 1 | 69 |  | Rebuild Y-124 Muscoda - Blue River Tap 69 kV | Planned |  | Engineering |  | WI | 8.9 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 13
A in MTEP16 | West | ATC | 7583 | 2017-01-09 | 20017 | 2017-03-30 | LNrb | 2020-01-13 | Blue River Tap | Boscobel | 1 | 69 |  | Rebuild Y-124 Blue River Tap - Boscobel 69 kV | Planned |  | Engineering |  | WI | 6.1 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 13
A in MTEP16 | West | ATC | 7983 | 2017-01-09 | 20253 | 2017-03-30 | CB | 2017-10-02 | Canal |  |  | 138 | 69 | Canal 138-69 kV transformer high/low side breaker additions | Planned | 5100000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 5100000 | 0% |  | 4
A in MTEP16 | West | ATC | 7985 | 2017-01-09 | 20255 | 2017-06-30 | RLY | 2017-06-25 | Canal |  |  | 138 |  | Installing redundant bus differential protection on the two Canal 138-kV buses. | Planned | 225000 | Engineering | 2014 | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 221116 | 1.757% | Updated estimate | 0
A in MTEP16 | West | ATC | 7986 | 2017-01-13 | 20256 | 2017-06-30 | CB | 2019-04-01 | Highway V |  |  | 138 |  | Install high side breakers on both Highway V transformers. | Planned | 9000000 | Planning | 2018 | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 7440210 | 20.96% | Updated estimate | 4
A in MTEP16 | West | ATC | 8442 | 2017-01-09 | 20670 | 2017-03-31 | TX | 2016-12-22 | Arnott |  | 1 | 138 | 69 | Replace the Arnott 138/69 kV Transformer with a 60 MVA Unit | M5_In Service | 3500000 | Planning |  | WI |  |  | 60 | 75 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 4545000 | -22.99% |  | 0
A in MTEP16 | West | ATC | 8640 | 2017-01-09 | 20710 | 2017-03-31 | BUS | 2018-12-20 | City Limits |  | 1 | 138 |  | Replace bus conductor at City Limits bus 1-2 with 2500 kcmil Lupine | Planned | 600000 | Planning |  | WI |  |  | 332 | 381 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 500000 | 20% | Estimate update | 12
A in MTEP16 | West | ATC | 8640 | 2017-01-09 | 20711 | 2017-03-31 | BUS | 2018-12-20 | City Limits |  | 2 | 138 |  | Replace bus conductor at City Limits bus 2-3 with 2500 kcmil Lupine | Planned |  | Planning |  | WI |  |  | 484 | 631 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20752 | 2017-06-30 | LNrb | 2019-12-01 | Finger Rd | Luxemburg | 1 | 69 |  | Rebuild J-10 Finger Road 69 - Luxemburg 69 with T2 4/0 ACSR | Planned | 13191000 |  |  | WI | 12.49 |  | 39 | 51 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 74000000 | -82.17% | Updated estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20753 | 2017-06-30 | LNrb | 2019-12-01 | Luxemburg | Booster | 1 | 69 |  | Rebuild J-10 Luxemburg 69 - Booster 69 with 4/0 T2 ACSR. | Planned | 5485000 |  |  | WI | 6.23 |  | 46 | 59 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20754 | 2017-06-30 | LNrb | 2019-12-01 | Booster | Beardsley | 1 | 69 |  | Rebuild J-10 Booster 69 - Beardsley 69 with 4/0 T2 ACSR. | Planned | 5671000 |  |  | WI | 5.51 |  | 46 | 59 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20755 | 2017-06-30 | LNrb | 2019-12-01 | Barnett | Beardsley | 1 | 69 |  | Rebuild J-10 Barnett 69 - Beardsley 69 with 4/0 T2 ACSR. | Planned | 3477000 |  |  | WI | 3.32 |  | 46 | 59 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20756 | 2017-06-30 | LNrb | 2019-12-01 | Algoma | Barnett | 1 | 69 |  | Rebuild J-10 Algoma S Tap 69 - Barnett 69 with 4/0 T2 ACSR. | Planned | 7235000 |  |  | WI | 7.01 |  | 46 | 59 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Update estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20757 | 2017-06-30 | LNrb | 2019-12-01 | Algoma | Algoma | 1 | 69 |  | Rebuild J-10 Algoma 69 - Algoma S Tap 69 with 4/0 T2 ACSR. | Planned | 2980000 |  |  | WI | 1.74 |  | 39 | 43 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 8841 | 2017-01-09 | 20758 | 2017-06-30 | LNrb | 2019-12-01 | Canal | Algoma | 1 | 69 |  | Rebuild J-10 Canal 69 - Algoma 69 with 4/0 T2 ACSR. | Planned | 22678000 |  |  | WI | 18.73 |  | 39 | 43 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 9423 | 2017-01-09 | 20899 | 2017-03-30 | LNrb | 2018-06-01 | Plover | Whiting Avenue | 1 | 115 |  | Rebuild line B-106 (Plover-Okray-Whiting 115) using existing conductor 795 ACSR. | Planned | 6217603 | Planning |  | WI | 5.8 |  | 205 | 279 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 6217603 | 0% |  | -18
A in MTEP16 | West | ATC | 9896 | 2017-01-09 | 21307 | 2016-01-26 | SUB | 2015-12-31 | Lyndon |  |  | 138 |  | Install 2 line breakers to sectionalize. | M5_In Service | 3100000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | M5_In Service | 3100000 | 0% |  | 0
A in MTEP16 | West | ATC | 9911 | 2017-01-09 | 21322 | 2017-03-30 | SUB | 2016-04-21 | Maes |  |  | 138 |  | Maes substation: Install 2 line breakers to sectionalize | M5_In Service | 2600000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-04-22 | Planned | 1800000 | 44.44% | Updated estimate | 0
A in MTEP16 | West | ATC | 9917 | 2017-01-09 | 21331 | 2017-03-30 | SUB | 2016-09-12 | Bloomington |  |  | 69 |  | Install SCADA controlled breakers to sectionalize | M5_In Service | 2000000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1600000 | 25% | Updated estimate | -3
A in MTEP16 | West | ATC | 9918 | 2017-01-09 | 21332 | 2017-03-31 | SUB | 2016-03-10 | Red Maple |  |  | 138 |  | Install a bus tie breaker. | M5_In Service | 666000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 1200000 | -44.5% |  | -3
A in MTEP16 | West | ATC | 9921 | 2017-01-09 | 21334 | 2017-03-30 | SUB | 2017-11-16 | Birchwood |  |  | 138 |  | Install a bus tie breaker. | Planned | 1200000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 700000 | 71.43% | Updated estimate. | -1
A in MTEP16 | West | ATC | 9923 | 2017-01-09 | 21335 | 2017-03-30 | SUB | 2018-12-30 | Mukwonago |  |  | 138 |  | Install line breaker on line 67K61. | Planned | 800000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 600000 | 33.33% | Updated estimate | 12
A in MTEP16 | West | ATC | 9934 | 2017-01-09 | 21349 | 2017-03-31 | LNup | 2018-08-31 | Oak Creek | Hayes | 1 | 138 |  | Oak Creek - Hayes 138-kV line 811 upgrade and reconfiguration. | Planned | 21000000 |  |  | WI |  |  | 310 | 406 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-30 | Planned | 21000000 | 0% |  | 2
A in MTEP16 | West | ATC | 9938 | 2017-01-09 | 21360 | 2017-03-31 | TX | 2016-05-26 | Sunset Point |  |  | 138 |  | Replace Sunset Point 138-69 kV Transformer | M5_In Service | 6000000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 6000000 | 0% |  | -7
A in MTEP16 | West | ATC | 9944 | 2017-01-09 | 21364 | 2017-06-30 | TX | 2016-08-01 | Erdman |  |  | 138 |  | Replace Erdman T31 Transformer. | M5_In Service | 1300000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 6000000 | -78.33% |  | -16
A in MTEP16 | West | ATC | 9954 | 2017-01-09 | 21369 | 2017-06-30 | TX | 2019-08-01 | Lost Dauphin |  |  | 138 |  | Replace Lost Dauphin T1 Transformer. | Planned | 6700000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 6700000 | 0% |  | 8
A in MTEP16 | West | ATC | 9958 | 2017-01-09 | 21370 | 2015-09-15 | TX | 2017-12-31 | East Krok |  |  | 138 |  | Replace East Krok Transformer. | Planned |  |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2500000 | -100% |  | 0
A in MTEP16 | West | ATC | 9961 | 2017-01-09 | 21372 | 2017-03-31 | TX | 2019-12-01 | Nelson Dewey |  |  | 138 |  | Replace Nelson Dewey T31/T32 Transformers. | Planned | 4800000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 6000000 | -20% |  | 12
A in MTEP16 | West | ATC | 9977 | 2017-01-09 | 21394 | 2016-09-14 | LNrb | 2020-06-30 | Goodman | Caldron Falls | 1 | 69 |  | Rebuild 69KV Line J-88 Goodman - Caldron Falls Substation. | Planned | 35000000 |  |  | WI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-06-30 | Planned | 35000000 | 0% |  | 0
A in MTEP16 | West | ATC | 9986 | 2017-01-09 | 21408 | 2017-06-30 | LNrb | 2020-12-31 | Port Washington | Saukville | 1 | 138 |  | Rebuild 138KV Line 762 Port Washington - Saukville Substation. | Planned | 18000000 |  |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-12-31 | Planned | 15000000 | 20% | Updated schedule | -12
A in MTEP16 | West | ATC | 10403 | 2017-01-09 | 21577 | 2017-03-31 | LNup | 2017-07-31 | Kegonsa | Sun Prairie | 1 | 69 |  | Re-rate Y -81 69kV line between Kegonsa - Sun Prairie. | Planned | 1500000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-21 | Planned | 5000000 | -70% |  | 3
A in MTEP16 | West | ATC | 10404 | 2017-01-09 | 21578 | 2016-05-04 | LNup | 2017-03-17 | 9 Mile | Detour | 1 | 69 |  | Re-rate Approximately 56.87 miles (6950) 69kV Line between 9 Mile - Detour substations. | Planned | 7000000 |  |  | MI | 56.87 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-17 | Planned | 7000000 | 0% |  | 0
A in MTEP16 | West | ATC | 10484 | 2017-01-09 | 21588 | 2017-06-29 | LN | 2019-06-01 | HWY V | Eaton | 1 | 138 |  | Construct a new ATC 138KV loop through at Eaton Substation. | Planned | 2500000 |  |  | WI | 6.54 |  | 690 | 690 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 2500000 | 0% | Updated estimate | 0
A in MTEP16 | West | ATC | 10484 | 2017-01-09 | 21589 | 2015-12-16 | LN | 2019-06-01 | Eaton | East Krok | 1 | 138 |  | Construct a new ATC 138KV loop through at Eaton Substation. | Planned |  |  |  | WI | 14.92 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10484 | 2017-01-09 | 21590 | 2015-12-16 | SUB | 2019-06-01 | Eaton |  |  | 138 | 24.9 | New Eaton 138 KV substation | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10485 | 2017-01-09 | 21591 | 2015-12-16 | LN | 2022-06-01 | HWY V | BAY RIDGE | 1 | 138 |  | Construct a new ATC 138KV loop through at Bay Ridge Substation. | Planned |  |  |  | WI | 1.06 |  | 526 | 526 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2022-06-01 | Planned | 2000000 | -100% |  | 0
A in MTEP16 | West | ATC | 10485 | 2017-01-09 | 21592 | 2015-12-16 | LN | 2022-06-01 | BAY RIDGE | ONTARIO | 1 | 138 |  | Construct a new ATC 138KV loop through at Bay Ridge Substation. | Planned |  |  |  | WI | 1.61 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2022-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10485 | 2017-01-09 | 21593 | 2015-12-16 | SUB | 2022-06-01 | BAYRIDGE |  |  | 138 | 24.9 | Construct a new ATC 138KV loop through at Bay Ridge Substation. | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2022-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10543 | 2017-01-09 | 21603 | 2017-06-29 | TAP | 2017-01-01 | Escanaba2 ESC North Tap | West Side Tap | 1 | 69 |  | Construct T-D Escanaba North Substation (GOAB) | Planned | 738000 |  |  | MI |  | 0.99 | 390 | 390 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 1000000 | -26.2% | Updated estimate | 0
A in MTEP16 | West | ATC | 10543 | 2017-01-09 | 21604 | 2016-05-25 | TAP | 2017-01-01 | Escanaba2 | Northshore Tap | 1 | 69 |  | Construct T-D Escanaba North Substation (GOAB) | Planned |  |  |  | MI |  | 0.3 | 390 | 390 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10563 | 2017-01-09 | 21618 | 2017-06-29 | SUB | 2018-06-01 | Oakview |  |  | 138 |  | Construct T-D Escanaba North Substation | Planned | 3300000 |  |  | WI |  |  | 2000 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 4900000 | -32.65% | Updated estimate | 0
A in MTEP16 | West | ATC | 10589 | 2017-01-09 | 21619 | 2017-06-30 | LNup | 2017-06-09 | Whitcomb | Tigerton Tap | 1 | 69 |  | Rerate Whitcomb - Tigerton Tap 69kV | M5_In Service | 1900000 |  |  | WI |  |  | 335 | 425 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-09 | Planned | 1400000 | 35.71% | Updated estimate | 0
A in MTEP16 | West | ATC | 10603 | 2017-01-09 | 21623 | 2017-06-29 | LN | 2018-08-31 | Wild Rose | Springwater | 1 | 69 |  | Construct T - D Springwater Substation. | Planned | 3800000 |  |  | WI |  | 1.25 | 660 | 900 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 7100000 | -46.48% | Updated estimate | -16
A in MTEP16 | West | ATC | 10643 | 2017-01-09 | 21628 | 2017-06-29 | BUS | 2018-06-01 | St. Martins |  |  | 138 |  | Bus expansion. | Planned | 4700000 |  |  | WI |  |  | 2000 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-01-01 | Planned | 2300000 | 104.3% | Updated schedule. | 5
A in MTEP16 | West | ATC | 10643 | 2017-01-09 | 21629 | 2016-02-29 | CB | 2018-01-01 | St. Martins |  |  | 138 |  | Install a bus-tie circuit breaker. | Planned |  |  |  | WI |  |  | 2000 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-01-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10643 | 2017-01-09 | 21630 | 2016-02-29 | LINE | 2017-01-01 | St. Martins |  |  | 138 |  | Relocate line 3025. | Planned |  |  |  | WI |  |  | 1030 | 1402 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 10683 | 2017-01-09 | 21643 | 2017-06-30 | LINE | 2017-06-09 | Lone Rock | Richland Center | 1 | 69 |  | Uprate Y-78 Lone Rock - Richland Center. | Planned | 512000 | Planning |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-09 | Planned | 1700000 | -69.88% | Updated estimate | 0
A in MTEP16 | West | ATC | 10684 | 2017-01-09 | 21644 | 2017-06-29 | TX | 2017-06-01 | Ellinwood |  |  | 138 | 24.9 | T-D distribution transformer addition at Ellinwood Substation. | M5_In Service | 110000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 100000 | 10% | Updated estimate. | 0
A in MTEP16 | West | ATC | 10685 | 2017-01-09 | 21645 | 2017-06-29 | SUB | 2017-03-27 | Tomahawk |  |  | 115 |  | Install Tomahawk Substation Bus-Tie Breaker. | Planned | 460000 |  |  | WI |  |  | 2000 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 700000 | -34.29% | Updated schedule. | -3
A in MTEP16 | West | ATC | 10686 | 2017-01-09 | 21646 | 2017-06-29 | BUS | 2021-06-01 | Roosevelt Road |  |  | 138 |  | ATC bus expansion and T-D distribution transformer addition. | Planned | 250000 |  |  | WI |  |  | 1391 | 1595 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 200000 | 25% | Updated estimate. | 36
A in MTEP16 | West | ATC | 10703 | 2017-01-09 | 21648 | 2017-06-30 | CB | 2016-11-15 | Jefferson SS |  |  | 138 |  | Replace Jefferson SS 138 kV Circuit Breakers. | M5_In Service |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-15 | Planned | 2200000 | -100% |  | 0
A in MTEP16 | West | ATC | 10703 | 2017-01-09 | 21649 | 2016-02-08 | CAP | 2016-11-15 | Jefferson SS |  |  | 138 |  | Replace Jefferson SS 138 kV Capacitor Bank. | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-15 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ATC | 11223 | 2017-01-09 | 21745 | 2017-03-30 | TAP | 2017-11-30 | Y-32 Tap | Townhall | 1 | 69 |  | New T-D Townhall Substation - GOAB on Y-32 and approx. 2 miles of new 69 kV ROW. | Planned | 1600000 | Planning |  | WI | 2 |  | 40 | 46 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 3900000 | -58.97% |  | 5
A in MTEP16 | West | ATC | 11224 | 2017-01-09 | 21746 | 2016-05-12 | CB | 2017-11-01 | White Lake |  |  | 138 |  | White Lake Line Breaker. | Planned | 908000 | Planning |  | WI |  |  | 2,000 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-11-01 | Planned | 908000 | 0% |  | 0
A in MTEP16 | South | AXLA | 10122 | 2017-01-09 | 21469 | 2016-05-16 | LNrc | 2017-06-01 | Hunter | Downtown | 1 | 138 |  | Reconductor the existing Hunter - Downtown 138kV transmission line | Planned | 340000 |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 340000 | 0% |  | 0
A in MTEP16 | South | AXLA | 10123 | 2017-01-09 | 21470 | 2016-05-16 | LNrc | 2017-06-01 | Prescott | Sterks | 1 | 138 |  | Reconductor the existing Prescott - Sterkx 138kV transmission line | Planned | 490000 |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 490000 | 0% |  | 0
A in MTEP16 | South | CETO | 9543 | 2017-01-09 | 20926 | 2016-12-16 | CB | 2016-06-30 | Stamping Plant |  |  | 138 |  | Increase short-circuit capacity of the 177 and 188 circuit breakers | M5_In Service | 742626 | Actual | 2016 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-30 | M5_In Service | 560000 | 32.61% |  | 0
A in MTEP16 | East | CETO | 9544 | 2017-01-09 | 20925 | 2017-06-28 | CB | 2017-12-31 | CE Breaker Replacement Program - 2017 |  |  | 138 |  | Replace damaged or defective circuit breakers across the system. | M4_Pre-Construction | 1240000 |  | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1240000 | 0% |  | 0
A in MTEP16 | South | CETO | 9545 | 2017-01-09 | 20927 | 2017-03-29 | CB | 2017-03-24 | CE Breaker Replacement Program - 2016 |  |  | 138 |  | Replace damaged or defective circuit breakers across the system. | M5_In Service | 1380000 |  | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1380000 | 0% |  | 3
A in MTEP16 | South | CETO | 9859 | 2017-03-29 | 21240 | 2017-06-26 | LNup | 2016-12-31 | CE Line Equipment Replacement Program - 2016 |  |  | 138 |  | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | M5_In Service | 0 | Planning | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 160000 | -100% |  | 0
A in MTEP16 | South | CETO | 9860 | 2017-01-09 | 21241 | 2017-06-28 | LNup | 2017-12-31 | CE Line Equipment Replacement Program - 2017 |  |  | 138 |  | Replace cross arms, insulators, guying, and switches as needed to maintain the lines' condition | M4_Pre-Construction | 160000 | Planning Preliminary | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 160000 | 0% |  | 0
A in MTEP16 | South | CETO | 9861 | 2017-01-09 | 21242 | 2017-06-27 | LNup | 2016-12-31 | CE Pole Replacement Program - 2016 |  |  | 138 |  | Replace damaged or defective poles with new poles | M5_In Service | 79000 | Planning | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 360000 | -78.06% |  | 0
A in MTEP16 | South | CETO | 9862 | 2017-01-09 | 21243 | 2017-06-28 | LNup | 2017-12-31 | CE Pole Replacement Program - 2017 |  |  | 138 |  | Replace damaged or defective poles with new poles | M4_Pre-Construction | 680000 | Planning Preliminary | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 680000 | 0% |  | 0
A in MTEP16 | South | CETO | 9863 | 2017-01-09 | 21244 | 2017-03-29 | LNup | 2016-12-31 | Miles Road |  |  | 138 |  | Replace/install poles to remediate sag limits | M5_In Service | 5000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 400000 | -98.75% |  | 0
A in MTEP16 | South | CETO | 9865 | 2017-01-09 | 21245 | 2017-06-28 | RLY | 2017-11-30 | CE Relay Replacement Program - 2016 |  |  | 138 |  | Replace electromechanical and/or defective relays with new digital relays | M4_Pre-Construction | 400000 | Planning | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 240000 | 66.67% | Revised estimates due increased scope needed | 11
A in MTEP16 | South | CETO | 9866 | 2017-01-09 | 21246 | 2017-06-27 | RLY | 2017-12-31 | CE Relay Replacement Program - 2017 |  |  | 138 |  | Replace electromechanical and/or defective relays with new digital relays | M4_Pre-Construction | 480000 | Planning Preliminary | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 480000 | 0% |  | 0
A in MTEP16 | South | CETO | 9868 | 2017-01-09 | 21252 | 2017-03-29 | TEQ | 2016-12-31 | CE Substation Equipment Replacements - 2016 |  |  | 138 |  | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | M5_In Service | 870000 | Planning | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 560000 | 55.36% | Equipment failures were higher cost than anticipated | 0
A in MTEP16 | South | CETO | 9870 | 2017-01-09 | 21253 | 2017-06-27 | TEQ | 2017-12-31 | CE Substation Equipment Replacements - 2017 |  |  | 138 |  | Replace damaged or defective substation equipment, not including breakers or relays, with new equipment | M4_Pre-Construction | 500000 | Planning Preliminary | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 500000 | 0% |  | 0
A in MTEP16 | South | CETO | 9871 | 2017-01-09 | 21254 | 2017-06-27 | LNrb | 2017-06-01 | Edenville | Edenville Jct | 1 | 138 |  | Rebuild the north portion of the Edenville-Edenville Jct 138 kV Line, approximately 9.8 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | M5_In Service | 3470000 | Planning | 2017 | MI | 9.8 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4170000 | -16.79% |  | -6
A in MTEP16 | South | CETO | 9872 | 2017-01-09 | 21255 | 2016-12-16 | LNrb | 2016-11-30 | Edenville | Edenville Jct | 1 | 138 |  | Rebuild the south portion of the Edenville-Edenville Jct 138 kV Line, approximately 2.0 miles, utilizing 138 kV single circuit construction and 336.4 ACSR conductor. | M5_In Service | 720000 | Construction | 2016 | MI | 2 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 850000 | -15.29% |  | -1
A in MTEP16 | South | CETO | 9874 | 2017-01-09 | 21258 | 2017-06-27 | LNrb | 2017-12-31 | Cole Creek | Cole Creek Jct | 1 | 138 |  | Rebuild the Cole Creek-Cole Creek Jct 138 kV Line, approximately 4.7 miles, utilizing 138 kV single circuit construction and 795 ACSR conductor. | M3_Long Lead Materials | 1960000 | Planning Preliminary | 2017 | MI | 4.7 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1960000 | 0% |  | 0
A in MTEP16 | South | CETO | 9875 | 2017-01-09 | 21259 | 2017-06-05 | SUB | 2017-12-31 | Chase |  |  | 138 |  | Rebuild the 138 kV portion of Chase Substation to a three breaker ring bus | M4_Pre-Construction | 3700000 | Engineering Preliminary | 2017 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 3200000 | 15.62% | Labor bid higher than estimated. | 0
A in MTEP16 | South | CETO | 9878 | 2017-01-09 | 21263 | 2017-06-27 | SUB | 2018-06-01 | Vrooman |  |  | 138 |  | Complete the 138 kV bus as a ring by adding one 138 kV breaker | M2a_Pre-Project Approval | 800000 | Planning Preliminary | 2018 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 800000 | 0% |  | 0
A in MTEP16 | South | CETO | 10046 | 2017-01-09 | 21447 | 2017-06-27 | SUB | 2017-12-31 | Beaver Creek |  |  | 138 |  | Construct a 138 kV three breaker ring bus at Beaver Creek Substation | M4_Pre-Construction | 3200000 | Planning Preliminary | 2018 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-03-01 | Planned | 3200000 | 0% |  | -3
A in MTEP16 | South | CETO | 10046 | 2017-01-09 | 21448 | 2017-06-27 | RLY | 2017-12-31 | Higgins |  |  | 138 |  | Replace the relaying on the Higgins end of the line to Beaver Creek | M4_Pre-Construction | 300000 | Planning Preliminary | 2018 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-03-01 | Planned | 300000 | 0% |  | -3
A in MTEP16 | South | CETO | 10763 | 2017-01-09 | 21661 | 2016-06-28 | TEQ | 2016-06-17 | Emmet |  |  | 138 |  | Add a wavetrap and upgrade relaying on the Emmet-Livingston 138 kV Line to a dual-pilot scheme. | M5_In Service | 874000 | Pre-Construction | 2016 | MI |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-06-17 | M5_In Service | 874000 | 0% |  | 0
A in MTEP16 | South | CFU-PMEU | 11383 | 2017-01-09 | 21764 | 2016-06-15 | CAP | 2017-08-01 | Pella West sub | Pella Clark St. sub | na | 69 |  | Move the capacitor from the Pella West Sub to Pella Clark St. Sub to make room for J329 interconnection at Pella West. | Under Construction | 169250 | GIA | 2014 | IA |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-08-01 | Under Construction | 169250 | 0% |  | 0
A in MTEP16 | South | CFU-PMEU | 11383 | 2017-01-09 | 21766 | 2016-06-15 | TEQ | 2017-08-01 | Pella West Substation |  |  | 69 |  | Terminal for J329 69kV line into the Pella West substation. | Under Construction | 800050 | GIA | 2014 | IA |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-08-01 | Under Construction | 800050 | 0% |  | 0
A in MTEP16 | South | CFU-PMEU | 11383 | 2017-01-09 | 21767 | 2016-06-15 | RLY | 2017-08-01 | Pella West Substation |  |  | 69 |  | Line relaying for G329 including relaying changes for capacitor bank move to Pella clark st sub. | Planned | 74400 | GIA | 2014 | IA |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-08-01 | Planned | 74400 | 0% |  | 0
A in MTEP16 | South | CLECO | 9542 | 2017-01-09 | 20924 | 2015-08-31 | SUB | 2016-12-01 | DoletHills Mine |  |  | 230 |  | Tap existing Dolet Hills to Mansfield compressor 8.4 miles from Dolet Hills to serve new load. | Planned | 5000000 | Budgetary |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 5000000 | 0% |  | 0
A in MTEP16 | South | CLECO | 9713 | 2017-01-09 | 21093 | 2015-09-11 | CB | 2016-11-01 | Dolet Hills |  |  | 345 |  | Replace one of the 345kV breakers at Dolet Hills | Planned | 294580 | Budgetary |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-11-01 | Planned | 294580 | 0% |  | 0
A in MTEP16 | South | CLECO | 9715 | 2017-01-09 | 21094 | 2015-09-11 | CB | 2016-10-01 | Wax Lake |  |  | 138 |  | Replaced existing MOS for Cap bank 1 and 2 with new Cap Switchers | Planned | 406013 |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 406013 | 0% |  | 0
A in MTEP16 | South | CLECO | 10983 | 2017-01-09 | 21695 | 2016-04-04 | CB | 2017-05-01 | HOPKINS |  |  | 138 |  | Add a breaker in series with Hopkins Breaker 8061 | Planned | 300000 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 300000 | 0% |  | 0
A in MTEP16 | Central | CWLD | 10162 | 2017-02-23 | 21625 | 2016-09-14 | TEQ | 2016-03-01 | McBaine | McBaine Tap | 1 | 161 |  | New wave trap and new switch on McBaine-McBaine Tap 161 kV line. | M5_In Service | 50000 | Budgetary | 2016 | MO |  |  | 249 | 249 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-03-01 | M5_In Service | 50000 | 0% |  | 0
A in MTEP16 | Central | DEI | 2873 | 2017-01-09 | 5026 | 2017-03-08 | Dist | 2018-06-01 | Danville East | new dist sub | 1 | 69 | 12 | Construct new Danville East substation near HRH hospital - single 22.4MVA transformer - 6945 ckt to be looped through | M3_Long Lead Materials | 1040000 | Planning | 2013 | IN |  | 0.5 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 990000 | 5.051% | non-BES transition to detailed estimate | 0
A in MTEP16 | Central | DEI | 9834 | 2017-01-09 | 21211 | 2017-03-08 | LNrb | 2020-12-31 | Noblesville Gen Station | Tipton West | 1 | 230 |  | Noblesville to Tipton West 23008 ckt: Replace all single/H-frame pole structures with steel poles, reconductor with 954ACSR45X7 OVAL / OPGW and build Switching Station with 3-2000A line switches near existing Carmel 146th St. junction. | M1_Final SPM or OOC | 12079985 | Engineering w/AFUDC | 2015 | IN | 12 |  | 501 | 501 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 12079985 | 0% |  | 24
A in MTEP16 | Central | DEI | 9850 | 2017-01-09 | 21227 | 2017-03-08 | SwSta | 2017-12-31 | Lebanon Prairie Crk. SS |  |  | 69 |  | New Lebanon Prairie Crk. 69kV Switching Station to be inserted in the 6983 ckt. | M4_Pre-Construction | 3518244 | Engineering w/AFUDC | 2015 | IN |  | 1.1 | 100 | 100 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 3518244 | 0% |  | 0
A in MTEP16 | Central | DEI | 9854 | 2017-01-09 | 21231 | 2017-06-02 | CB | 2017-12-31 | Speed |  |  | 138 |  | Speed 138kV - Replace OCB 13850, 13857, 13869, 13881, 138138 TIE and obsolete relays on CIR 13850, 13857, 13881. | Under Construction | 2264125 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2264125 | 0% |  | 0
A in MTEP16 | Central | DEI | 9855 | 2017-01-09 | 21232 | 2017-03-08 | CB | 2020-12-31 | Columbus North |  |  | 230 | 69 | Columbus North: Replace OCB 6975, 6929, 69230-1, 6950 and obsolete relays on CIR 6929, 6950, 6975, 6982. Also replace relays on CIR 23019. | M1_Final SPM or OOC | 2711016 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2020-12-31 | Planned | 2711016 | 0% |  | 0
A in MTEP16 | Central | DEI | 9856 | 2017-01-09 | 21233 | 2017-06-02 | CB | 2017-12-31 | Walton |  |  | 230 | 69 | Walton: Replace OCB 69 KV CAP BK, 69230-1, 69110, 69 KV TRANSFER, 6927, 6987, 23020-21. | Under Construction | 3303866 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 3303866 | 0% |  | 0
A in MTEP16 | Central | DEI | 9858 | 2017-01-09 | 21238 | 2017-03-08 | TX | 2018-12-31 | Bedford 345kV |  |  | 345 | 138 | Bedford 345: Replace 345/138kV Bank 7 | M3_Long Lead Materials | 4151661 | Engineering w/AFUDC | 2015 | IN |  |  | 400 | 400 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 4151661 | 0% |  | 0
A in MTEP16 | Central | DEI | 9858 | 2017-01-09 | 21239 | 2017-03-08 | CB | 2018-12-31 | Bedford 345kV |  |  | 345 | 69 | Bedford 345: Replace relays on CIR 6995, 13829, 13837, 34506, 34521. Replace all 69kV and 138kV Oil Circuit Breakers. | M3_Long Lead Materials | 7927152 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 7927152 | 0% |  | 0
A in MTEP16 | Central | DEI | 9888 | 2017-01-09 | 21275 | 2017-06-02 | LNrb | 2020-12-31 | Middlefork | Deer Crk. Jct. | 1 | 69 |  | Rebuild 6988 ckt. from MiddleFork sub to deadend 879/1041-01 and from Deer Cr Jct to 879/1046. 477acsr@120C w/ OPGW - 187 wood poles to be replaced with light duty steel. | M3_Long Lead Materials | 4860632 | Engineering w/AFUDC | 2015 | IN | 7.1 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 4860632 | 0% |  | 36
A in MTEP16 | Central | DEI | 9889 | 2017-01-09 | 21277 | 2017-03-08 | LNrb | 2017-12-31 | Sharpsville | Kokomo Southeast |  | 69 |  | Rebuild 69174 ckt. from Sharpsville sub to Kokomo SE. 477acsr@120C w/ OPGW - 174 wood poles to be replaced with light duty steel. | M4_Pre-Construction | 4287945 | Engineering w/AFUDC | 2015 | IN | 7.3 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 4287945 | 0% |  | 0
A in MTEP16 | Central | DEI | 9890 | 2017-01-09 | 21278 | 2017-03-08 | LNup | 2020-12-31 | Gibson Gen. Sta. | HE Merom Gen. Sta. |  | 345 |  | Gibson to Merom: Install (10) double deadend structures in the 34511 ckt. | M1_Final SPM or OOC | 4433734 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4433734 | 0% |  | 36
A in MTEP16 | Central | DEI | 9891 | 2017-01-09 | 21279 | 2017-02-09 | LNup | 2020-12-31 | Flat Rock | Hope Jct. |  | 69 |  | Flat Rock to Hope Jct. 6975 ckt. pole replacements (45), replace line switches at both ends. Transfer existing conductor to new poles. | M3_Long Lead Materials | 1087274 | Engineering w/AFUDC | 2015 | IN | 3.3 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 1087274 | 0% |  | 48
A in MTEP16 | Central | DEI | 9892 | 2017-01-09 | 21280 | 2017-03-08 | LNup | 2018-12-31 | Lewis Crk. | Flat Rock |  | 69 |  | Lewis Crk. to Flat Rock 6975 ckt. pole replacements (100), replace line switches at Lewis Crk with 1200A. Transfer existing conductor to new poles. | M3_Long Lead Materials | 1875342 | Engineering w/AFUDC | 2015 | IN | 5.7 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 1875342 | 0% |  | 0
A in MTEP16 | Central | DEI | 9893 | 2017-01-09 | 21281 | 2017-03-08 | CB | 2017-06-01 | Shelbyville Northeast |  |  | 138 | 69 | Shelbyville Northeast - Replace CIR 6946, 6976, 69183, 13803, 13865 relays, replace OCBs 6946, 6976, 69183, 69138-1, 13803, replace Bank 1 ground switch with circuit switcher, and station battery. | Under Construction | 3511433 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 3511433 | 0% |  | 0
A in MTEP16 | Central | DEI | 9897 | 2017-01-09 | 21295 | 2017-03-08 | Dist | 2018-12-31 | River Ridge Gateway |  |  | 138 | 12 | River Ridge Gateway 138-12kV Sub. to be inserted in the 13857 ckt. between Clark Maritime and HE Northport | M3_Long Lead Materials | 1141000 | Planning Preliminary | 2015 | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1000000 | 14.1% | transition to detailed estimate | 6
A in MTEP16 | Central | DEI | 9905 | 2017-01-09 | 21313 | 2017-03-08 | LNrb | 2017-12-31 | Sharpsville | Windfall Jct. |  | 69 |  | Rebuild 69174 from Sharpsville sub to Windfall Jct - 477acsr@120C w/ OPGW - 81 wood poles to be replaced with light duty steel. Replace (3) Windfall Jct switches with 1200A. Install new motor mechs on 69-1 and 69-3 at Windfall Junction. | M4_Pre-Construction | 2179983 | Engineering w/AFUDC | 2015 | IN | 3.5 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 2179983 | 0% |  | 0
A in MTEP16 | Central | DEI | 9914 | 2017-01-09 | 21327 | 2017-03-08 | LNrb | 2017-06-01 | Mohawk | Lee Hanna Jct |  | 69 |  | Rebuild 5.84 mile 69kV - 69130 ckt. from Mohawk to Mohawk Ind. Jct to Lee Hanna Jct with 954ACSR@120C - replace (2) Lee Hanna Jct line switches with 1200A | Under Construction | 3741298 | Engineering w/AFUDC | 2015 | IN | 5.84 |  | 153 | 153 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 3741298 | 0% |  | 0
A in MTEP16 | Central | DEI | 9926 | 2017-01-09 | 21338 | 2017-03-08 | Dist | 2018-12-31 | Spelterville |  |  | 138 | 34 | Spelterville: expand sub footprint, Install 138/34kV 60MVA Bank | M3_Long Lead Materials | 1332000 | Planning Preliminary | 2015 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 1000000 | 33.2% | transition to detailed estimate | 0
A in MTEP16 | Central | DEI | 10144 | 2017-01-09 | 21480 | 2017-03-08 | CB | 2017-12-31 | Cayuga Gen. Sta. |  |  | 230 |  | Cayuga Gen. Sta.: Replace existing 230kV OCBs 23011-03, 23013-11,230B9-13 and associated disconnect switches. New brkrs will be 3000 amp, 63KIA with 3000A disc. switches | M4_Pre-Construction | 1536000 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1536000 | 0% |  | 0
A in MTEP16 | Central | DEI | 11343 | 2017-01-09 | 21762 | 2017-03-08 | LNrc | 2018-06-01 | Lafayette SE | General Foods Jct | 1 | 138 |  | Lafayette SE to General Foods Jct 13808 Reconductor: reconductor 0.64 mile of 138kV line with 954acsr@120C | M3_Long Lead Materials | 1594932 | Engineering w/AFUDC | 2016 | IN | 0.64 |  | 301 | 301 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1060000 | 50.47% |  | 0
A in MTEP16 | South | Entergy-AR | 4665 | 2017-01-09 | 8845 | 2017-06-23 | TX | 2019-06-01 | Mabelvale 500 kV Substation | Mabelvale 115 kV Substation | 1 | 500 | 115 | Replace transformer | Planned | 18304733 | Planning |  | AR |  |  | 598 | 598 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 17417000 | 5.097% | Budget increases | 18
A in MTEP16 | South | Entergy-AR | 4665 | 2017-01-09 | 8846 | 2017-03-23 | TX | 2018-06-01 | Mabelvale 500 kV Substation | Mabelvale 115 kV Substation | 2 | 500 | 115 | Replace transformer | Planned |  |  |  | AR |  |  | 598 | 598 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-AR | 7942 | 2017-01-09 | 20193 | 2017-06-23 | LNrb | 2019-06-01 | Mayflower 115kV substation | Morgan 115kV substation | 1 | 115 |  | Rebuild 5 miles of 115kV line from Mayflower to Morgan. | Planned | 3488585 | Planning |  | AR | 5 |  | 390MVA | 390MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 4877301 | -28.47% | Scoping Changes | 0
A in MTEP16 | South | Entergy-AR | 7944 | 2017-01-09 | 20195 | 2017-06-07 | LNrb | 2017-06-01 | Stuttgart Ricuskey | Stuttgart Industrial | 1 | 115 |  | Rebuild 2.6 miles of 115kV line from Stuttgart Ricuskey - Stuttgart Industrial. | M5_In Service | 7869202 | Planning |  | AR | 2.6 |  | 259MVA | 259MVA | GIP |  |  | N | N | Y | Externally Driven | A | 2018-01-30 | Planned | 2526158 | 211.5% | Goodwin Road and Stuttgart Ricuskey - Stuttgart Ind. Rebuild costs looped together. | -7
A in MTEP16 | South | Entergy-AR | 9673 | 2017-01-09 | 20991 | 2017-06-23 | TX | 2018-06-01 | El Dorado EHV |  |  | 500 | 115 | 598 MVA - 500/115 kV autotransformer | Planned | 6261993 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 16446045 | -61.92% | scoping has changed estimate. | 0
A in MTEP16 | South | Entergy-AR | 9691 | 2017-01-09 | 21015 | 2017-03-22 | CAP | 2017-03-17 | Lonoke East 115kV |  |  | 115 |  | Add a 20.5 MVAR capacitor bank at Lonoke East 115 kV station to provide voltage support upon contingency | M5_In Service | 1077113 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1456861 | -26.07% | estimate volatility (within estimate uncertainty for level 3 estimate) | -3
A in MTEP16 | South | Entergy-AR | 9693 | 2017-01-09 | 21017 | 2017-06-23 | IND | 2018-11-01 | Pleasant Hill |  |  | 500 | 161 | Add three 30 MVAR reactors on the tertiary windings of the 500/161/13.8 kV transformer at the Pleasant Hill EHV substation | Planned | 3352049 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-10-01 | Planned | 2184660 | 53.44% | Estimation increased | 13
A in MTEP16 | South | Entergy-AR | 9696 | 2017-01-09 | 21020 | 2017-06-23 | SwSta | 2018-12-01 | Newport SS |  |  | 161 |  | Build a 4-breaker switching station near Newport Industrial and re-terminate the Newport-Swifton 161 kV line into the new switching station. Build a new 161 kV line between the Newport switching station and Newport Industrial to eliminate the voltage issue. | Planned | 16090475 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 15150000 | 6.208% | budget changes | 6
A in MTEP16 | South | Entergy-AR | 9697 | 2017-01-09 | 21021 | 2017-03-22 | LNrb | 2017-03-21 | Trumann 161kV | Trumann West 161kV |  | 161 |  | Re-build 6.5 mile long line to a minimum rating of 1300A. | M5_In Service |  | Planning |  | AR | 6.5 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 12115000 | -100% |  | -15
A in MTEP16 | South | Entergy-AR | 9698 | 2017-01-09 | 21022 | 2017-06-23 | LNrb | 2018-06-01 | El Dorado East 115kV | El Dorado Jackson 115kV |  | 115 |  | Re-build the 2.92 mile long 115 kV line to a minimum rating of 259 MVA (1300 Amps) to eliminate the thermal constraints | Planned | 3392889 | Planning |  | AR | 2.92 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 4926295 | -31.13% |  | 0
A in MTEP16 | South | Entergy-AR | 9703 | 2017-01-09 | 21031 | 2017-06-23 | SUB | 2017-11-07 | Bono |  |  | 161 |  | Purchase substation Site with enough land for future second transformer. Install 1-40 MVA - 161/13.8 kV - LTC substation transformer and three (3) breaker bays. Construct the feeder bays for overhead exits. Install one 2000 amp / 15 kV main breaker and three 1200 amp / 15kV feeder breakers. Install SCADA and metering in accordance with Entergy standards. Build new circuit N310- Replace 2 miles of 1/0 Acsr with 795 AA from substation south on Highway 285 to Highway 225. Build new circuit N320 - build new 2 miles of 795AA and reconductor 1.67 miles of 1/0 Acsr with 795 AA from substation south on Highway 285 to Highway 25. Build new circuit N330 - 500 feet of 795 to tie into existng 1/0 Acsr to the north on Highway 285 to pick up Republican Road.. Install 3-1200 amp Air breaks(Republican Road, Highway 225, and Highway 25) to be normally OPEN.Install 3-1200 amp getaway disconnects on each circuit. | Under Construction | 9013484 | Planning |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-10-01 | Planned | 9380200 | -3.909% | budget changes | 1
A in MTEP16 | South | Entergy-AR | 9704 | 2017-01-09 | 21035 | 2017-06-23 | SUB | 2018-12-01 | London North 161kV |  |  | 161 |  | Purchase substation Site with enough land for future second transformer. Install 1-40 MVA - 161/13.8 kV - LTC substation transformer and three (3) breaker bays. Construct the feeder bays for overhead exits. Install one 2000 amp / 15 kV main breaker and three 1200 amp / 15kV feeder breakers. Install SCADA and metering in accordance with Entergy standards. Build 300 feet of 795 AA for new circuit XXXX from substation north to Highway 64. Replace 1.4 miles of 3 phase #6 copper with 336 acsr from substation site west on Highway 64 to the town of London. Replace Recloser 7Y21with a 600 amp air break to be normally OPEN.. Build 500 feet of 795 for new circuit XXXX to tie in to 336 Acsr that travels south via Transmission Line to the ANO plant. Build 300 feet of 795 AA for new circuit XXXX from substation north to Highway 64 to tie into the existing 336 east toward Russellville North substation. Reconductor 0.8 mile of 336 Acssr with 795 AA from substation east on Highway 64 to Mill creek Road. Install 2-1200 amp Air breaks on Highway 64. Install 1200 amp getaway disconects on each feeder circuit. | Planned | 9106531 | Planning |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-10-01 | Planned | 9244000 | -1.487% | budget changes | 14
A in MTEP16 | South | Entergy-AR | 9707 | 2017-01-09 | 21040 | 2017-06-23 | SUB | 2018-04-01 | Camden Maguire 115kV |  |  | 115 |  | Reconfigure Camden Maguire 115 kV substation so that a single bus failure will not open all the elements in the Camden Maguire substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | Under Construction | 6932146 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 5772470 | 20.09% | Estimation increased. | 10
A in MTEP16 | South | Entergy-AR | 9708 | 2017-01-09 | 21041 | 2017-06-07 | SUB | 2017-06-01 | Independence 161kV |  |  | 161 |  | Reconfiguring the Independence 161 kV station to a breaker-and-a-half configuration or a double bus/double breaker configuration will help eliminate area thermal and voltage violations. The specific configuration will be determined in project scoping. | M5_In Service | 6398321 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-10-01 | Under Construction | 9100851 | -29.7% | Construction activity delays due to outage scheduling. | -4
A in MTEP16 | South | Entergy-AR | 9709 | 2017-01-09 | 21042 | 2017-06-23 | SUB | 2021-06-01 | Mabelvale 115kV |  |  | 115 |  | Reconfigure the Mabelvale 115 kV substation so that a single bus tie breaker failure will not open all the elements in the Mabelvale 115 kV substation. Some potential configurations are double bus double breaker, breaker and a half, and ring bus. The final configuration will be decided during project scoping. | Planned | 10910837 | Planning |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 17446076 | -37.46% | scoping | 24
A in MTEP16 | South | Entergy-AR | 10044 | 2017-01-09 | 21446 | 2017-06-16 | SwSta | 2017-11-01 | Goodwin |  |  | 115 |  | New 115 kV breaker switching station | Under Construction |  | GIA |  | AR |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2018-01-30 | Planned | 10064000 | -100% |  | -2
A in MTEP16 | South | Entergy-AR | 11483 | 2017-01-09 | 21774 | 2017-06-23 | SUB | 2017-09-15 | Hurricane Lake |  |  | 115 |  | New delivery point on River Ridge - Mabelvale 115 kV line. | Under Construction | 365306 | Planning |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 1589494 | -77.02% | Estimate increased. | 4
A in MTEP16 | South | Entergy-LA | 4634 | 2017-01-09 | 8797 | 2017-06-22 | LNrc | 2018-06-01 | Ninemile 115 kV substation | Westwego 115 kV substation | 1 | 115 |  | Reconductor Line | Planned | 6010637 | Planning |  | LA | 5.65 |  | 320 MVA | 320 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 9026000 | -33.41% | Area of rebuild | 0
A in MTEP16 | South | Entergy-LA | 4634 | 2017-01-09 | 8798 | 2017-06-22 | TEQ | 2018-06-01 | Ninemile 115 kV substation | Westwego 115 kV substation | 1 | 115 |  | Upgrade terminal equipment | Planned |  |  |  | LA |  |  | 320 MVA | 320 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 4639 | 2017-01-09 | 8804 | 2017-06-22 | LNrc | 2018-06-01 | Ninemile 115 kV substation | Harvey2 115 kV substation | 1 | 115 |  | Reconductor Line | Planned | 16057769 | Planning |  | LA | 9.5 |  | 320 MVA | 320 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 15121000 | 6.195% | Scoping | 0
A in MTEP16 | South | Entergy-LA | 4639 | 2017-01-09 | 8805 | 2017-06-22 | TEQ | 2018-06-01 | Ninemile 115 kV substation | Harvey2 115 kV substation | 1 | 115 |  | Upgrade terminal equipment | Planned |  |  |  | LA |  |  | 320 MVA | 320 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 7949 | 2017-01-09 | 20209 | 2017-06-22 | TX | 2018-12-01 | SOLAC 230 | SOLAC 69 | 1 | 230 | 69 | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. Each of the 138-69 kV Solac autotransformers will exceed their thermal rating during the single contingency (P1-3) transformer loss of one autotransformer on the other. This project will mitigate the thermal load violations on the two autotransformers by installing a third 138-69 kV Autotransformer at Solac." | Planned | 16189749 | Planning |  | LA |  |  | 300 | 300 | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 8457000 | 91.44% | costs | 6
A in MTEP16 | South | Entergy-LA | 7949 | 2017-01-09 | 21135 | 2017-06-22 | TX | 2018-12-01 | Solac 230 | Solac 69 | 2 | 230 | 69 | Upgrade AT2 | Planned |  |  |  | LA |  |  | 300 | 300 | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 7950 | 2017-01-09 | 20210 | 2017-06-22 | LNrc | 2018-06-01 | 335235 East Broad 69 | 335237 Ford 69 | 1 | 69 |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The East Broad to Ford 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Contraband to Solac 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading the line conductor." | Planned | 2912834 | Planning |  | LA | 1.49 |  | 143 MVA | 143 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1474000 | 97.61% | Scoping | 0
A in MTEP16 | South | Entergy-LA | 7952 | 2017-01-09 | 20212 | 2017-06-22 | LNrc | 2018-06-01 | 335239 SOLAC 69 | 335240 SOLAC 69 | 1 | 69 |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Contraband to Solac 69 kV line will exceed its thermal rating during the single contingency (P2-1) open breaker at East Broad toward Ford 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading the line conductor." | Planned | 6349307 | Planning |  | LA | 2.26 |  | 143 MVA | 143 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 4125000 | 53.92% | Cost | 0
A in MTEP16 | South | Entergy-LA | 9682 | 2017-01-09 | 20997 | 2017-06-22 | LNrb | 2018-06-01 | Vienna | Trussell Crossing | 1 | 115 |  | Upgrade line rating. | Planned | 7733777 | Planning |  | LA | 6.9 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 8823757 | -12.35% | Schedule | -24
A in MTEP16 | South | Entergy-LA | 9684 | 2017-01-09 | 21006 | 2017-06-22 | Dist | 2018-06-01 | Cadeville |  |  | 115 |  | 115 kV distribution substation | Planned | 36498301 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 41643000 | -12.35% | Cost | 0
A in MTEP16 | South | Entergy-LA | 9684 | 2017-01-09 | 21007 | 2017-06-22 | LN | 0 | Rilla | Cadeville | 1 | 115 |  | 15 mile 115 kV line constructed to 230 kV specs | Planned |  |  |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 0 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 9686 | 2017-01-09 | 21009 | 2017-06-22 | Dist | 2020-06-01 | Lake Providence |  |  | 115 |  | New Lake Providence distribution sub. | Planned | 34924044 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 31830074 | 9.72% | Full project scoping | 0
A in MTEP16 | South | Entergy-LA | 9686 | 2017-01-09 | 21010 | 2017-06-22 | LN | 0 | OakGrove | Lake Providence | 1 | 115 |  | New 115 kV line to new distribution substation. | Planned |  |  |  | LA |  | 15 | 176 | 176 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 0 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 9690 | 2017-01-09 | 21014 | 2017-06-22 | Dist | 2018-12-01 | Hodge |  |  | 230 |  | 230 kV substation | Planned | 14434862 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 14121450 | 2.219% | Cost | 0
A in MTEP16 | South | Entergy-LA | 9763 | 2017-01-09 | 21137 | 2017-06-22 | LNrc | 2018-06-01 | Baker | Blount | 1 | 69 |  | Upgrade Line | Planned | 4466686 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 5182000 | -13.8% |  | 0
A in MTEP16 | South | Entergy-LA | 9765 | 2017-01-09 | 21139 | 2017-06-22 | LNrc | 2017-04-20 | Harelson | Line 369 Tap | 1 | 69 |  | Upgrade Line | M5_In Service | 2827344 |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 3165000 | -10.67% |  | -20
A in MTEP16 | South | Entergy-LA | 9770 | 2017-01-09 | 21144 | 2017-03-23 | TEQ | 2016-11-15 | Goosport | L673 Tp | 1 | 69 |  | Upgrade Line | M5_In Service | 289644 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2016-11-18 | Planned | 145205 | 99.47% | Construction | 0
A in MTEP16 | South | Entergy-LA | 9771 | 2017-01-09 | 21145 | 2017-06-26 | SUB | 2019-12-31 | Jefferson Davis |  |  | 138 | 69 | Build new Sub | Planned | 89114245 |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 76570000 | 16.38% | Schedule | 6
A in MTEP16 | South | Entergy-LA | 9772 | 2017-01-09 | 21146 | 2017-03-23 | LN | 2019-12-31 | Colonial Welsh Tap | Jefferson Davis | 1 | 138 |  | Construct New Line | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9773 | 2017-01-09 | 21147 | 2017-03-23 | LN | 2019-12-31 | Jefferson Davis | Carter | 1 | 69 |  | Build new line | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9774 | 2017-01-09 | 21148 | 2017-03-23 | LN | 2019-12-31 | Jefferson Davis | L-13 | 1 | 69 |  | Cut L-13 in and out of Jeff Davis 69 kV sub | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9775 | 2017-01-09 | 21149 | 2017-03-23 | TAP | 2019-12-31 | Derouen |  |  | 69 |  | Cut Derouen into Line 11 | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9776 | 2017-01-09 | 21150 | 2017-03-23 | TAP | 2019-12-31 | Lawtag |  |  | 69 |  | Cut Lawtag sub in and out of Line 13. | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9777 | 2017-01-09 | 21151 | 2017-03-23 | TAP | 2019-12-31 | Welsh |  |  | 69 |  | Cut Welsh in and out of line 13A | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9778 | 2017-01-09 | 21152 | 2017-03-23 | LNrc | 2019-12-31 | Colonial Welsh Tap | Jefferson Davis | 1 | 138 |  | Reconductor Line | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 6
A in MTEP16 | South | Entergy-LA | 9779 | 2017-01-09 | 21153 | 2017-03-23 | LNrc | 2019-12-31 | Carter | Serpent | 1 | 69 |  | Reconductor Line | Planned |  | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 19235078 | -100% |  | 12
A in MTEP16 | South | Entergy-LA | 9780 | 2017-01-09 | 21154 | 2017-03-23 | LNrc | 2019-12-31 | Compton | Elton | 1 | 69 |  | Reconductor Line | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-01 | Planned | 12782000 | -100% |  | 0
A in MTEP16 | South | Entergy-LA | 9782 | 2017-01-09 | 21156 | 2017-03-23 | SUBmisc | 2019-12-31 | Lake Arthur |  |  | 69 |  | Adjust Normally Open Point | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2022-06-01 | Planned | 0 | 0% |  | -30
A in MTEP16 | South | Entergy-LA | 9786 | 2017-01-09 | 21160 | 2017-06-22 | CB | 2018-06-01 | Nelson |  |  | 138 |  | Add a breaker on line 274. | Planned | 1109453 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1142000 | -2.85% | Schedule | 12
A in MTEP16 | South | Entergy-LA | 9787 | 2017-01-09 | 21161 | 2017-03-24 | TEQ | 2016-05-06 | Air Products | Giegy | 1 | 138 |  | Upgrade line | M5_In Service | 300077 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 300000 | 0.02567% | Construction | -1
A in MTEP16 | South | Entergy-LA | 9788 | 2017-01-09 | 21162 | 2017-06-22 | CAP | 2018-06-01 | Port Barre |  |  | 69 |  | Add Cap Bank | Planned | 619540 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 786000 | -21.18% |  | 0
A in MTEP16 | South | Entergy-LA | 9790 | 2017-01-09 | 21164 | 2017-06-22 | Dist | 2017-05-30 | Swisco |  |  | 138 |  | Construct new distribution Substation | M5_In Service | 14128400 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 8191000 | 72.49% | Consrtuction | -1
A in MTEP16 | South | Entergy-LA | 9791 | 2017-01-09 | 21165 | 2017-06-22 | Dist | 2019-05-01 | Thompson Road |  |  | 230 |  | New distribution substation | Planned | 8591534 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 9252000 | -7.139% |  | 11
A in MTEP16 | South | Entergy-LA | 9792 | 2017-01-09 | 21166 | 2017-06-22 | Dist | 2019-06-01 | Lowe Grout Road |  |  | 138 |  | New Distribution Substation | Planned | 6454122 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 6989000 | -7.653% |  | 0
A in MTEP16 | South | Entergy-LA | 9794 | 2017-01-09 | 21168 | 2017-06-22 | TEQ | 2018-06-01 | Repapco | Port Hudson | 1 | 230 |  | Upgrade line | Planned | 1984483 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 101000 | 1865% | Scoping | 0
A in MTEP16 | South | Entergy-LA | 9795 | 2017-01-09 | 21169 | 2017-06-22 | CAP | 2017-05-18 | Nesser |  |  | 69 |  | Add Capacitor bank | M5_In Service | 856828 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 1053000 | -18.63% | Schedule | -7
A in MTEP16 | South | Entergy-LA | 9801 | 2017-01-09 | 21175 | 2017-06-22 | CAP | 2017-12-01 | North Norco |  |  | 115 |  | New Capacitor Bank | Planned | 2066038 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 1826000 | 13.15% | Schedule | 0
A in MTEP16 | South | Entergy-LA | 9805 | 2017-01-09 | 21179 | 2017-06-22 | LNrc | 2019-12-01 | Patterson | Pontchartrain Park | 1 | 115 |  | Upgrade Line | Planned | 11263455 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 11851000 | -4.958% | Schedule | 12
A in MTEP16 | South | Entergy-LA | 9847 | 2017-01-09 | 21224 | 2017-06-22 | CB | 2017-12-01 | Mossville |  |  | 69 |  | Replace breaker | Planned | 1154781 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 700000 | 64.97% | Scoping | 0
A in MTEP16 | South | Entergy-LA | 9848 | 2017-01-09 | 21225 | 2017-06-22 | CB | 2017-12-01 | Mossville |  |  | 69 |  | Replace breaker | Planned |  | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 9849 | 2017-01-09 | 21226 | 2017-06-22 | CB | 2017-12-01 | Carlyss |  |  | 69 |  | Replace breaker | Planned |  | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 10008 | 2017-01-09 | 21432 | 2017-06-22 | LN | 2020-06-01 | Nelson 230 kV | Menena 230 kV | 1 | 230 |  | Approximately 5.5 miles of 1272 ACSS single conductor. | Planned | 14812658 | Planning Preliminary |  | LA | 0 | 5.5 | 779 | 779 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 15500000 | -4.434% |  | 0
A in MTEP16 | South | Entergy-LA | 10223 | 2017-01-09 | 21500 | 2017-03-22 | TAP | 2016-05-27 | HollyRidge |  |  | 115 |  | New cut-in for LAGEN Holly Ridge substation | M5_In Service | 859891 | Facility Study |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 254833 | 237.4% | project complete | -7
A in MTEP16 | South | Entergy-LA | 10583 | 2017-01-09 | 21605 | 2017-06-22 | CB | 2018-06-01 | Coly 230 |  |  | 230 |  | Add 230 kV Breaker at Coly | Planned | 1685216 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1692865 | -0.4518% | Schedule | 0
A in MTEP16 | South | Entergy-LA | 10584 | 2017-01-09 | 21606 | 2017-06-22 | CB | 2018-06-01 | Tiger 230 |  |  | 230 |  | Add breaker at Tiger 230 kV | Planned | 1684042 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1692865 | -0.5212% | Schedule | 0
A in MTEP16 | South | Entergy-LA | 10585 | 2017-01-09 | 21607 | 2017-06-22 | CB | 2018-06-01 | Harelson 230 |  |  | 230 |  | Add breaker at Harelson 230 kV | Planned | 1693362 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1692865 | 0.02936% | Schedule | 0
A in MTEP16 | South | Entergy-LA | 10588 | 2017-01-09 | 21616 | 2017-06-22 | SUB | 2018-12-31 | Fleur 230 |  |  | 230 |  | Construct new substation on the Oakville to Alliance 230 kV line. | Planned | 14176609 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 11100000 | 27.72% | Scoping | 0
A in MTEP16 | South | Entergy-LA | 10588 | 2017-01-09 | 21617 | 2017-06-22 | CAP | 2018-12-31 | Fleur |  |  | 230 |  | Add cap bank to support the customer load | Planned |  | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 10588 | 2017-01-09 | 21669 | 2017-06-22 | LNrb | 2019-06-01 | Ninemile | Barataria | 1 | 115 |  | Rebuild Line | Planned | 41154179 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 31605000 | 30.21% | Cost | 6
A in MTEP16 | South | Entergy-LA | 10591 | 2017-01-09 | 21622 | 2017-06-22 | TX | 2017-01-16 | Willow Glen 500 | Willow Glen 138 |  | 500 | 138 | Adjust Tap on Auto | M5_In Service | 15027 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 15027 | 0% |  | 7
A in MTEP16 | South | Entergy-LA | 10623 | 2017-01-09 | 21626 | 2017-06-22 | SUB | 2018-11-01 | Sadie |  |  | 230 |  | Construct New 230 kV Substation on the PPG to Rosebluff line | Planned | 17806599 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 24814742 | -28.24% | Schedule | 5
A in MTEP16 | South | Entergy-LA | 10624 | 2017-01-09 | 21627 | 2017-06-22 | SUB | 2020-07-01 | Big Lake |  |  | 230 |  | Construct 230 kV substation on the Vincent to Graywood 230 kV line. | Planned | 13790751 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 28000000 | -50.75% |  | 13
A in MTEP16 | South | Entergy-LA | 11423 | 2017-01-09 | 21769 | 2017-06-22 | SUB | 2017-12-29 | PPG | Rosebluff | 1 | 230 |  | Construct a new 230 kV substation on the PPG to Rosebluff 230 kV line. | Under Construction | 11646401 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 7290000 | 59.76% | Schedule | 0
A in MTEP16 | South | Entergy-LA | 12016 | 2017-01-16 | 22087 | 2017-01-23 | TEQ | 2016-11-22 | Minden | Sarepta |  | 115 |  | Upgrade line terminal equipment on Minden – Sarepta 115kV to increase the MVA rating to 176MW | M5_In Service | 553129 |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2020-01-01 | Planned | 1900000 | -70.89% |  | -38
A in MTEP16 | South | Entergy-LA | 12017 | 2017-01-09 | 22088 | 2016-09-13 | SUB | 2022-01-01 | NSUB1 |  |  | 230 |  | New substation south of Ninemile substation | Planned | 13687330 |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2022-01-01 | Planned | 13687330 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 12017 | 2017-01-09 | 22089 | 2016-09-13 | LN | 2022-01-01 | Waterford | NSUB1 |  | 230 |  | New 230 kV transmission line connecting existing Waterford 230 kV to the new (NSUB1) substation | Planned | 69700811 |  |  | LA |  | 27 |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2022-01-01 | Planned | 69700811 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 12017 | 2017-01-09 | 22090 | 2016-09-13 | TEQ | 2022-01-01 | Waterford |  |  | 230 |  | Waterford Substation Modifications | Planned | 2568610 |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2022-01-01 | Planned | 2568610 | 0% |  | 0
A in MTEP16 | South | Entergy-LA | 12017 | 2017-01-09 | 22091 | 2016-09-13 | CB | 2022-01-01 | Michoud |  |  | 115 |  | Add breaker and reconfigure 115 kV bus at Michoud | Planned | 1700000 |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2022-01-01 | Planned | 1700000 | 0% |  | 0
A in MTEP16 | South | Entergy-MS | 9822 | 2017-01-09 | 21197 | 2017-06-22 | SwSta | 2018-12-31 | Harper |  |  | 115 |  | New 115 kV switching station on the Gloster - Crosby 115 kV. The Gloster - Centreville line will be rerouted from Gloster to Harper. | Planned | 7199368 | Planning |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 5300000 | 35.84% | Full project scoping | 0
A in MTEP16 | South | Entergy-MS | 9833 | 2017-01-09 | 21209 | 2017-06-22 | CAP | 2018-06-01 | Greenville North |  |  | 115 |  | Install 2nd capacitor bank | Planned | 1208424 | Planning |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1185857 | 1.903% | Full project scoping | 0
A in MTEP16 | South | Entergy-MS | 9839 | 2017-01-09 | 21218 | 2017-03-22 | SUBmisc | 2017-03-08 | Gerald Andrus 230 kV |  |  | 230 |  | Reteriminate line node. | M5_In Service |  |  |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-01 | Planned | 310000 | -100% |  | -12
A in MTEP16 | South | Entergy-MS | 9949 | 2017-01-09 | 21826 | 2017-06-22 | SwSta | 2018-06-01 | International Paper |  |  | 115 |  | The Cloverdale DP will be served from the existing Entergy IP to Johns Manville 115kV transmission line via a looped transmission feed into a new switching station to be constructed at the DP site. | Planned | 1256000 |  |  | MS |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 0 | Planned | 900000 | 39.56% | Updated costing | 1421
A in MTEP16 | South | Entergy-MS | 9955 | 2017-01-09 | 21749 | 2017-06-22 | SwSta | 2018-01-01 | Shaw Switching Station |  |  | 115 |  | Near EMI’s 115 kV transmission line number 107.5 between South Cleveland and Shaw Switching Station approximately 1.6 miles Northeast of the Shaw Switching Station between structure numbers 109 and 110. | Planned | 1050000 |  |  | MS |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 0 | Planned | 810000 | 29.63% | New switching station site required and short tap line | 1416
A in MTEP16 | South | Entergy-MS | 10863 | 2017-01-09 | 21674 | 2017-03-22 | LNrb | 2017-02-16 | Attala | Conehoma Creek | 1 | 115 |  | Upgrade line path rating to minimum 1303 A. | M5_In Service | 1958250 | Planning | 2016 | MS | 2 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1716001 | 14.12% | Project Complete | -4
A in MTEP16 | South | Entergy-MS | 10864 | 2017-01-09 | 21675 | 2017-06-26 | LNrb | 2017-05-30 | Pelahatchie | Morton | 1 | 115 |  | Upgrade Pelahatchie - Morton 115 kV to minimum 1303 A. | M5_In Service | 5578547 | Planning |  | MS | 6.07 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 5593224 | -0.2624% | Schedule | -7
A in MTEP16 | South | Entergy-MS | 10865 | 2017-01-09 | 21676 | 2017-06-22 | LNrb | 2018-06-01 | Morton | Forest Ind | 1 | 115 |  | Upgrade to 1303 A. | Planned | 10831119 | Planning |  | MS | 9 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 10987197 | -1.421% | Cost | 0
A in MTEP16 | South | Entergy-MS | 10943 | 2017-01-09 | 21692 | 2016-09-14 | SUB | 2019-06-01 | Norrel Road |  |  | 230 |  | New 230 kV delivery point | Planned | 9197916 | Facility Study |  | MS |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 9197916 | 0% |  | 0
A in MTEP16 | South | Entergy-MS | 11623 | 2017-01-09 | 21802 | 2016-07-25 | SwSta | 2016-12-31 | Gallman |  |  | 115 |  | Install 115 kV breakers at Gallman | Under Construction | 2988936 | Engineering |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2988936 | 0% |  | 0
A in MTEP16 | South | Entergy-MS | 11705 | 2017-01-09 | 21818 | 2016-08-24 | TX | 2017-12-31 | Wynndale |  |  | 115 | 13.8 | Install distribution facilities in switching station to serve area/customer load | Planned | 7789909 | Planning | 2016 | MS |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 7789909 | 0% |  | 0
A in MTEP16 | South | Entergy-MS | 11783 | 2017-01-09 | 21828 | 2017-06-22 | TX | 2020-06-01 | McAdams |  |  | 500 | 230 | Replace current autotransformers at McAdams with autotransformers that have at least a 700 MVA rating. | Planned | 6552959 | Facility Study |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 12633990.04 | -48.13% | Cost | 0
A in MTEP16 | South | Entergy-MS | 11783 | 2017-01-09 | 21829 | 2017-03-22 | TX | 2020-06-01 | McAdams |  |  | 500 | 230 | Replace current autotransformers at McAdams with autotransformers that have at least a 700 MVA rating. | Planned |  |  |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 0 | Planned | 0 | 0% |  | 1445
A in MTEP16 | South | Entergy-MS | 12015 | 2017-01-09 | 22086 | 2017-06-22 | TX | 2019-12-01 | Lakeover |  |  | 500 | 230 | Relocate existing 500/230kV transformer from McAdams to Lakeover | M3_Long Lead Materials | 8031288 |  |  | MS |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2020-01-01 | Planned | 6700000 | 19.87% | Full project scoping | -1
A in MTEP16 | South | Entergy-TX | 4620 | 2017-01-09 | 8777 | 2017-06-22 | CAP | 2017-06-29 | Kolbs 230 kV Substation |  |  | 230 |  | Add capacitor bank | Under Construction | 5896623 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 3000000 | 96.55% | Additional work required | 0
A in MTEP16 | South | Entergy-TX | 7930 | 2017-01-09 | 20186 | 2017-06-22 | Dist | 2018-12-15 | Heights |  |  | 230 | 34.5 | Construct new substation | Planned | 20604890 | Planning |  | TX |  |  | 75 | 75 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 14208000 | 45.02% | Scoping | -6
A in MTEP16 | South | Entergy-TX | 9806 | 2017-01-09 | 21180 | 2017-06-22 | TX | 2019-06-01 | Bryan 138 | Bryan 69 | 1 | 138 | 69 | Replace Auto | Planned | 8203862 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 8268000 | -0.7757% | Schedule | 0
A in MTEP16 | South | Entergy-TX | 9806 | 2017-01-09 | 21181 | 2016-05-02 | TX | 2019-06-01 | Bryan 138 | Bryan 69 | 2 | 138 | 69 | Replace Auto | Planned |  |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 0
A in MTEP16 | South | Entergy-TX | 9807 | 2017-01-09 | 21182 | 2017-06-22 | SwSta | 2018-12-01 | Pintail |  |  | 138 |  | New Switching Station | Planned | 9021735 | Planning |  | TX |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 9524000 | -5.274% |  | 0
A in MTEP16 | South | Entergy-TX | 9808 | 2017-01-09 | 21183 | 2017-06-22 | CAP | 2018-06-01 | Kirbyville |  |  | 69 |  | New Capacitor bank | Planned | 711171 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1000000 | -28.88% |  | 0
A in MTEP16 | South | Entergy-TX | 9809 | 2017-01-09 | 21184 | 2017-06-22 | LNrc | 2020-06-01 | Hull | Sour Lake |  | 69 |  | Upgrade Line | Planned | 36150351 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 30759000 | 17.53% | Scoping | 12
A in MTEP16 | South | Entergy-TX | 9810 | 2017-01-09 | 21185 | 2017-06-22 | LNrc | 2019-12-01 | Raywood | Daisetta | 1 | 69 |  | Upgrade Line | Planned | 7495170 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-01 | Planned | 8655000 | -13.4% |  | 0
A in MTEP16 | South | Entergy-TX | 9812 | 2017-01-09 | 21187 | 2017-06-26 | SwSta | 2020-06-01 | Garden |  |  | 230 |  | Build New Substation | Planned | 65938672 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 65835000 | 0.1575% | Schedule | 12
A in MTEP16 | South | Entergy-TX | 9813 | 2017-01-09 | 21188 | 2017-03-24 | LN | 2020-06-01 | Garden | Legend | 1 | 230 |  | Build new line | Planned |  |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 12
A in MTEP16 | South | Entergy-TX | 9814 | 2017-01-09 | 21189 | 2017-03-24 | SwSta | 2020-06-01 | Legend |  |  | 230 |  | Build New Substation | Planned |  |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 12
A in MTEP16 | South | Entergy-TX | 9817 | 2017-01-09 | 21192 | 2017-06-22 | CB | 2019-06-01 | Helbig |  |  | 230 |  | Add Circuit Breakers | Planned | 6766061 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 7196000 | -5.975% | Schedule | 6
A in MTEP16 | South | Entergy-TX | 9818 | 2017-01-09 | 21193 | 2017-06-22 | LNcnv | 2019-06-01 | Stowell | Himex | 1 | 138 |  | Convert line to 138 kV | Planned | 11662851 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 13600000 | -14.24% | Schedule | 0
A in MTEP16 | South | Entergy-TX | 9852 | 2017-01-09 | 21229 | 2017-06-22 | CB | 2017-05-31 | Grimes |  |  | 345 |  | Install new breaker | M5_In Service | 2622869 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1142000 | 129.7% | Schedule | -1
A in MTEP16 | South | Entergy-TX | 10823 | 2017-01-09 | 21668 | 2017-03-24 | SUB | 2017-02-17 | Moscow |  |  | 138 |  | Construct New Customer substation | M5_In Service | 4832408 | Facility Study |  | TX |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 7004002 | -31.01% |  | -4
A in MTEP16 | South | Entergy-TX | 11363 | 2017-01-09 | 21763 | 2017-06-22 | TEQ | 2017-12-31 | Hartburg |  |  | 500 |  | Re-position line bays Hartburg-Cottonwood 500 kV line 1 & Hartburg-Cypress 500 kV line | Planned | 3702894 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 2000000 | 85.14% | Schedule | 6
A in MTEP16 | West | GRE | 4378 | 2017-01-09 | 8387 | 2013-09-13 | CB | 2020-09-01 | Long Lake |  |  | 115 |  | Circuit breakers for new lines related to Hubbard-Potato Lake line | Planned | 835000 | Planning |  | MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-09-01 | Planned | 835000 | 0% |  | 0
A in MTEP16 | West | GRE | 4378 | 2017-01-09 | 8890 | 2016-08-11 | CB | 2017-04-01 | Hubbard |  |  | 115 |  | Circuit breakers for new lines to Cat River and Potato Lake | Planned | 1670000 | Planning |  | MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 1670000 | 0% |  | 0
A in MTEP16 | West | GRE | 4378 | 2017-01-09 | 8891 | 2017-06-27 | SUB | 2017-10-19 | Blueberry |  |  | 115 | 34.5 | New Blueberry 115/34.5 kV substation using Hubbard transformer | Planned | 2400000 | Planning |  | MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 2400000 | 0% |  | 6
A in MTEP16 | West | GRE | 4378 | 2017-01-09 | 20790 | 2017-06-27 | LN | 2017-05-02 | Blueberry | Red Eye |  | 115 |  | Construct a new 115 kV transmission line from the Blueberry substation to Koch Pipeline's new pumping substation (approximately 8 miles). | M5_In Service | 13655748.68 | Planning Preliminary |  | MN |  | 8 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 13655748.68 | 0% |  | 1
A in MTEP16 | West | GRE | 7884 | 2017-01-09 | 20114 | 2016-04-14 | SUB | 2018-12-10 | Riverview |  |  | 345 | 115 | Construct the new Riverview 345/115/69 kV substation directly off the CapX 345 kV line between the Melrose East and Millwood 69 kV substations. The transformers will be a 448 MVA, 345/115 kV transformer and a 70 MVA 115/69 MVA transformer. This substation will initially have two 345 line terminating breakers, a single 345 kV breaker on the high side of the transformer, two 69 kV line termination breakers in addition to a low side 69 kV breaker. The substation should be designed for future development and be laid out for nine 345 breaker (3 rows of 345 kV breakers in a breaker and half scheme), six 115 kV (2 rows of 115 kV breakers in a breaker and half scheme), and four 69 kV breakers in a straight bus configuration. | Planned | 13425055.97 | Planning Preliminary |  | MN |  |  | 448 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-10 | Planned | 13425055.97 | 0% |  | 0
A in MTEP16 | West | GRE | 7884 | 2017-01-09 | 20128 | 2016-04-14 | SUB | 2018-12-10 | Riverview |  |  | 115 | 69 | Construct the new Millwood (Riverview Road ) 345/115/69 kV substation directly off the CapX 345 kV line between the Melrose East and Millwood 69 kV substations. The transformers will be a 448 MVA, 345/115 kV transformer and a 70 MVA 115/69 MVA transformer. This substation will initially have two 345 line terminating breakers, a single 345 kV breaker on the high side of the transformer, two 69 kV line termination breakers in addition to a low side 69 kV breaker. The substation should be designed for future development and be laid out for nine 345 breaker (3 rows of 345 kV breakers in a breaker and half scheme), six 115 kV (2 rows of 115 kV breakers in a breaker and half scheme), and four 69 kV breakers in a straight bus configuration.. Please see the online diagram included in this PDR. This project will also be coordinated with Xcel Energy for rebuilding the existing Melrose-Millwood 69 kV line with 795 ACSS and 115 kV design. Desired in-service date is spring 2017. | Planned | 4583671.1 | Planning Preliminary |  | MN |  |  | 70 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-10 | Planned | 4583671.1 | 0% |  | 0
A in MTEP16 | West | GRE | 7884 | 2017-01-09 | 20129 | 2016-04-14 | LNrb | 2018-12-10 | Melrose | Riverview | 1 | 69 | 69 | Rebuild E Melrose to Millwood Tap 4.6 mile line. | Planned | 2042956.93 | Planning Preliminary |  | MN | 4.6 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-10 | Planned | 2042956.93 | 0% |  | 0
A in MTEP16 | West | GRE | 7896 | 2017-01-09 | 20133 | 2016-09-15 | LN | 2017-08-31 | Fish Trap Pumping Station |  | 1 | 115 | 115 | Construct a new 115 kV transmission line from the Wing River to Long Prairie ( #47 Line) 115 kV transmission line to Koch Pipeline?s new Fish Trap pumping substation (approximately 20 miles). | Planned | 10855000.26 | Planning Preliminary |  | MN |  | 20 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-08-31 | Planned | 10855000.26 | 0% |  | 0
A in MTEP16 | West | GRE | 10423 | 2017-01-09 | 21579 | 2017-06-27 | Dist | 2017-04-20 | Randolph |  |  | 115 |  | New distribution substation | Planned | 605154 | Planning |  | MN |  | 0.25 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-03-30 | Planned | 525000 | 15.27% | Land | 1
A in MTEP16 | West | GRE | 10424 | 2017-01-09 | 21580 | 2017-06-27 | Dist | 2018-06-08 | Zinran |  |  | 115 |  | New distribution substation | Planned | 1818663.27 | Planning |  | MN |  | 0.5 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-10-31 | Planned | 1000000 | 81.87% | Scope change | 8
A in MTEP16 | West | GRE | 11463 | 2017-01-09 | 21773 | 2016-10-20 | TEQ | 2016-10-12 | Leland Olds | Stanton | 1 | 230 |  | Replace 31RB3 jumpers to increase line rating above 313 MVA. | M5_In Service | 33033 | Planning |  | ND |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-11-01 | Planned | 33033 | 0% |  | -1
A in MTEP16 | West | GRE, MP | 4378 | 2017-01-09 | 8383 | 2017-06-27 | LN | 2017-05-02 | Hubbard | Blueberry | 1 | 115 |  | Build new 115 kV line from Hubbard to new Blueberry substation | M5_In Service | 10800000 | Planning |  | MN |  | 15 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 10800000 | 0% |  | 1
A in MTEP16 | Central | IPL | 9221 | 2017-01-09 | 20837 | 2017-01-12 | CB | 2016-12-31 | Southport |  |  | 138 |  | Replacement of 138 kV line breaker on 132-29 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9222 | 2017-01-09 | 20838 | 2017-01-12 | CB | 2016-12-31 | Thompson |  |  | 138 |  | Replacement of 138 kV line breaker on 132-77 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9222 | 2017-01-09 | 20840 | 2017-01-12 | CB | 2016-12-31 | Thompson |  |  | 138 |  | Replacement of 138 kV line breaker on 132-68 line due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9222 | 2017-01-09 | 20841 | 2017-01-12 | CB | 2016-12-31 | Thompson |  |  | 138 |  | Replacement of 138 kV bus-tie breaker due to results of annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9602 | 2017-01-09 | 20935 | 2017-01-12 | CB | 2016-12-31 | Mooresville |  |  | 138 |  | Replacement of 138 kV 132-84 Line breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9602 | 2017-01-09 | 20936 | 2017-01-12 | CB | 2016-12-31 | Mooresville |  |  | 138 |  | Replacement of 138 kV 132-24 Line breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 9602 | 2017-01-09 | 20937 | 2017-01-12 | CB | 2016-12-31 | Mooresville |  |  | 138 |  | Replacement of 138 kV bus-tie breaker due to results of J238 GIP and annual short circuit analysis; NERC TPL-001-4 requirements R2.3 and R2.8. | M5_In Service |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 11123 | 2017-01-09 | 21714 | 2016-04-26 | RLY | 2017-07-15 | Guion 345 kV |  |  | 345 |  | Addition of redundant relay on Guion 345kV south bus section to mitigate P55 contingency. | Planned |  |  |  | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-07-15 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 11523 | 2017-01-09 | 21784 | 2016-07-15 | LNup | 2021-06-30 | Stout CT | Stout North | 98 | 138 |  | Increase line rating to345 MVA | Planned |  |  |  | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2021-06-30 | Planned | 0 | 0% |  | 0
A in MTEP16 | Central | IPL | 11643 | 2017-01-09 | 21803 | 2016-07-29 | TX | 2017-06-01 | Stout North |  |  | 345 |  | Replace Failed Stout Auto | Under Construction |  |  |  | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-06-01 | Under Construction | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21050 | 2017-06-29 | SwSta | 2018-12-31 | White Pole Road | Switch Station |  | 69 | 69 | Construct a new 3 terminal switch station named White Pole Road. | Planned | 2341176 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 2341176 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21051 | 2017-06-29 | TAP | 2018-12-31 | White Pole Road | Switch Station |  | 69 | 69 | 69 kV line taps for the new White Pole Road station | Planned | 540000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 540000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21052 | 2017-06-29 | LNcnv | 2018-12-31 | Guthrie | White Pole Road | 1 | 69 | 69 | Convert Guthrie - White Pole Rd to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 240000 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 240000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21053 | 2017-06-29 | LNcnv | 2018-12-31 | White Pole Raod | Hawkeye REC | 1 | 69 | 69 | Convert White Pole Rd - Hawkeye REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21054 | 2017-06-29 | LNcnv | 2018-12-31 | Hawkeye REC | Stuart REC Tap | 1 | 69 | 69 | Convert Hawkeye REC - Stuart REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) Add load break capability and SCADA controlled motor operators at Hawkeye REC. | Planned | 264000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 264000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21055 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart REC Tap | Stuart Muni South Tap | 1 | 69 | 69 | Convert Stuart REC Tap - Stuart Muni South Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21056 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart Muni South Tap | Stuart Muni South | 1 | 69 | 69 | Convert Stuart Muni South Tap - Stuart Muni South Sub to 69 kV (existing 34.5 kV line built to 69 kV construction | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21057 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart Muni South Tap | Stuart REC | 1 | 69 | 69 | Convert Stuart Muni South Tap - Stuart REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21058 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart REC Tap | Stuart Muni Tap | 1 | 69 | 69 | Convert Stuart REC Tap - Stuart Muni Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21059 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart Muni Tap | Stuart Muni | 1 | 69 | 69 | Convert Stuart Muni Tap - Stuart Muni to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 0.8 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21060 | 2017-06-29 | LNcnv | 2018-12-31 | Stuart Muni Tap | Diamondhead REC Tap | 1 | 69 | 69 | Convert Stuart Muni Tap - Diamondhead REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 8 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21061 | 2017-06-29 | LNcnv | 2018-12-31 | Diamondhead REC Tap | Diamondhead REC | 1 | 69 | 69 | Convert Diamondhead REC Tap - Diamondhead REC to 69 kV (existing 34.5 kV line built to 69 kV construction | Planned | 0 | Engineering |  | IA | 1.75 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21062 | 2017-06-29 | LNcnv | 2018-12-31 | Diamondhead REC Tap | Redfield Tap | 1 | 69 | 69 | Convert Diamondhead REC Tap - Redfield Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 1.85 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21063 | 2017-06-29 | LNcnv | 2018-12-31 | Redfield Tap | Redfield | 1 | 69 | 69 | Convert Redfield Tap - Redfield to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 0.7 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21064 | 2017-06-29 | LNcnv | 2018-12-31 | Redfield Tap | Panora Switch Station | 1 | 69 | 69 | Convert Redfield Tap - Panora Switch Station to 69 kV | Planned | 0 | Engineering |  | IA | 10 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21065 | 2017-06-29 | SwSta | 2018-12-31 | Paonra Switch Station | Switch Station |  | 69 | 69 | CIPCO will construct a new Panora 69 kV 3 terminal switch station | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21066 | 2017-06-29 | LNcnv | 2018-12-31 | Panora Switch Station | Guthrie | 1 | 69 | 69 | Convert Panora Switch Station - Guthrie to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 6 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21067 | 2017-06-29 | LNcnv | 2018-12-31 | Panora Switch Station | Panora REC | 1 | 69 | 69 | Convert Panora Switch Station - Panora REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 0.7 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21068 | 2017-06-29 | LNcnv | 2018-12-31 | Panora Switch Station | Panora Muni Tap | 1 | 69 | 69 | Convert Panora Switch Station - Panora Muni Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 5.72 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21069 | 2017-06-29 | LNcnv | 2018-12-31 | Panora Muni Tap | Panora Muni | 1 | 69 | 69 | Convert Panora Muni Tap - Panora Muni to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 0.61 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21070 | 2017-06-29 | LNcnv | 2018-12-31 | Panora Muni Tap | Panorama REC Tap | 1 | 69 | 69 | Convert Panora Muni Tap - Panorama REC Tap to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 1.57 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9664 | 2017-01-09 | 21071 | 2017-06-29 | LNcnv | 2018-12-31 | Panorama REC Tap | Panorama REC | 1 | 69 | 69 | Convert Panorama REC Tap - Panorama REC to 69 kV (existing 34.5 kV line built to 69 kV construction) | Planned | 0 | Engineering |  | IA | 0.8 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9665 | 2017-01-09 | 21037 | 2017-06-30 | SUB | 2018-12-31 | PCI | Substation |  | 69 | 69 | Convert PCI-Oak Hill to 69 kV operation | Planned | 12000 | Engineering | 2017 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 12000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9665 | 2017-01-09 | 21038 | 2017-06-30 | Dist | 2018-12-31 | Oak Hill | Substation |  | 69 | 69 | Convert to 69 kV operation | Planned | 0 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9665 | 2017-01-09 | 21039 | 2017-06-30 | LN | 2018-12-31 | PCI | Oak Hill | 1 | 69 | 69 | Convert to 69 kV operation (already built for 69 kV). | Planned | 21600 | Engineering | 2015 | IA | 4.5 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 21600 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21027 | 2017-06-30 | LNcnv | 2019-12-31 | Emerald Isle | Harrison | 1 | 69 | 69 | Convert Emerald Isle-Harrison line to 69 kV operation (already built for 69 kV) | Planned | 240000 | Engineering | 2015 | IA | 3.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 240000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21028 | 2017-06-30 | SUB | 2019-12-31 | Emerald Isle | Substation |  | 69 | 69 | Add 69 kV terminal at Emerald Isle | Planned | 443671 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 443671 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21029 | 2017-06-30 | LNcnv | 2019-12-31 | Harrison | Taylor | 1 | 69 | 69 | Convert Harrison-Taylor line to 69 kv operation (already built for 69 kV) | Planned | 0 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21030 | 2017-06-30 | Dist | 2019-12-31 | Taylor | Substation |  | 69 | 69 | New Taylor 69kV/distribution substation | Planned |  | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21032 | 2017-06-30 | LNcnv | 2019-12-31 | Taylor | Beverly | 1 | 69 | 69 | Convert the Beverly-Taylor line to 69kV operation | Planned | 1502754 | Engineering | 2015 | IA | 5.15 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 1502754 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21033 | 2017-06-30 | LNrb | 2019-12-31 | PCI | Beverly | 1 | 69 | 69 | Rebuild a portion of the PCI-Beverly line to double circuit 69 kV. | Planned | 1466754 | Engineering | 2015 | IA | 1.2 |  | 103 MVA | 103 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 1466754 | 0% |  | 12
A in MTEP16 | West | ITCM | 9666 | 2017-01-09 | 21034 | 2017-06-30 | SUB | 2019-12-31 | Beverly | Substation |  | 69 | 69 | Add two new 69 kV line terminals and a 69 kV bus tie breaker at the Beverly substation. | Planned | 1461539 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 1461539 | 0% |  | 12
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 20989 | 2017-06-30 | BUS | 2018-02-15 | Wapello | Substation |  | 161 | 69 | Rebuild the 161kV to breaker and 1/2 design and upgrade 69kV ring bus. | Planned | 9094680 | Engineering | 2015 | IA |  |  | 558 MVA | 558 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 9094680 | 0% |  | 2
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 21634 | 2017-06-30 | SUB | 2018-02-15 | OGS | Substation |  | 161 | 161 | Upgrades required at OGS for the Wapello Co upgrades | Planned | 7985 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 7985 | 0% |  | 2
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 21635 | 2017-06-30 | LNup | 2018-02-15 | OGS | Wapello Co | 1 | 161 | 161 | Line work for sub reconfiguration. | Planned | 550200 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 550200 | 0% |  | 2
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 21636 | 2017-06-30 | LNup | 2018-02-15 | Appanoose County | Wapello Co | 1 | 161 | 161 | Line work for sub reconfiguration. | Planned | 118200 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 118200 | 0% |  | 2
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 21637 | 2017-06-30 | LNup | 2018-02-15 | OGS | Wapello Co | 2 | 161 | 161 | Line work for sub reconfiguration | Planned | 118200 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 118200 | 0% |  | 2
A in MTEP16 | West | ITCM | 9667 | 2017-01-09 | 21638 | 2017-06-30 | LNup | 2018-02-15 | Jefferson | Wapello Co | 1 | 161 | 161 | Line work for sub reconfiguration. | Planned | 226200 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 226200 | 0% |  | 2
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21079 | 2016-01-29 | SUB | 2019-12-31 | New Hills area | Substation |  | 345 | 69 | Construct a new substation in the Hills area. | Planned | 19029110 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 19029110 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21080 | 2015-09-11 | TX | 2019-12-31 | New Hills area sub | Transformer | 1 | 345 | 161 | Install a new 345/161 kV 450 MVA transformer. | Planned |  |  |  | IA |  |  | 450 MVA |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21081 | 2015-09-11 | TX | 2019-12-31 | New Hills area | Transformer | 1 | 161 | 69 | CIPCO will install a new 161/69kV 150 MVA tranformer | Planned |  |  |  | IA |  |  | 150 MVA |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21082 | 2015-09-11 | SwSta | 2019-12-31 | ClearCreek | Switch Station |  | 69 | 69 | CIPCO will construct a new switch station | Planned |  |  |  | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21083 | 2015-09-11 | LN | 2019-12-31 | New Hills area | North Liberty | 1 | 161 | 161 | CIPCO will own a new 161 kV line from the new Hills area sub to the new North Liberty sub. The new line will be double circuit with a new 69 kV line owned by ITC. | Planned |  |  |  | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21084 | 2016-01-29 | LN | 2019-12-31 | New Hills area | Clear Creek | 1 | 69 | 69 | New ITC owned 69 kv line double circuit with the new Hills area to North Liberty 161 kv line owned by CIPCO. | Planned | 8678400 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 8678400 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21085 | 2015-09-11 | SUB | 2019-12-31 | New North Liberty | Substation |  | 161 | 69 | New CIPCO owned 161/69 kV North Liberty sub | Planned |  |  |  | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21086 | 2015-09-11 | TX | 2019-12-31 | New North Liberty | Transformer | 1 | 161 | 69 | New CIPCO owned 161/69 kV 200 MVA transformer. | Planned |  |  |  | IA |  |  | 200 MVA | 200 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21087 | 2016-01-29 | LN | 2022-12-31 | North Liberty | Fairfax | 1 | 161 | 161 | New 161 kV line from North Liberty-Fairfax (double circuit with new North Liberty-Tharp 69 kV line). | Planned | 27788400 | Engineering | 2015 | IA |  |  | 446 MVA |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2022-12-31 | Planned | 27788400 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21088 | 2016-01-29 | LN | 2022-12-31 | North Liberty | Tharp | 1 | 69 | 69 | Re-build existing North Liberty REC - Tharp line (double circuit with new North Liberty - Fairfax 161 kV) | Planned | 11080800 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2022-12-31 | Planned | 11080800 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21089 | 2016-01-29 | SUB | 2022-12-31 | Fairfax | Substation |  | 161 | 161 | Add a 161 kV terminal for the new North Liberty-Fairfax 161 kV line | Planned | 904828 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2022-12-31 | Planned | 904828 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21090 | 2016-01-29 | SwSta | 2025-12-31 | Homestead | Switch Station |  | 69 | 69 | New Homestead 69 kV switching station | Planned | 3979450 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 3979450 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21091 | 2016-01-29 | SwSta | 2025-12-31 | Conroy | Switch Station |  | 69 | 69 | New Conroy 69 kV switching station | Planned | 3979450 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 3979450 | 0% |  | 0
A in MTEP16 | West | ITCM | 9668 | 2017-01-09 | 21092 | 2015-09-11 | LN | 2025-12-31 | Conroy | Homestead | 1 | 69 | 69 | New CIPCO owned Conroy-Homestead 69 kV line | Planned |  |  |  | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9669 | 2017-01-09 | 21047 | 2016-05-24 | TAP | 2017-11-17 | St. Ansgar Industrial | Substation |  | 69 | 69 | 69 kV line taps for the new 69/distribution St. Ansgar Industrial substation. | Planned | 213240 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-11-17 | Planned | 213240 | 0% |  | 0
A in MTEP16 | West | ITCM | 9669 | 2017-01-09 | 21048 | 2016-05-24 | SUB | 2017-11-11 | St. Ansgar Industrial | Substation |  | 69 | 69 | ITCM has proposed the addition of a box structure, line breakers, and the construction of line taps to reach the proposed location. Due to the size of the load, and having two transformers in the future to back-up the load, ITCM has proposed the addition of the breakers as opposed to tapping the line with no breakers. The in-service date spans from the beginning of the year to a date prior to the 2017 summer peak season, actual in-service date will be dependent on Alliant Energy progress. | Planned | 2295577 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-11-11 | Planned | 2295577 | 0% |  | 0
A in MTEP16 | West | ITCM | 9670 | 2017-01-09 | 21049 | 2015-11-18 | SUB | 2020-12-31 | Columbus Junction | Substation |  | 69 | 69 | Install a second 69 kV breaker at Columbus Jct | Planned | 932101 | Engineering | 2015 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2020-12-31 | Planned | 932101 | 0% |  | 0
A in MTEP16 | West | ITCM | 9671 | 2017-01-09 | 20990 | 2016-12-12 | CAP | 2016-12-08 | Amber Creamery | Capacitor |  | 69 | 69 | Add a 7.2 MVAR cap bank at the Amber Creamery substation. | M5_In Service | 515076 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 515076 | 0% |  | 0
A in MTEP16 | West | ITCM | 9672 | 2017-01-09 | 20992 | 2017-06-30 | SUB | 2020-12-31 | 76th AVE SW | Substation |  | 69 | 69 | Construct a new four (4) terminal, four (4) break 69 kV substation southeast of the city of Cedar Rapids | Planned | 3757232 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 3757232 | 0% |  | 12
A in MTEP16 | West | ITCM | 9672 | 2017-01-09 | 20993 | 2017-06-30 | LN | 2020-12-31 | PCI | Tharp | 1 | 69 | 69 | Tap PCI-Tharp 69kV line for 2 of the new line terminals | Planned | 149536 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 149536 | 0% |  | 12
A in MTEP16 | West | ITCM | 9672 | 2017-01-09 | 20994 | 2017-06-30 | LN | 2020-12-31 | Prairie Creek | CKT 0210 | 1 | 69 | 69 | Tap the 69kV Prairie Creek CKT 0210 | Planned | 149536 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 149536 | 0% |  | 12
A in MTEP16 | West | ITCM | 9672 | 2017-01-09 | 20995 | 2017-06-30 | CAP | 2020-12-31 | 76th AVE SW | Capacitor |  | 69 | 69 | Install a 13.2MVAR cap bank at the new 76th AVE SW substation | Planned | 0 | Engineering | 2015 | IA |  |  | 13.2 MVAR |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21072 | 2016-11-08 | SUB | 2017-12-01 | Huntley | Substation |  | 69 | 69 | Relocate the 161/69 kV T1 Adams transformer to Huntley and replace the 161/69 kV T2 transformer and 69 kV breakers to the new Huntley substation that is currently proposed for the MVP #3 project. | Under Construction | 5014447 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 5014447 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21073 | 2016-11-08 | SUB | 2017-12-01 | Winnebago Jct. | Substation |  | 161 | 69 | Retire the Winnebago Jct 69kV portion of the sub. | Under Construction | 300000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 300000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21074 | 2016-11-08 | LN | 2017-12-01 | Huntley | Winnebago Local | 1 | 69 | 69 | Connect the new Huntley 69kV to the Winnebago Local 69kV sub | Under Construction | 676000 | Engineering | 2015 | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 676000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21075 | 2016-11-08 | LN | 2017-12-01 | Huntley | Walters | 1 | 69 | 69 | Connect the new Huntley sub to the Walter 69 kV sub | Under Construction | 1792800 | Engineering | 2015 | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 1792800 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21076 | 2016-11-08 | LN | 2017-12-01 | Huntley | Blue Earth | 1 | 69 | 69 | Connect the Huntley 69kV to the Blue Earth 69 kV sub | Under Construction | 1272000 | Engineering | 2015 | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 1272000 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21077 | 2016-11-08 | TX | 2017-12-01 | Huntley | Transformer | 1 | 161 | 69 | Relocate the Winnebago Jct 161/69 kV 75 MVA transformer to the new Huntley sub. | Under Construction | 0 | Engineering | 2015 | IA |  |  | 75 MVA | 75 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9706 | 2017-01-09 | 21078 | 2016-11-08 | TX | 2017-12-01 | Huntley | Transformer | 2 | 161 | 69 | Relocate the Adams 161/69 kV 75 MVA transformer to the new Huntley sub for transformer #2 and retire the Winnebago 30 MVA unit. | Under Construction | 0 | Engineering | 2015 | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 12
A in MTEP16 | West | ITCM | 9711 | 2017-01-09 | 21044 | 2017-06-30 | BUS | 2017-06-05 | Traer | Substation |  | 161 | 161 | Convert the 161 kV to a ring bus | M5_In Service | 3667882 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 3667882 | 0% |  | -6
A in MTEP16 | West | ITCM | 9711 | 2017-01-09 | 21045 | 2017-06-30 | SUBmisc | 2017-06-05 | Dysart | Substation |  | 161 | 161 | Upgrade 161 kV switch | M5_In Service | 54000 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 54000 | 0% |  | -6
A in MTEP16 | West | ITCM | 9711 | 2017-01-09 | 21759 | 2017-06-30 | TAP | 2017-06-05 | Traer | 161 kV line taps |  | 161 | 161 | Reroute 161 kV lines and new dead ends near the Traer substation for the new ring bus configuration. | Planned | 1344000 | Engineering | 2016 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1344000 | 0% |  | -6
A in MTEP16 | West | ITCM | 9712 | 2017-01-09 | 21046 | 2015-09-10 | SUB | 2017-06-01 | Burlington Gnerating Station | Substation |  | 161 | 69 | Modify the Burlington Generating Station’s substation for increased reliability and to accommodate the required NERC PRC-005 maintenance testing of the BGS relaying schemes. Replace 161 kV circuit switcher 1272 with a breaker to isolate the BGS - Denmark #2 161 kV line from 161/69 kV T2 transformer. The 69 kV motor-operated switches will be replaced with 69 kV main circuit breakers to create separately relayed 161/69 kV transformer and 69 kV bus sections. Additional three-phase 161 kV voltage transformers will be added. A new control enclosure will be added outside the BGS power plant. All ITC relaying will be replaced and be installed in this new enclosure. The existing schemes in the BGS plant control room will be retired and removed. | Planned | 3114346 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 3114346 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21291 | 2017-06-29 | SwSta | 2018-12-31 | Lyon | Switch Station |  | 69 | 69 | Construct a new 3 terminal switch station near Lyon (official name TBD). | Planned | 3420000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 3420000 | 0% |  | -12
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21292 | 2016-05-26 | LNcnv | 2019-12-31 | Doud | Ridgeport REc | 1 | 69 | 69 | Doud to Ridgeport REC 34.5 to 69 kV line conversion | Planned | 0 | Engineering | 2015 | IA | 11.15 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21293 | 2016-05-26 | LNcnv | 2019-12-31 | Ridgeport REC | Stratford REC Tap | 1 | 69 | 69 | Ridgeport REC to Stratford REC Tap 34.5 to 69 kV line conversion | Planned | 0 | Engineering | 2015 | IA | 4.94 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21294 | 2016-05-26 | LNcnv | 2019-12-31 | Stratford REC Tap | Stratford REC | 1 | 69 | 69 | Stratford REC Tap to Startford REC 34.5 to 69 kV line conversion | Planned | 0 | Engineering | 2015 | IA | 2.7 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21296 | 2016-05-26 | LNcnv | 2019-12-31 | Stratford REC Tap | Stanhope Muni Tap | 1 | 69 | 69 | Startford REC Tap to Stanhoep Muni Tap 34.5 to 69 kV line conversion | Planned | 0 | Engineering | 2015 | IA | 4.98 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21297 | 2016-05-26 | LNcnv | 2019-12-31 | Stanhope Muni Tap | Stanhope Muni | 1 | 69 | 69 | Stanhope Muni Tap to Stanhope Muni 34.5 to 69 kV line conversion | Planned | 420974 | Engineering | 2015 | IA | 0.25 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 420974 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21298 | 2016-05-26 | LNcnv | 2019-12-31 | Stanhope Muni Tap | Jewell | 1 | 69 | 69 | Stanhope Muni Tap to Jewell 34.5 to 69 kV line conversion | Planned | 257505 | Engineering | 2015 | IA | 10.22 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 257505 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21300 | 2016-05-26 | LNcnv | 2019-12-31 | Jewell | Lyon | 1 | 69 | 69 | Jewell to Lyon Breaker Station 34.5 to 69 kV line conversion | Planned | 0 | Engineering | 2015 | IA | 0.96 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21631 | 2016-05-26 | LN | 2019-12-31 | Boone CKT 2230 |  | 1 | 69 | 69 | Retire the 34kV Boone CKT 2230. | Planned | 360000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 360000 | 0% |  | 0
A in MTEP16 | West | ITCM | 9714 | 2017-01-09 | 21632 | 2016-05-26 | SUB | 2019-12-31 | Lyon | Substation |  | 69 | 69 | Retire the old Lyon 34kV substation. | Planned | 180000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 180000 | 0% |  | 0
A in MTEP16 | West | ITCM | 9901 | 2017-01-09 | 21306 | 2015-11-18 | SUB | 2018-12-31 | Kneedler | Substation |  | 69 | 69 | New sub north of Mt. Ayr instead of rebuilding the Mount Ayr 69 kV substation. | Planned | 4291794 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 4291794 | 0% |  | 0
A in MTEP16 | West | ITCM | 9901 | 2017-01-09 | 21752 | 2016-05-24 | TAP | 2018-12-31 | Mt Ayr (Kneedler) | Substation |  | 69 | 69 | 69kV line tap work for the new Kneedler substation | Planned | 652800 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 652800 | 0% |  | 0
A in MTEP16 | West | ITCM | 9901 | 2017-01-09 | 21753 | 2016-05-24 | CAP | 2018-12-31 | Mt Ayr (Kneedler) | Substation |  | 69 | 69 | Add a 21.42 MVAr cap at Kneedler sub. (Three stages of 7.1 MVAr) | Planned | 0 | Engineering | 2105 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 9904 | 2017-01-09 | 21311 | 2015-11-18 | SUB | 2019-12-31 | Appanoose County | Substation |  | 161 | 69 | Due to a lack of voltage support in Southwest Iowa and an aging transformer at Appanoose County substation, ITC will replace it with a unit equipped with a Load Tap Changer (LTC). The 100 MVA (equipped with a LTC) 161:69kV transformer at Fernald will be relocated to Appanoose County after the MGS upgrades are completed. In addition, to increase reliability, ITC will rebuild the existing 161kV bus to a ring configuration. | Planned | 4944594 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 4944594 | 0% |  | 0
A in MTEP16 | West | ITCM | 9907 | 2017-01-09 | 21315 | 2016-05-26 | LNrb | 2022-12-31 | Summit | Dovray | 1 | 69 | 69 | Rebuild ~12.9 miles of old line to new T2-4/0 ACSR | Planned | 9162091 | Engineering | 2015 | MN | 12.89 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2022-12-31 | Planned | 9162091 | 0% |  | 0
A in MTEP16 | West | ITCM | 9908 | 2017-01-09 | 21316 | 2016-05-26 | LNrb | 2023-12-31 | Dovray | Fulda |  | 69 | 69 | Rebuild 69kV line from Dovrey substation to the Fulda Junction | Planned | 9410124 | Engineering | 2015 | MN | 14.5 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2023-12-31 | Planned | 9410124 | 0% |  | 0
A in MTEP16 | West | ITCM | 9910 | 2017-01-09 | 21318 | 2016-05-26 | LNrb | 2024-12-31 | Fulda Junction | Heron Lake | 1 | 69 | 69 | Rebuild 69kV line from Fulda Junction to Heron Lake | Planned | 14976652 | Engineering | 2015 | MN | 20.14 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2024-12-31 | Planned | 14976652 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21353 | 2016-11-30 | TX | 2016-11-07 | Fernald | Transformer | 1 | 161 | 69 | Replace existing 161/69 kV transformer with 150 MVA unit | M5_In Service | 2392800 | Engineering | 2015 | IA |  |  | 150 MVA | 150 MVA | GIP |  |  | N | N | NT | Externally Driven | A | 2016-11-30 | Planned | 2392800 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21354 | 2016-05-25 | TX | 2016-04-22 | Jasper | Transformer | 1 | 161 | 69 | Replace existing 161/69 kV transformer with 150 MVA unit | M5_In Service | 2392800 | Engineering | 2015 | IA |  |  | 150 MVA | 150 MVA | GIP |  |  | N | N | NT | Externally Driven | A | 2016-04-22 | M5_In Service | 2392800 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21355 | 2016-03-30 | TX | 2016-02-01 | Newton | Transformer | 1 | 161 | 69 | Replace existing 161/69 kV transformer with 150 MVA unit | M5_In Service | 2392800 | Engineering | 2015 | IA |  |  | 150 MVA | 150 MVA | GIP |  |  | N | N | NT | Externally Driven | A | 2016-02-01 | M5_In Service | 2392800 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21356 | 2016-03-30 | LNup | 2015-09-15 | Marshalltown | Blairstown Junction | 1 | 115 | 115 | Raise/Replace structures to allow operation at 90 MVA | M5_In Service | 1560000 | Engineering | 2015 | IA |  |  | 90 MVA | 90 MVA | GIP |  |  | N | N | Y | Externally Driven | A | 2015-09-15 | M5_In Service | 1560000 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21357 | 2017-02-23 | LNrc | 2016-11-16 | Jasper | Laurel | 1 | 161 | 161 | Replace conductor to allow operation at 361 MVA | M5_In Service | 151037 | Engineering | 2015 | IA |  |  | 361 MVA | 361 MVA | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-31 | Planned | 151037 | 0% |  | -1
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21358 | 2016-11-30 | LNup | 2016-11-04 | Jasper | Newton | 1 | 161 | 161 | Raise structure to allow operation at 276 MVA | M5_In Service | 108000 | Engineering | 2015 | IA |  |  | 276 MVA | 276 MVA | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-31 | Planned | 108000 | 0% |  | -1
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21359 | 2017-02-23 | LNrb | 2017-03-30 | Newton | Prairie City | 1 | 69 | 69 | Rebuild ITCM portion of jointly-owned line with T2-4/0 conductor. Rating to increase to MEC limit of 40 MVA | Under Construction | 4647247 | Engineering | 2015 | IA |  |  | 40 MVA |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-03-30 | Planned | 4647247 | 0% |  | 0
A in MTEP16 | West | ITCM | 9937 | 2017-01-09 | 21640 | 2016-01-29 | SUB | 2015-12-15 | Marshalltown | Substation |  | 161 | 161 | Network upgrades for the J233 project | M5_In Service | 4095731 | Engineering | 2015 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2015-12-15 | M5_In Service | 4095731 | 0% |  | 0
A in MTEP16 | West | ITCM | 9939 | 2017-01-09 | 21361 | 2016-10-20 | LNrb | 2016-10-17 | Jasper | Aurora Heights | 1 | 69 | 69 | Rebuild line with T2-477 ACSR conductor to allow operation of line at 140 MVA | M5_In Service | 3720000 | Engineering | 2015 | IA |  |  | 140 NVA | 140 MVA | GIP |  |  | N | N | NT | Externally Driven | A | 2016-12-31 | Planned | 3720000 | 0% |  | -2
A in MTEP16 | West | ITCM | 9941 | 2017-01-09 | 21362 | 2016-11-01 | TEQ | 2016-06-29 | Traer | Traer Tap | 1 | 69 | 69 | Upgrade terminal/replace breaker to increase rating to bus conductor limit of 61 MVA | M5_In Service | 293449 | Engineering | 2015 | IA |  |  | 61 MVA | 61 MVA | GIP |  |  | N | N | NT | Externally Driven | A | 2016-06-01 | Planned | 293449 | 0% |  | 0
A in MTEP16 | West | ITCM | 9985 | 2017-01-09 | 21411 | 2017-06-30 | LNrb | 2020-05-04 | Newhall | Willaimsburg | 1 | 161 | 161 | Rebuild Williamsburg 115kV tap to 161kV | Planned | 40174153 | Engineering | 2015 | IA | 23 | 3 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 40174153 | 0% |  | 17
A in MTEP16 | West | ITCM | 9988 | 2017-01-09 | 21409 | 2015-09-15 | SwSta | 2018-12-31 | Newhall | Switch Station |  | 161 | 161 | Construct 3 position 161kV Breaker Station | Planned | 6924478 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 6924478 | 0% |  | 0
A in MTEP16 | West | ITCM | 9988 | 2017-01-09 | 21757 | 2016-05-26 | TAP | 2018-12-31 | Newhall | Line Taps |  | 161 | 161 | Construct 161kV line taps for 3 position 161kV Breaker Station | Planned | 1166404 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1166404 | 0% |  | 0
A in MTEP16 | West | ITCM | 10022 | 2017-01-09 | 21434 | 2016-05-26 | SUB | 2019-12-31 | Lisbon North | Substation | 1 | 69 | 69 | Two (2) 69 kV breakers and associated equipment will be installed at the Lisbon North substation | Planned | 598171 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 598171 | 0% |  | 0
A in MTEP16 | West | ITCM | 10022 | 2017-01-09 | 21435 | 2017-06-30 | SUB | 2021-12-31 | PCI | Substation | 1 | 69 | 69 | A 69 kV breaker and associated equipment will be installed at the PCI substation | Planned | 321361 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 321361 | 0% |  | 24
A in MTEP16 | West | ITCM | 10022 | 2017-01-09 | 21436 | 2016-05-26 | LN | 2019-12-31 | PCI | 76th AVE (Eagle) | 1 | 69 | 69 | approximately 0.6 mile of new 69 kV transmission line will be constructed to complete the PCI to 76th Ave circuit | Planned | 2037600 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 2037600 | 0% |  | 0
A in MTEP16 | West | ITCM | 10022 | 2017-01-09 | 21437 | 2016-05-26 | LNup | 2019-12-31 | 76th AVE (Eagle) | Tharp | 1 | 69 | 69 | OPGW will need to be installed. | Planned | 2175600 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 2175600 | 0% |  | 0
A in MTEP16 | West | ITCM | 10022 | 2017-01-09 | 21633 | 2016-05-26 | LNcnv | 2019-12-31 | PCI | Mt. Vernon | 1 | 69 | 69 | Convert to 69kV operation. | Planned | 661200 | Engineering | 2015 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 661200 | 0% |  | 0
A in MTEP16 | West | ITCM | 10023 | 2017-01-09 | 21441 | 2017-02-24 | LN | 2017-12-31 | ITCM Asset Blanket for 2017 | Throughout system |  | 345 | 69 | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | Under Construction | 37200000 | Engineering | 2015 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 37200000 | 0% |  | 0
A in MTEP16 | West | ITCM | 10023 | 2017-01-09 | 21442 | 2016-05-25 | LN | 2018-12-31 | ITCM Asset Blanket for 2018 | Throughout system |  | 345 | 69 | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | Planned | 37200000 | Engineering | 2015 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 37200000 | 0% |  | 0
A in MTEP16 | West | ITCM | 10023 | 2017-01-09 | 21443 | 2016-05-25 | LN | 2019-12-31 | ITCM Asset Blanket for 2019 | Throughout system |  | 345 | 69 | Replace aging and outdated equipment on a cycle that will ensure each system is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and will typically use longer maintenance intervals which reduces maintenance costs. Equipment is commonly equipped with better monitoring and alarming functionality giving improved remote supervision. | Planned | 37200000 | Engineering | 2015 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 37200000 | 0% |  | 0
A in MTEP16 | West | ITCM | 10024 | 2017-01-09 | 21438 | 2015-09-15 | LN | 2019-12-31 | Blanket for Customer Interconnections under $1 million for 2019 | Throughout system |  | 345 | 69 | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | Planned | 2000000 | Engineering | 2015 | IA,MN,IL |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 2000000 | 0% |  | 0
A in MTEP16 | West | ITCM | 10268 | 2017-01-09 | 21511 | 2016-05-25 | SUB | 2017-04-30 | Dubuque 8th Street | Substation |  | 69 | 69 | Sub upgrades associated with the Alliant Energy distribution transformer change outs. | Planned | 1290000 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 1290000 | 0% |  | 0
A in MTEP16 | West | ITCM | 10268 | 2017-01-09 | 21512 | 2015-10-28 | LN | 2017-04-30 | Dubuque 8th Street | Bunker Hill | 1 | 69 | 69 | Replcace guyed structure with self-suporting structure. | Planned | 156697 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 156697 | 0% |  | 0
A in MTEP16 | West | ITCM | 10268 | 2017-01-09 | 21513 | 2015-10-28 | LN | 2017-04-30 | Dubuque 8th Street | Sandridge | 1 | 69 | 69 | Re-terminate Sandridge 69kV line. | Planned | 156696 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 156696 | 0% |  | 0
A in MTEP16 | West | ITCM | 10269 | 2017-01-09 | 21514 | 2016-05-25 | LNrb | 2017-12-31 | Lore | Hickory Creek | 1 | 161 | 161 | Rebuild 6.81 miles of the Lore-Hiclory Creek 161 kV line. | Planned | 12471467 | Engineering | 2015 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 12471467 | 0% |  | 0
A in MTEP16 | West | ITCM | 10269 | 2017-01-09 | 21515 | 2016-02-18 | TEQ | 2017-12-31 | Lore | Hickory Creek | 1 | 161 | 161 | Upgrade the Lore 161kV terminal and remove the wave trap | Planned | 127980 | Engineering | 2016 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 127980 | 0% |  | 0
A in MTEP16 | West | ITCM | 10269 | 2017-01-09 | 21639 | 2016-02-18 | TEQ | 2017-12-31 | Hickory Creek | Substation |  | 161 | 161 | Remove the wave trap | Planned | 101400 | Engineering | 2016 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 101400 | 0% |  | 0
A in MTEP16 | West | ITCM | 10303 | 2017-01-09 | 21559 | 2015-11-05 | SUB | 2017-12-31 | Williamsburg | Substation |  | 161 | 34 | The two aging and miss-matched 115/34.5kV transformers will be replaced with a newer and larger 161/36kV transformer from the Hiawatha Substation. This will provide an increased level of reliability to Williamsburg by serving the high-side from a newly rebuilt and shorter 161kV line compared to an older and longer 115kV line. | Planned | 1204368 | Engineering | 2015 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 1204368 | 0% |  | 0
A in MTEP16 | West | ITCM | 10303 | 2017-01-09 | 21560 | 2015-11-05 | LN | 2017-12-30 | Parnell | Williamsburg | 1 | 161 | 161 | To provide a reliable conversion to 69kV the 34.5kV will need temporary configurations to provide a reliable transition. The Williamsburg 115kV high side will be converted to 161kV. | Planned | 0 | Engineering |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-30 | Planned | 0 | 0% |  | 0
A in MTEP16 | West | ITCM | 11163 | 2017-01-09 | 21722 | 2017-06-30 | SUB | 2018-05-04 | Ft. Madison Devils Creek | Substation |  | 69 |  | New Ft. Madison Devils Creek Distribution Substation | Planned | 1941853 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 1718107 | 13.02% | Additional relaying and OPGW fiber was required. | 5
A in MTEP16 | West | ITCM | 11163 | 2017-01-09 | 21723 | 2017-06-30 | LN | 2018-05-04 | Ft. Madison Devils Creek | Substation |  | 69 |  | Line work for new 69kV line taps to the new Devil's Creek distribution substation. | Planned | 680596 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 260596 | 161.2% | Additional 1 mile of OPGW fiber is required for adequate protection. | 5
A in MTEP16 | West | ITCM | 11163 | 2017-01-09 | 21724 | 2017-06-30 | LN | 2018-05-04 | Viele 9660 Ckt | Viele 9660 Ckt | 1 | 69 |  | Retire the Viele 9660 Ckt (~3.6 miles) and the Viele bkr 9660 | Planned | 38333 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 38333 | 0% |  | 5
A in MTEP16 | West | ITCM | 11163 | 2017-01-09 | 21725 | 2017-06-30 | SUB | 2018-05-04 | Dial | Substation |  | 69 |  | Retire the Dial substation. | Planned | 9187 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 9187 | 0% |  | 5
A in MTEP16 | West | ITCM | 11164 | 2017-01-09 | 21726 | 2017-06-29 | SUB | 2017-04-26 | Oelwein Hub | New Substation |  | 69 |  | New Oelwein Hub Distribution Substation | M5_In Service | 2067518 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 2067518 | 0% |  | 0
A in MTEP16 | West | ITCM | 11164 | 2017-01-09 | 21727 | 2017-06-29 | CAP | 2018-04-30 | Oelwein | Capacitor |  | 69 |  | Install new 11.2 MVAr capacitor at the Oelwein Substation | Planned | 602509 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 602509 | 0% |  | 12
A in MTEP16 | West | ITCM | 11164 | 2017-01-09 | 21728 | 2017-06-29 | TEQ | 2017-04-26 | Hazleton | Substation |  | 69 |  | Upgrade terminal equipment at Hazleton on breakers 940, 941, and 947. | M5_In Service | 120600 | Engineering | 2016 | IA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 120600 | 0% |  | 0
A in MTEP16 | West | ITCM | 11164 | 2017-01-09 | 21729 | 2017-06-29 | LNrb | 2017-04-26 | Hazleton | Oelwein | 1 | 69 |  | Rebuild 1.42 miles of the existing Hazleton-Oelwein 69kV line due to condition. | M5_In Service | 3526841 | Engineering | 2016 | IA | 1.42 |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 3526841 | 0% |  | 0
A in MTEP16 | West | ITCM | 11763 | 2017-01-09 | 21823 | 2016-08-16 | SwSta | 2017-09-01 | Irvine | Switch Station |  | 161 | 161 | Build a new 161 kV three terminal switch station tapping the Beacon-Poweshiek 161 kV line. | Planned | 4277540 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 4277540 | 0% |  | 0
A in MTEP16 | West | ITCM | 11763 | 2017-01-09 | 21824 | 2016-08-16 | TAP | 2017-09-01 | Beacon | Irvine | 1 | 161 | 161 | Install 161 kV line taps for the new Irvine Switch Station. | Planned | 480000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 480000 | 0% |  | 0
A in MTEP16 | West | ITCM | 11763 | 2017-01-09 | 21825 | 2016-08-16 | TAP | 2017-09-01 | Irvine | Poweshiek | 1 | 161 | 161 | Install 161 kV line taps for the new Irvine Switch Station. | Planned | 480000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 480000 | 0% |  | 0
A in MTEP16 | West | ITCM | 11763 | 2017-01-09 | 21827 | 2016-08-16 | LNup | 2017-09-01 | Beacon | Irvine | 1 | 161 | 161 | Raise the structures on the Beacon-Irvine-Poweshiek 161 kV line. | Planned | 300000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 300000 | 0% |  | 0
A in MTEP16 | West | ITCM | 11883 | 2017-01-09 | 21852 | 2017-06-26 | SUBmisc | 2022-01-01 | Huntley |  |  | 345 |  | Substation modifications at Huntley | Planned | 2471713 |  |  | MN |  |  |  |  | MEP | Shared |  | Y | Y | Y | Top-Down | A | 2022-01-01 | M2a_Pre-Project Approval | 2471713 | 0% |  | 0
A in MTEP16 | West | ITCM, XEL | 11883 | 2017-01-09 | 21848 | 2017-06-26 | LN | 2022-01-01 | Huntley | Wilmarth |  | 345 |  | 38.5 miles of 345 kV Single Ckt | Planned | 103056574 |  |  | MN |  | 38.5 |  |  | MEP | Shared |  | Y | Y | Y | Top-Down | A | 2022-01-01 | M2a_Pre-Project Approval | 103056574 | 0% | Updated from scoping estimate | 0
A in MTEP16 | East | ITCT | 9685 | 2017-01-19 | 21008 | 2017-01-19 | LNup | 2018-06-01 | Jacob | St. Clair | 1 | 120 |  | Remediate the Sag Limit on Jacob-St. Clair 120 kV to 292 MVA (1405 Amp) | M2a_Pre-Project Approval | 139000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 139000 | 0% |  | -18
A in MTEP16 | East | ITCT | 9692 | 2017-01-09 | 21016 | 2017-06-27 | LNup | 2018-12-31 | Seneca | Spokane | 1 | 120 |  | Raise the Sag Limit on Seneca-Spokane 120 kV to 283 MVA (1362 Amp) | M3_Long Lead Materials | 339000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 339000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9883 | 2017-01-09 | 21271 | 2016-12-20 | CB | 2019-12-31 | Ironton |  |  | 120 |  | Install two 120 kV breakers to terminate the two River Rouge–Ironton 120 kV connections at Ironton | M2a_Pre-Project Approval | 910000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 910000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9884 | 2017-01-09 | 21272 | 2016-12-20 | LNup | 2019-12-31 | Belle River | Pontiac | 1 | 345 |  | Raise the Sag Limit on Belle River-Pontiac 345 kV to 1414 MVA (2366 Amp) | M2a_Pre-Project Approval | 340000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 340000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9887 | 2017-01-09 | 21276 | 2016-12-20 | LNup | 2019-12-31 | Pontiac | Wxom | 1 | 345 |  | Raise the Sag Limit on Pontiac-Wixom 345 kV to 1185 MVA (1983 Amp) | M2a_Pre-Project Approval | 305000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 305000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9900 | 2017-01-09 | 21301 | 2017-06-27 | LNup | 2018-12-31 | River Rouge | Ironton | 2 | 120 |  | Raise the Sag Limit on River Rouge-Ironton #2 120 kV to 271 MVA (1304 Amps) | M3_Long Lead Materials | 340000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 340000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9902 | 2017-01-09 | 21308 | 2016-12-20 | SUB | 2018-12-31 | Sterling |  |  | 120 |  | Install a new 120 kV bus and one 120 kV breaker to convert Sterling to a ring bus. Also move the Sterling transformer #201 connection to the new bus and install a disconnect switch on the low side. Breaker “HT” will become the bus-tie between bus #101 and #104 | M2a_Pre-Project Approval | 1100000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1100000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9994 | 2017-01-09 | 21418 | 2016-12-20 | LNrb | 2019-12-31 | Custer | Monroe | 1 | 120 |  | Rebuild the entire Custer – Monroe 120 kV line. Pre-build it to 230 kV construction to facilitate future 230 kV expansion in southern Michigan. Replace the existing assets (all structures and 954 ACSR 45/7 conductor) with new double-circuit structures that are designed for bundled 2-954 ACSR 54/7 conductor and install this conductor along with an OPGW path for the existing line only. | M2a_Pre-Project Approval | 14500000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 14500000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9998 | 2017-01-09 | 21420 | 2016-12-20 | SUB | 2017-12-31 | ITCT Asset Replacement Program - 2017 |  |  | 345 | 120 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | M2a_Pre-Project Approval | 47970000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 47970000 | 0% |  | 0
A in MTEP16 | East | ITCT | 9999 | 2017-01-09 | 21421 | 2016-12-20 | SUB | 2018-12-31 | ITCT Asset Replacement Program - 2018 |  |  | 345 | 120 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | M2a_Pre-Project Approval | 53250000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 53250000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10000 | 2017-01-09 | 21423 | 2015-09-15 | SUB | 2019-12-31 | ITCT Asset Replacement Program - 2019 |  |  | 345 | 120 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | Planned | 53310000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 53310000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10010 | 2017-01-09 | 21433 | 2016-12-20 | Dist | 2019-12-31 | Blanket for Customer Interconnections 2019 | Througout System |  | 120 |  | Connect interconnecting entities as requested | M2a_Pre-Project Approval | 2000000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 2000000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10243 | 2017-01-09 | 21501 | 2017-06-27 | CB | 2018-06-30 | Navarre |  |  | 120 |  | Upgrade the existing Navarre 120 kV breaker HX to have an interrupting capability of 50 kA. | M3_Long Lead Materials | 70000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-30 | Planned | 70000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10270 | 2017-01-09 | 21516 | 2017-06-27 | LNup | 2018-12-31 | Apache | Seneca | 1 | 120 |  | The proposed solution is to remediate the sag limit on the Apache – Seneca 120 kV line to 230 MVA (1107 Amp). | M3_Long Lead Materials | 202000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 202000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10425 | 2017-01-09 | 21581 | 2016-09-14 | SUB | 2017-09-01 | Grassmere |  |  | 345 |  | Install a 345 kV breaker w/ associated disconnects | Under Construction | 1421500 | Engineering | 2015 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Under Construction | 1421500 | 0% |  | 0
A in MTEP16 | East | ITCT | 10425 | 2017-01-09 | 21582 | 2016-09-14 | TX | 2017-09-01 | Grassmere |  |  | 345 | 120 | Install a 345/120 kV transformer at Grassmere | Under Construction | 5062000 | Engineering | 2015 | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2017-09-01 | Under Construction | 5062000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10425 | 2017-01-09 | 21583 | 2016-09-14 | LN | 2017-09-01 | J340 Substation | Grassmere | 1 | 120 |  | Rebuild 5.3 miles of the existing 120 kV Cosmo tap using double circuit structures, and string 954 ACSR conductor between the J340 Interconnection substation and Grassmere. Relocate the Harvest Wind tap point to the new line to create the J340-Havest Wind-Grassmere 120 kV 3 terminal line. | Under Construction | 7170000 | Engineering | 2015 | MI | 5.3 |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2017-09-01 | Under Construction | 7170000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10425 | 2017-01-09 | 22187 | 2016-09-14 | SUB | 2017-09-01 | Grassmere |  |  | 120 |  | 120 kV breakers and associated disconnects | Under Construction | 1496500 |  |  | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2017-09-01 | Under Construction | 1496500 | 0% |  | 0
A in MTEP16 | East | ITCT | 10723 | 2017-01-09 | 21650 | 2017-03-29 | SUB | 2017-12-01 | Skylark 120 kV |  |  | 120 |  | Construct the 120 kV Skylark substation and install 2-120 kV line breakers and 2-120 kV section breakers, along with a control house, associated disconnects, and all other required 120 kV equipment. | M4_Pre-Construction | 3487000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 3487000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10723 | 2017-01-09 | 21651 | 2017-03-29 | LN | 2017-12-01 | Northeast | Skylark | 1 | 120 |  | Line created by looping the existing Northeast-Sloan 120 kV circuit into Skylark. Install approx. 4.7 miles of OPGW on the line | M4_Pre-Construction | 941000 | Engineering | 2016 | MI | 4.6 | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 941000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10723 | 2017-01-09 | 21652 | 2017-03-29 | LN | 2017-12-01 | Skylark | Sloan | 1 | 120 |  | Line created by looping the existing Northeast-Sloan 120 kV circuit into Skylark. Install approx. 3.2 miles of OPGW on the line | M4_Pre-Construction | 627000 | Engineering | 2016 | MI | 3.1 | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 627000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10723 | 2017-01-09 | 21653 | 2017-03-29 | RLY | 2017-12-01 | Northeast 120kV |  |  | 120 |  | Upgrade relaying at Northeast to accommodate the new Skylark Substation. | M4_Pre-Construction | 223000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 223000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10723 | 2017-01-09 | 21654 | 2017-03-29 | RLY | 2017-12-01 | Sloan 120 kV |  |  | 120 |  | Upgrade relaying at Sloan to accommodate the Skylark substation | M4_Pre-Construction | 117000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 117000 | 0% |  | 0
A in MTEP16 | East | ITCT | 10923 | 2017-01-09 | 21690 | 2016-12-20 | TEQ | 2017-12-31 | Throughout System |  |  | 120 |  | Install a new GOAB switch or replace an existing 120 kV, full-load-break pole top switch at necessary tap points. | Planned | 2400000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 2400000 | 0% |  | 12
A in MTEP16 | East | ITCT | 10924 | 2017-01-09 | 21691 | 2016-12-20 | TEQ | 2018-12-31 | Throughout System |  |  | 120 |  | Install a new GOAB switch or replace an existing 120 kV, full-load-break pole top switch at necessary tap points. | M2a_Pre-Project Approval | 2400000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 2400000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21698 | 2017-06-27 | SUB | 2017-12-01 | Mercury 120 kV |  |  | 120 |  | 120 kV, 3-breaker substation in a straight bus configuration. | M4_Pre-Construction | 2721000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 2721000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21699 | 2017-06-27 | LN | 2017-12-01 | Arctic | Mercury | 1 | 120 |  | Line created by looping the existing Arctic-Crestwood 120 kV line into the new Mercury substation. | M4_Pre-Construction | 2965000 | Engineering | 2016 | MI |  | 0.8 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 2965000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21700 | 2017-06-27 | LN | 2017-12-01 | Crestwood | Mercury | 1 | 120 |  | Line created by looping the existing Arctic-Crestwood 120 kV line into the new Mercury substation. | M4_Pre-Construction | 2965000 | Engineering | 2016 | MI |  | 0.8 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 2965000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21701 | 2017-06-27 | RLY | 2017-12-01 | Ranger |  |  | 120 |  | Upgrade relaying equipment at Ranger substation | M4_Pre-Construction | 127000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 127000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21702 | 2017-06-27 | RLY | 2017-12-01 | Crestwood |  |  | 120 |  | Upgrade relaying equipment at Crestwood Substation | M4_Pre-Construction | 206000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 206000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11003 | 2017-01-09 | 21703 | 2017-06-27 | RLY | 2017-12-01 | Arctic | Ranger | 1 | 120 |  | Install 4.7 miles of OPGW (fiber) on the existing structures of the Arctic-Ranger 120 kV line. | M4_Pre-Construction | 1116000 | Engineering | 2016 | MI | 4.7 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 1116000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11043 | 2017-01-09 | 21712 | 2016-08-11 | TEQ | 2016-04-04 | Monroe | Bay Shore |  | 345 |  | Replace 345kV terminal equipment at Monroe on the Monroe - Bay Shore circuit | M5_In Service | 250000 | Engineering |  | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2016-04-04 | M5_In Service | 250000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11443 | 2017-01-09 | 21775 | 2017-06-27 | SUB | 2017-12-01 | Ranger |  |  | 120 |  | Install 2-3000A 120kV 40 kA min. int capability line breakers and associated equipment. Breakers are for the Elm - Ranger, and Ranger - Arctic 120kV lines. | M4_Pre-Construction | 1899000 | Engineering | 2016 | MI | 0 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 1899000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11443 | 2017-01-09 | 21776 | 2017-06-27 | RLY | 2017-12-01 | ELM |  |  | 120 |  | Install line differential and breaker control relaying for position HO. | M4_Pre-Construction | 260000 | Engineering | 2016 | MI | 0 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 260000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11443 | 2017-01-09 | 21777 | 2017-06-27 | SUBmisc | 2017-12-01 | River Rouge Power Plant |  |  | 120 |  | Replace Trainers on River Rogue - Warren #2 120 kV line with 1590 SAC. | M4_Pre-Construction | 7000 | Engineering |  | MI | 0 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 7000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11443 | 2017-01-09 | 21778 | 2017-06-27 | SUBmisc | 2017-12-01 | Warren |  |  | 120 |  | Replace Trainers on River Rogue - Warren #2 120 kV line with 1590 SAC. | M4_Pre-Construction | 7000 | Engineering | 2016 | MI | 0 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 7000 | 0% |  | 0
A in MTEP16 | East | ITCT | 11583 | 2017-06-27 | 21787 | 2017-06-27 | SUB | 2018-10-15 | Kirk 345 kV |  |  | 345 |  | New 345 kV, 3-breaker substation laid out in a ring bus configuration | M3_Long Lead Materials | 7559500 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 7559500 | 0% |  | 13
A in MTEP16 | East | ITCT | 11583 | 2017-06-27 | 21788 | 2017-06-27 | LN | 2018-10-15 | Kirk | Ringle | 1 | 345 |  | New 345 kV line created by looping the Bauer-Ringle 345 kV line into Kirk. | M3_Long Lead Materials | 626250 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626250 | 0% |  | 13
A in MTEP16 | East | ITCT | 11583 | 2017-06-27 | 21789 | 2017-06-27 | LN | 2018-10-15 | Kirk | Bauer | 1 | 345 |  | New 345 kV line created by looping the Bauer-Ringle 345 kV line into Kirk. | M3_Long Lead Materials | 626250 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626250 | 0% |  | 13
A in MTEP16 | East | ITCT | 11583 | 2017-06-27 | 21790 | 2017-06-27 | TEQ | 2018-10-15 | Kirk 345 kV |  |  | 345 |  | TOIFs associated with the J301 Project. This includes a 345 kV disconnect switch and entrance structure at the POI. | M3_Long Lead Materials | 685000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 685000 | 0% |  | 13
A in MTEP16 | East | ITCT | 11584 | 2017-06-27 | 21791 | 2017-06-27 | SUB | 2018-10-15 | Helena 345 kV |  |  | 345 |  | New 345 kV, 3-breaker substation laid out in a ring bus configuration. | M3_Long Lead Materials | 7495000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 7495000 | 0% |  | 13
A in MTEP16 | East | ITCT | 11584 | 2017-06-27 | 21792 | 2017-06-27 | LN | 2018-10-15 | Helena | Rapson | 1 | 345 |  | New 345 kV line created by looping in the Greenwood-Rapson #2 line into Helena. | M3_Long Lead Materials | 626500 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626500 | 0% |  | 13
A in MTEP16 | East | ITCT | 11584 | 2017-06-27 | 21793 | 2017-06-27 | LN | 2018-10-15 | Helena | Greenwood | 1 | 345 |  | New 345 kV line created by looping in the Greenwood-Rapson #2 line into Helena. | M3_Long Lead Materials | 626500 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626500 | 0% |  | 13
A in MTEP16 | East | ITCT | 11584 | 2017-06-27 | 21794 | 2017-06-27 | TEQ | 2018-10-15 | Helena 345 kV |  |  | 345 |  | TOIFs for the J308 Project. These include a 345 kV disconnect switch and entrance structure at the POI. | M3_Long Lead Materials | 673000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2016-09-01 | Planned | 673000 | 0% |  | 25
A in MTEP16 | East | ITCT | 11603 | 2017-06-27 | 21795 | 2017-06-27 | SUB | 2020-10-01 | Stringer 345 kV |  |  | 345 |  | New 345 kV, 3 breaker substation laid out in a ring bus configuration. | M3_Long Lead Materials | 7411000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 7411000 | 0% |  | 37
A in MTEP16 | East | ITCT | 11603 | 2017-06-27 | 21796 | 2017-06-27 | LN | 2020-10-01 | Stringer | Rapson | 1 | 345 |  | New 345 kV line created by looping the Greenwood-Rapson #2 345 kV line into Stringer substation. | M3_Long Lead Materials | 626500 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626500 | 0% |  | 37
A in MTEP16 | East | ITCT | 11603 | 2017-06-27 | 21797 | 2017-06-27 | LN | 2020-10-01 | Stringer | Greenwood | 1 | 345 |  | New 345 kV line created by looping the Greenwood-Rapson #2 345 kV line into Stringer substation. | M3_Long Lead Materials | 626500 | GIA | 2016 | MI |  | 0.1 |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 626500 | 0% |  | 37
A in MTEP16 | East | ITCT | 11603 | 2017-06-27 | 21798 | 2017-06-27 | TEQ | 2020-10-01 | Stringer 345 kV |  |  | 345 |  | TOIFs for the J321 project. These include a 345 kV disconnect switch and entrance structure at the POI. | M3_Long Lead Materials | 666000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 666000 | 0% |  | 37
A in MTEP16 | East | ITCT | 11603 | 2017-06-27 | 21799 | 2017-06-27 | RLY | 2020-10-01 | Greenwood 345 |  |  | 345 |  | Upgrade relaying at pos. HI at Greenwood substation | M3_Long Lead Materials | 36000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2017-09-01 | Planned | 36000 | 0% |  | 37
A in MTEP16 | East | ITCT | 11604 | 2017-01-24 | 21800 | 2017-01-24 | SUBmisc | 2019-06-30 | Milan 120 kV |  |  | 120 |  | Extend 120 kV Bus 103 at Milan substation | M3_Long Lead Materials | 136000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2018-06-30 | Planned | 136000 | 0% |  | 12
A in MTEP16 | East | ITCT | 11604 | 2017-01-24 | 21801 | 2017-01-24 | SUB | 2019-06-30 | Milan 120 kV |  |  | 120 |  | TOIFs for the J419 project. These include a 120 kV breaker and associated disconnects at pos. HD at Milan | M3_Long Lead Materials | 667000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2018-06-30 | Planned | 667000 | 0% |  | 12
A in MTEP16 | South | LAFA | 8821 | 2017-01-09 | 20746 | 2016-02-01 | LN | 2019-12-31 | Northeast | Peck |  | 69 |  | 69kv line connecting Northeast station to Peck station. | Planned | 4230000 |  |  | LA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 4230000 | 0% |  | 0
A in MTEP16 | West | MDU | 4140 | 2017-01-09 | 7871 | 2017-01-16 | SUB | 2019-03-31 | Bowdle Jct |  |  | 115 | 41.6 | A new 115/41.6 kV substation | Planned | 5500000 | Engineering |  | SD |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-30 | Planned | 5500000 | 0% |  | 21
A in MTEP16 | West | MDU | 9120 | 2017-01-09 | 20815 | 2017-06-21 | LN | 2018-12-31 | Ellendale Jct | Leola Jct | 1 | 115 |  | New Ellendale Jct-Leola Jct 115 kV line | Planned | 8830000 | Budgetary | 2015 | SD,ND |  | 45 | 127 | 127 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-10-31 | Planned | 8830000 | 0% |  | 14
A in MTEP16 | West | MDU | 9120 | 2017-01-09 | 20816 | 2017-06-21 | SUB | 2018-12-31 | Leola Jct |  |  | 115 | 41.6 | New 115/41.6 kV substation connecting to the Ellendale Jct - Bowdle Jct 41.6 kV line | Planned | 4005000 | Budgetary | 2015 | SD |  |  | 50 | 50 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-10-31 | Planned | 4005000 | 0% |  | 14
A in MTEP16 | West | MDU | 9121 | 2017-01-09 | 20817 | 2017-03-17 | TEQ | 2016-10-13 | Heskett 115 Switchyard |  |  | 115 |  | Replace switches 7097, 7002 & 7005 | M5_In Service | 79000 | Engineering | 2015 | ND |  |  | 159 | 191 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 125000 | -36.8% |  | -2
A in MTEP16 | West | MDU | 11403 | 2017-01-09 | 21768 | 2016-06-20 | LNrc | 2015-12-31 | Coyote Jct | Beulah Jct | 1 | 115 |  | Reconductor Coyote Jct-Beulah Jct 115 kV line | M5_In Service | 350000 | Facility Study |  | ND | 4.3 |  |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2015-12-31 | M5_In Service | 350000 | 0% |  | 0
A in MTEP16 | West | MEC | 8108 | 2017-01-09 | 20445 | 2014-09-22 | LNup | 2017-06-01 | Sub 73 | Dumont Tap |  | 69 |  | Replace structures increasing line clearance and rating | Planned | 40000 | Planning | 2017 | IA | 0.63 |  | 72 | 72 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 40000 | 0% |  | 0
A in MTEP16 | West | MEC | 8110 | 2017-01-09 | 20447 | 2014-09-22 | LNup | 2017-06-01 | Sub 73 | Elvira Tap |  | 69 |  | Replace structures, increasing line clearance and rating. | Planned | 50000 | Planning | 2014 | IA | 1.95 | 0 | 72 | 72 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 50000 | 0% |  | 0
A in MTEP16 | West | MEC | 8112 | 2017-01-09 | 20448 | 2014-09-22 | LNup | 2017-06-01 | Buffalo Bill Tap | Elvira Tap |  | 69 |  | Replace structures to increase line clearance and rating. | Planned | 25000 | Planning | 2014 | IA | 6.36 | 0 | 72 | 72 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 25000 | 0% |  | 0
A in MTEP16 | West | MEC | 9947 | 2017-01-09 | 21366 | 2016-09-16 | SUB | 2018-06-01 | Polk City |  |  | 161 | 13 | New Polk City 33 MVA 161-13 kV distribution substation | Planned | 1300000 | Planning |  | IA |  |  | 33 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1300000 | 0% |  | 0
A in MTEP16 | West | MEC | 9947 | 2017-01-09 | 21367 | 2016-09-16 | LN | 2018-06-01 | Polk City | Bittersweet | 1 | 161 |  | Build four miles of new 161 kV line from Polk City to the existing Bittersweet - NE Ankeny 161 kV line | Planned | 3200000 | Planning | 2015 | IA |  | 4 | 210 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 3200000 | 0% |  | 0
A in MTEP16 | West | MEC | 9947 | 2017-01-09 | 21368 | 2016-09-16 | LN | 2018-06-01 | Polk City | NE Ankeny | 1 | 161 |  | New 3 mile line from Polk City Substation to existing Bittersweet-NE Ankeny 161 kV line. | Planned | 2500000 | Planning |  | IA |  | 3 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 2500000 | 0% |  | 0
A in MTEP16 | West | MEC | 9973 | 2017-01-09 | 21390 | 2016-06-07 | TX | 2017-10-01 | Manawa |  |  | 161 | 13 | Add a second 33 MVA 161-13 kV transformer at Manawa Substation. | Planned | 1100000 | Planning | 2016 | IA |  |  | 33 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-10-01 | Planned | 1100000 | 0% |  | 0
A in MTEP16 | West | MEC | 9976 | 2017-01-09 | 21396 | 2016-06-07 | CB | 2016-12-01 | Avoca |  |  | 69 |  | Add a new 69 kV breaker on transformer 8T1 at Avoca Substaiton. | Planned | 415000 | Planning | 2016 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-01 | Planned | 415000 | 0% |  | 0
A in MTEP16 | West | MEC | 9980 | 2017-01-09 | 21398 | 2016-03-21 | IND | 2016-10-01 | Teakwood |  |  | 34.5 |  | Add two 10 MVAR 34.5 kV reactors at Teakwood Substation. | Planned | 850000 | Planning | 2016 | IA |  |  | 20 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-10-01 | Planned | 850000 | 0% |  | 0
A in MTEP16 | West | MEC | 9981 | 2017-01-09 | 21403 | 2015-09-15 | LNrb | 2017-06-01 | Sub 701 | Honey Creek | 1 | 69 |  | Rebuild the Sub 701 to Honey Creek 69 kV line. | Planned | 3250000 | Planning | 2015 | IA | 10.2 | 0 |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 3250000 | 0% |  | 0
A in MTEP16 | West | MEC | 9987 | 2017-01-09 | 21410 | 2015-09-15 | SUB | 2016-11-30 | Johnston |  |  | 161 | 13 | New Johnston 33 MVA 161-13 kV distribution substation and two 161 kV tap lines approximately 0.5 miles each. | Planned | 2130000 | Planning | 2016 | IA |  |  | 33 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-11-30 | Planned | 2130000 | 0% |  | 0
A in MTEP16 | West | MEC | 9992 | 2017-01-09 | 21414 | 2017-06-28 | LNup | 2016-07-01 | Lake Cornelia | Coulter | 1 | 69 |  | Replace limiting structures to increase line rating. | M5_In Service | 91000 | Planning | 2016 | IA |  |  | 44 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-07-01 | Planned | 59000 | 54.24% | Replaced more poles than originally planned. | 0
A in MTEP16 | West | MEC | 9993 | 2017-01-09 | 21416 | 2017-06-28 | LNup | 2016-04-13 | Humboldt East | Thor | 1 | 69 |  | Replace limiting structures to increase line rating. Mitigates overloads for n-1-1 contingencies. | M5_In Service | 58000 | Planning | 2016 | IA |  |  | 44 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-04-13 | Planned | 61000 | -4.918% |  | 0
A in MTEP16 | West | MEC | 9996 | 2017-01-09 | 21419 | 2017-06-28 | TX | 2016-12-30 | Eagle Grove |  |  | 69 | 13 | Install second 69-13 kV Transformer & 69 kV bus tie breaker | M5_In Service | 2100000 | Planning | 2017 | IA |  |  | 25 MVA |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-09 | Planned | 2440000 | -13.93% |  | 0
A in MTEP16 | West | MEC | 10004 | 2017-01-09 | 21427 | 2016-09-16 | TX | 2018-06-01 | Sub 18 |  |  | 161 | 69 | Replace Sub 18 161-69 kV transformer with a 167 MVA unit. | Planned | 1080000 | Planning | 2017 | IA |  |  | 167 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-06-01 | Planned | 1080000 | 0% |  | 0
A in MTEP16 | West | MEC | 10005 | 2017-01-09 | 21428 | 2016-09-14 | CB | 2015-12-08 | Plymouth |  |  | 161 |  | Replace 161kV circuit breaker 9610 at Plymouth Substation. | M5_In Service | 264000 | Planning |  | IA |  |  | 40 kA/2000A continuous |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-12-08 | M5_In Service | 264000 | 0% |  | 0
A in MTEP16 | West | MEC | 10006 | 2017-01-09 | 21429 | 2015-09-18 | CB | 2016-12-31 | Sycamore |  |  | 161 |  | Replace 161 kV circuit breakers AG805, AG812 and AG816 at Sycamore Substation to maintain adequate current interrupting capability. | Planned | 685000 | Planning | 2015 | IA |  |  | 40 kA |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 685000 | 0% |  | 0
A in MTEP16 | West | MEC | 10009 | 2017-01-09 | 21430 | 2016-06-07 | CB | 2016-10-31 | Bondurant |  |  | 161 |  | Replace 161 kV circuit breaker AH810 at Bondurant Substation. | Planned | 325000 | Planning | 2016 | IA |  |  | 40 kA |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-31 | Planned | 325000 | 0% |  | 0
A in MTEP16 | West | MEC | 10503 | 2017-01-09 | 21601 | 2017-06-28 | CB | 2016-10-20 | Tate & Lyle |  |  | 161 |  | Add 161 kV bus tie breaker | M5_In Service | 318000 | Planning |  | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-20 | Planned | 443000 | -28.22% |  | 0
A in MTEP16 | West | MEC | 10663 | 2017-01-09 | 21641 | 2016-01-29 | TX | 2016-12-31 | Willow Creek | Willow Creek |  | 161 | 13.2 | Add three new 161 kV breakers to convert the substation to breaker and one-half configuration and to accommodate the addition of a new 50 MVA 161-13 kV transformer to meet increasing customer load. | Planned | 120000 | Planning | 2016 | IA | 0 | 0 | 50 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 120000 | 0% |  | 0
A in MTEP16 | West | MEC | 10664 | 2017-01-09 | 21642 | 2016-01-29 | TX | 2016-12-01 | 34th Ave. NW |  |  | 161 | 13.2 | Add a new 62 MVA 161-13 kV transformer at the 34th Ave. NW Substation to serve increasing customer load. | Planned | 90000 | Planning | 2016 | IA | 0 | 0 | 62 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-01 | Planned | 90000 | 0% |  | 0
A in MTEP16 | West | MEC | 10803 | 2017-01-09 | 21667 | 2017-06-29 | CAP | 2016-12-01 | Sub J Iowa City |  |  | 161 |  | Reducing the size of the Sub J capacitor bank to 37.8 MVAR provides increased operational flexibility while maintaining voltage within criteria. Replace the capacitor relays. | M5_In Service | 146000 | Budgetary | 2016 | IA |  |  | 37.8 | 37.8 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 300000 | -51.33% |  | 0
A in MTEP16 | West | MEC | 10867 | 2017-01-09 | 21677 | 2016-09-14 | INT | 2016-08-15 | Obrien County |  |  | 345 |  | New 345 kV circuit breaker position for J285 generator interconnection. | Under Construction | 3000000 | Planning | 2016 | IA |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2016-08-15 | Under Construction | 3000000 | 0% |  | 0
A in MTEP16 | West | MEC | 10868 | 2017-01-09 | 21678 | 2016-09-14 | SUB | 2016-07-15 | Ida County |  |  | 345 |  | Ida County 345 kV Substation to bisect the Raun-Lehigh 345 kV line for the J411 generator interconnection. | Under Construction | 5750000 | Planning | 2016 | IA |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2016-07-15 | Under Construction | 5750000 | 0% |  | 0
A in MTEP16 | West | MEC | 11103 | 2017-01-09 | 21716 | 2017-06-27 | CAP | 2016-11-15 | 636201 |  |  | 69 |  | Two 69 kV, 15 MVAR capacitors | M5_In Service | 1247000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-11-15 | Under Construction | 1180000 | 5.678% | The original estimated cost should have been $1,648,000, not $1,180,000. The $1,180,000 value represented the estimated amount to be reimbursed by non-MidAmerican parties. The current estimated project cost of $1,247,000 is $401,000 less than the $1,648,000 original estimated cost. | 0
A in MTEP16 | West | MEC | 11143 | 2017-01-09 | 21717 | 2016-06-07 | LNup | 2016-12-01 | 635645 | 652560 | 1 | 161 |  | structure replacements | Planned | 175000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-01 | Planned | 175000 | 0% |  | 0
A in MTEP16 | West | MEC | 11144 | 2017-01-09 | 21718 | 2017-06-28 | TEQ | 2016-07-15 | 636020 |  |  | 161 |  | Replace 161 kV switch | M5_In Service | 32000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-06-24 | Under Construction | 88000 | -63.64% |  | 1
A in MTEP16 | West | MEC | 11145 | 2017-01-09 | 21719 | 2017-06-28 | LNup | 2016-07-15 | 631079 | 636020 | 1 | 161 |  | structure replacements | M5_In Service | 163000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-06-30 | Planned | 173000 | -5.78% |  | 1
A in MTEP16 | West | MEC | 11146 | 2017-01-09 | 21720 | 2016-06-07 | LNup | 2017-06-01 | 635034 | 635038 | 1 | 161 |  | structure replacements | Planned | 200000 | Engineering | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-06-01 | Planned | 200000 | 0% |  | 0
A in MTEP16 | West | MEC | 11203 | 2017-01-09 | 21737 | 2016-12-05 | SUB | 2011-12-30 | Rolling Hills |  |  | 345 |  | Add a new 345 kV circuit breaker and associated switchgear to accommodate Generator Interconnection Project J191. | M5_In Service | 754100 | Facility Study | 2011 | IA |  |  | 3000A |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2011-12-30 | M5_In Service | 754100 | 0% |  | 0
A in MTEP16 | West | MEC | 11204 | 2017-01-09 | 21738 | 2016-12-05 | SUB | 2012-11-01 | Lehigh |  |  | 345 |  | Add two 345 kV circuit breakers and complete a 345 kV ring bus to accommodate Generator Interconnection Project R42. | M5_In Service | 2882000 | Actual | 2012 | IA |  |  | 3,000 A |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2012-11-01 | M5_In Service | 2882000 | 0% |  | 0
A in MTEP16 | West | MEC | 11283 | 2017-01-09 | 21754 | 2016-05-25 | LNup | 2017-06-01 | 541251 MARYVLE5 161.00 | 635034 CLRNDA 5 161.00 | 1 | 161 |  | Replace three structures. | Planned | 100100 | Budgetary | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-06-01 | Planned | 100100 | 0% |  | 0
A in MTEP16 | West | MEC | 11284 | 2017-01-09 | 21755 | 2016-05-25 | TEQ | 2017-06-01 | 541251 MARYVLE5 161.00 | 635034 CLRNDA 5 161.00 | 1 | 161 |  | Network Upgrades for J343 Adams County Wind. | Planned | 80500 | Budgetary | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-06-01 | Planned | 80500 | 0% |  | 0
A in MTEP16 | West | MEC | 11285 | 2017-01-09 | 21756 | 2016-05-25 | TEQ | 2017-09-01 | 631113 POWESHK5 161.00 | 635870 BEACON 5 161.00 | 1 | 161 |  | Non-Stand Alone Network Upgrade for J344 wind interconnection request. | Planned | 25000 | GIA | 2016 | IA |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-09-01 | Planned | 25000 | 0% |  | 0
A in MTEP16 | East | METC | 2809 | 2017-01-09 | 336 | 2017-06-27 | LNrb | 2019-12-31 | Garfield Avenue | Hemphill | 1 | 138 |  | Rebuild a ~9.5 mile-long portion of 336 ACSR conductor utilizing 1431 ACSR conductor on double-circuit, 138 kV structures, relocate a portion of the Weadock – Hemphill 138 kV line to the other side of the new structures | M2a_Pre-Project Approval | 11000000 | Engineering | 2015 | MI | 9.5 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 11000000 | 0% |  | 0
A in MTEP16 | East | METC | 3133 | 2017-01-09 | 5510 | 2017-06-27 | LNrb | 2019-12-31 | Bell Road | Cornell | 1 | 138 |  | Rebuild a ~4.3 mile-long portion of the Claremont – Cornell 2 line between Bell Road and Cornell. | M2a_Pre-Project Approval | 4350000 | Engineering | 2015 | MI | 4.3 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 4350000 | 0% |  | 0
A in MTEP16 | East | METC | 9422 | 2017-01-09 | 20906 | 2017-04-11 | SUB | 2017-04-10 | Newton 138 kV |  |  | 138 |  | Construct a 138 kV, 4 breaker substation laid out in a ring bus configuration | M5_In Service | 5222000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | M3_Long Lead Materials | 5222000 | 0% |  | 0
A in MTEP16 | East | METC | 9422 | 2017-01-09 | 20914 | 2017-04-11 | LN | 2017-04-07 | Michigan Ave | Newton | 1 | 138 |  | Construct an approx. 3 mile, 138 kV line between Michigan Ave and Newton, using 954 ACSR conductor | M5_In Service | 5868000 | Engineering | 2016 | MI |  | 3 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-30 | M3_Long Lead Materials | 5868000 | 0% |  | 0
A in MTEP16 | East | METC | 9422 | 2017-01-09 | 22384 | 2016-12-20 | CAP | 2018-06-01 | Newton 138 kV |  |  | 138 |  | Add an 18 MVAR switched capacitor bank at the new Newton Substation with a 138 kV synchronizing breaker. | M2a_Pre-Project Approval | 1220000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | M1_Final SPM or OOC | 1220000 | 0% |  | 0
A in MTEP16 | East | METC | 9695 | 2017-01-09 | 21019 | 2017-06-27 | TEQ | 2018-12-31 | Bullock |  |  | 138 |  | Upgrade terminal equipment at Bullock on the Dow Corning 138 kV line | M3_Long Lead Materials | 300000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 300000 | 0% |  | 0
A in MTEP16 | East | METC | 9705 | 2017-01-09 | 21036 | 2016-12-20 | LNup | 2018-12-31 | Alma | Regal | 2 | 138 |  | Remediate the sag limit on the Alma – Regal 2 138 kV line to a minimum of 208 MVA / 871 Amps | M2a_Pre-Project Approval | 200000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 200000 | 0% |  | 0
A in MTEP16 | East | METC | 9876 | 2017-06-23 | 21261 | 2017-06-27 | LNup | 2019-12-31 | Karn | Manning | 1 | 138 |  | Remediate the sag limit on the Karn - Manning 138 kV line to a minimum of 396 MVA / 1657 Amps | M2a_Pre-Project Approval | 470000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 470000 | 0% |  | 12
A in MTEP16 | East | METC | 9876 | 2017-06-23 | 21262 | 2017-06-27 | TEQ | 2019-12-31 | Karn |  |  | 138 |  | Upgrade terminal equipment at Karn | M2a_Pre-Project Approval | 150000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 150000 | 0% |  | 12
A in MTEP16 | East | METC | 9932 | 2017-01-09 | 21345 | 2016-12-20 | LNrb | 2019-12-31 | Karn | Saginaw River | 1 | 138 |  | Rebuild a ~2.7 mile-long portion of the Karn – Saginaw River 138 kV line that is comprised of only 2-3/0 copper conductor in a six-wired configuration utilizing 1431 ACSR conductor on single-circuit, 138 kV structures | M2a_Pre-Project Approval | 4500000 | Engineering | 2015 | MI | 16 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 4500000 | 0% |  | 0
A in MTEP16 | East | METC | 9932 | 2017-01-09 | 21346 | 2016-12-20 | LNup | 2019-12-31 | Karn | Saginaw River | 1 | 138 |  | Remediate the sag limit on the existing 1431 ACSR conductor to at least the planned target summer normal/summer emergency rating of 412 MVA/1724 Amps | M2a_Pre-Project Approval | 918000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 918000 | 0% |  | 0
A in MTEP16 | East | METC | 9932 | 2017-01-09 | 21347 | 2016-12-20 | TEQ | 2019-12-31 | Karn |  |  | 138 |  | Upgrade terminal equipment at Karn | M2a_Pre-Project Approval | 162000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 162000 | 0% |  | 0
A in MTEP16 | East | METC | 9932 | 2017-01-09 | 21348 | 2016-12-20 | TEQ | 2019-12-31 | Saginaw River |  |  | 138 |  | Upgrade terminal equipment at Saginaw River | M2a_Pre-Project Approval | 2920000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 2920000 | 0% |  | 0
A in MTEP16 | East | METC | 9945 | 2017-01-09 | 21365 | 2016-12-20 | SUB | 2017-12-31 | METC Asset Replacement Program - 2017 |  |  | 345 | 138 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | M2a_Pre-Project Approval | 54276000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 54276000 | 0% |  | 0
A in MTEP16 | East | METC | 9956 | 2017-01-09 | 21371 | 2016-12-20 | SUB | 2018-12-31 | METC Asset Replacement Program - 2018 |  |  | 345 | 138 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs | M2a_Pre-Project Approval | 49398000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 49398000 | 0% |  | 0
A in MTEP16 | East | METC | 9959 | 2017-01-09 | 21373 | 2016-12-20 | Dist | 2017-12-31 | Blanket for Customer Interconnections 2019 | Throughout System |  | 138 |  | Connect interconnecting entities as requested | M2a_Pre-Project Approval | 2500000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2500000 | 0% |  | 0
A in MTEP16 | East | METC | 9960 | 2017-01-09 | 21374 | 2016-12-20 | SUB | 2019-12-31 | METC Asset Replacement Program - 2019 |  |  | 345 | 138 | Replace aging and outdated equipment on a cycle that will ensure each piece of equipment is replaced near its expected end of life. Modern equipment can improve reliability, use state of the art technology, and typically will allow for longer maintenance intervals. New equipment is also commonly equipped with better monitoring and alarming functionality giving improved remote supervision. All of this will help to reduce overall maintenance costs. | M2a_Pre-Project Approval | 49398000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 49398000 | 0% |  | 0
A in MTEP16 | East | METC | 9972 | 2017-01-09 | 21389 | 2016-12-20 | RLY | 2017-12-31 | Four Mile |  |  | 138 |  | Replace METC relaying and controls at Four Mile Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | M2a_Pre-Project Approval | 3520000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 3520000 | 0% | Received updated Engineering level cost from Relay Design. | 0
A in MTEP16 | East | METC | 9975 | 2017-01-09 | 21393 | 2016-12-20 | RLY | 2017-12-31 | Verona |  |  | 138 |  | Replace METC relaying and controls at Verona Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | M2a_Pre-Project Approval | 2940000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2940000 | 0% |  | 0
A in MTEP16 | East | METC | 9978 | 2017-01-09 | 21399 | 2016-12-20 | SUB | 2018-06-30 | Eureka |  |  | 138 |  | Replace the Eureka 138 kV circuit switcher 256 with a synchronous breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA | M2a_Pre-Project Approval | 510000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-30 | Planned | 510000 | 0% |  | 0
A in MTEP16 | East | METC | 9984 | 2017-01-09 | 21407 | 2016-12-20 | SUB | 2018-06-30 | Tittabawassee |  |  | 345 |  | Replace the Tittabawassee 345 kV breaker 38H9 with a breaker that has a continuous rating of 3000 amp and a minimum interrupting capability of 40 kA. | M2a_Pre-Project Approval | 790000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-30 | Planned | 790000 | 0% |  | 0
A in MTEP16 | East | METC | 10286 | 2017-01-09 | 21531 | 2016-12-20 | TEQ | 2018-12-31 | Campbell |  |  | 138 |  | Remove the Campbell 508 disconnect switch. Modify the relaying to remove 588 breaker sparing capability. | M2a_Pre-Project Approval | 88000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 88000 | 0% |  | 0
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21673 | 2017-03-29 | SUB | 2018-12-31 | Michigan Ave 138kV |  |  | 138 |  | Install 2-138 kV line breakers and associated disconnect switches, along with a new control house at Michigan Ave substation | M3_Long Lead Materials | 2137000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 2137000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21739 | 2017-03-29 | SUB | 2018-12-31 | Wagner 138 kV |  |  | 138 |  | Add a 138 kV, 3 breaker substation laid out in a ring bus configuration named Wagner, in Union City, MI | M3_Long Lead Materials | 5122000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 5122000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21740 | 2017-03-29 | RLY | 2018-12-31 | Batavia 138 kV |  |  | 138 |  | Upgrade relaying at pos. BM37 @ Batavia substation | M3_Long Lead Materials | 21000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 21000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21741 | 2017-03-29 | RLY | 2018-12-31 | Coldwater 138 kV |  |  | 138 |  | Upgrade relaying on pos. 3040 @ Coldwater substation. | M3_Long Lead Materials | 188000 | Engineering | 2016 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 188000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21742 | 2017-03-29 | LN | 2018-12-31 | Newton | Wagner | 1 | 138 |  | Construct an approx. 13 mile, 138 kV line, on new future double circuit structures, using 954 ACSR between Newton and Wagner substations | M3_Long Lead Materials | 26117000 | Engineering | 2016 | MI |  | 13 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 26117000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21743 | 2017-03-29 | LN | 2018-12-31 | Alder Creek | Wagner | 1 | 138 |  | Line created by looping the Alder Creek-Batavia 138 kV circuit into Wagner substation. | M3_Long Lead Materials | 412000 | Planning | 2016 | MI |  | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 412000 | 0% |  | 7
A in MTEP16 | East | METC | 10323 | 2017-01-09 | 21744 | 2017-03-29 | LN | 2018-12-31 | Batavia | Wagner | 1 | 138 |  | Line created by looping the Alder Creek-Batavia 138 kV circuit into Wagner substation. | M3_Long Lead Materials | 412000 | Planning | 2016 | MI |  | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 412000 | 0% |  | 7
A in MTEP16 | East | METC | 10384 | 2017-06-08 | 21576 | 2017-06-08 | LNup | 2017-05-30 | VERONA | BARNUM CREEK JCT. | 138 | 138 |  | Fully remediate the sag limit on the 266.8 ACSR conductor from the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit to the conductor rating of 730 Amps / 174 VMVA (summer emergency) using new future double circuit (FDC) structures capable of supporting 954 ACSR in order to facilitate a rebuild of this circuit in the near future. | M5_In Service | 1070000 | Engineering | 2015 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 1070000 | 0% |  | -1
A in MTEP16 | East | METC | 10743 | 2017-01-09 | 21655 | 2016-09-14 | RLY | 2015-09-30 | Palisades 345 kV |  |  | 345 |  | Construct a new control house at Palisades substation and replace relaying to accommodate the interconnection request. | M5_In Service | 3482000 | Engineering | 2015 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2015-09-30 | M5_In Service | 3482000 | 0% |  | 0
A in MTEP16 | East | METC | 10743 | 2017-01-09 | 21656 | 2016-09-14 | RLY | 2015-09-30 | Covert |  |  | 345 |  | Remove METC SCADA equipment from Covert substation | M5_In Service | 11000 | Engineering | 2015 | MI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2015-09-30 | M5_In Service | 11000 | 0% |  | 0
A in MTEP16 | East | METC | 10743 | 2017-01-09 | 21657 | 2016-09-14 | LNrb | 2015-09-30 | Palisades | Segreto | 1 | 345 |  | Install OPGW on the Palisades-Segreto #1 line (formerly Cook-Palisades) | M5_In Service | 112000 | Engineering | 2015 | MI | 1.5 |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2015-09-30 | M5_In Service | 112000 | 0% |  | 0
A in MTEP16 | East | METC | 10744 | 2017-01-09 | 21658 | 2016-09-14 | SUB | 2016-05-09 | Van Tyle 138 kV |  |  | 138 |  | New 138 kV, 4 row, 11 breaker substation to be fed by looping in the Livingston-Stover 138 kV line and adding a Livingston-Van Tyle #2 line. | M5_In Service | 7947200 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-05-09 | M5_In Service | 7947200 | 0% |  | 0
A in MTEP16 | East | METC | 10744 | 2017-01-09 | 21659 | 2016-09-14 | LN | 2016-05-09 | Livingston | Van Tyle | 1 | 138 |  | New 138 kV line created by looping the Livingston-Stover line into Van Tyle | M5_In Service | 3245000 | GIA | 2016 | MI | 2.8 | 0.1 |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-05-09 | M5_In Service | 3245000 | 0% |  | 0
A in MTEP16 | East | METC | 10744 | 2017-01-09 | 21660 | 2016-09-14 | LN | 2016-05-09 | Livingston | Van Tyle | 2 | 138 |  | New 138 kV line created by rebuilding the Livingston-Van tyle line to double circuit structures and adding a second line between the substation using 1431 ACSR conductor | M5_In Service | 3245000 | GIA | 2016 | MI | 2.8 | 0.1 |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-05-09 | M5_In Service | 3245000 | 0% |  | 0
A in MTEP16 | East | METC | 10744 | 2017-01-09 | 21696 | 2016-09-14 | SUB | 2016-06-11 | Livingston |  |  | 138 |  | Create 2 new rows and install 5-138 kV breakers with associated disconnect switches at Livingston substation | M5_In Service | 3630000 | GIA | 2016 | MI | 2.8 |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-06-11 | M5_In Service | 3630000 | 0% |  | 0
A in MTEP16 | East | METC | 10744 | 2017-01-09 | 21697 | 2016-09-14 | RLY | 2016-05-06 | Gaylord |  |  | 138 |  | Upgrade relaying at Gaylord | M5_In Service | 20000 | GIA | 2016 | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-05-06 | M5_In Service | 20000 | 0% |  | 0
A in MTEP16 | East | METC | 11243 | 2017-01-09 | 21747 | 2017-03-29 | LNrb | 2018-05-31 | Verona | Barnum Creek Jct. |  | 138 |  | Rebuild the Verona – Barnum Creek Jct. section of the Verona – Batavia 138 kV circuit using 954 ACSR and OGPW on new 230 kV future double circuit structures. Replace PTS 3186. Upgrade terminal equipment at the Verona station. | M3_Long Lead Materials | 13300000 | Engineering | 2015 | MI | 6.2 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 13300000 | 0% |  | 0
A in MTEP16 | East | METC | 11243 | 2017-01-09 | 21748 | 2017-03-29 | LNrc | 2018-05-31 | Verona | Convis Jct. |  | 138 |  | Reconductor approximately 0.6 miles of the Verona – Foundry 138 kV circuit where it shares common structures with the Verona – Batavia 138 kV circuit. | M3_Long Lead Materials |  |  |  | MI | 0.6 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 0 | 0% |  | 0
A in MTEP16 | East | METC | 11683 | 2017-01-09 | 21814 | 2017-03-29 | LNup | 2018-05-31 | Barnum Creek | Alder Creek | 1 | 138 |  | Remediate Sag on the Barnum Creek Jct. – Alder Creek 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | M3_Long Lead Materials | 400000 | Engineering Preliminary |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 400000 | 0% |  | 0
A in MTEP16 | East | METC | 11684 | 2017-01-09 | 21815 | 2017-03-29 | LNup | 2018-05-31 | Alder Creek | Wagner | 1 | 138 |  | Remediate Sag on the Alder Creek – Wagner 138 kV section up to the conductor rating of 174 MVA (730 Amp.). | M3_Long Lead Materials | 365000 | Engineering Preliminary |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 365000 | 0% |  | 0
A in MTEP16 | East | METC | 11704 | 2017-01-09 | 21817 | 2017-06-27 | LNup | 2018-05-31 | Denso J. | Vrooman | 1 | 138 |  | Remediate the sag limit on the Denso J.–Vrooman 138 kV section to at least 150 MVA (628 Amp). | M3_Long Lead Materials | 195000 | Engineering Preliminary |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 195000 | 0% |  | 0
A in MTEP16 | West | MP | 7910 | 2017-01-09 | 20153 | 2015-04-02 | LNrc | 2019-11-01 | Brainerd | Mud Lake | 1 | 115 |  | Reconductor Brainerd - Mud Lake 115 kV Line with 636 ACSR @ 100C | Planned | 1900000 | Planning | 2015 | MN | 4.41 | 0 | 182 | 200.2 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 1900000 | 0% |  | 0
A in MTEP16 | West | MP | 7996 | 2017-01-09 | 20269 | 2015-09-04 | LNrb | 2017-12-31 | FondDuLac | Hibbard | 1 | 115 |  | Fond Du Lac - Hibbard 115 kV Line | Planned | 5500000 | Planning Preliminary | 2014 | MN | 11.3 | 0 | 122 | 134.2 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 5500000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20271 | 2015-09-04 | TEQ | 2018-12-31 | 15th Avenue West |  |  | 115 | 13.8 | 115 kV substation improvements (fencing, grounding, relocations, misc. equipment) | Planned | 3500000 | Planning | 2015 | MN | 0 | 0 | 39.2 | 49 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 3500000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20273 | 2015-09-04 | Dist | 2018-12-31 | 15th Avenue West |  |  | 13.8 |  | New 14 kV switchgear, 14 kV bus, & 14 kV feeder relocations (includes removals) | Planned | 5000000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 5000000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20274 | 2015-09-04 | CB | 2018-12-31 | 15th Avenue West |  | 1 | 115 |  | 115 kV "71L" breaker replacement | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20276 | 2015-09-04 | CB | 2018-12-31 | 15th Avenue West |  | 1 | 115 |  | 115 kV "21L" breaker replacement | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20938 | 2015-09-04 | CB | 2018-05-01 | 15th Avenue West |  |  | 115 |  | 115 kV "21-71MW" breaker replacement | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 7997 | 2017-01-09 | 20939 | 2015-09-04 | TX | 2018-05-01 | 15th Avenue West |  | 1 | 114 | 13.8 | New 115/14 kV transformer | Planned | 750000 | Planning | 2015 | MN | 0 | 0 | 39.2 | 49 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-05-01 | Planned | 750000 | 0% |  | 0
A in MTEP16 | West | MP | 9064 | 2017-01-09 | 20809 | 2016-08-15 | BUS | 2017-12-31 | Arrowhead |  |  | 115 |  | Expand and reconfigure 115 kV bus | Planned | 600000 | Budgetary | 2016 | MN | 0 | 0 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 600000 | 0% |  | 0
A in MTEP16 | West | MP | 9622 | 2017-01-09 | 20940 | 2015-09-04 | TEQ | 2019-06-01 | Boswell |  |  | 230 |  | Replace limiting switches at Boswell | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 9622 | 2017-01-09 | 20941 | 2015-09-04 | TEQ | 2019-06-01 | Blackberry |  |  | 230 |  | Replace limiting switches at Blackberry | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 9623 | 2017-01-09 | 20942 | 2015-09-04 | TEQ | 2019-06-01 | Boswell |  |  | 230 |  | Replace limiting switches at Boswell | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 9623 | 2017-01-09 | 20943 | 2015-09-04 | TEQ | 2019-06-01 | Blackberry |  |  | 230 |  | Replace limiting switches at Blackberry | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 9624 | 2017-01-09 | 20944 | 2015-09-04 | Dist | 2017-12-31 | Bear Creek |  |  | 69 | 46 | Add 69/46 kV transformer | Planned | 2000000 | Planning | 2015 | MN | 0 | 0 | 18.7 | 23.4 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 2000000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20945 | 2015-09-04 | SwSta | 2017-12-31 | Nemadji |  |  | 115 |  | NEW Nemadji Switching Station | Planned | 4630000 | Engineering | 2014 | WI | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4630000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20946 | 2015-09-04 | CAP | 2017-12-31 | Nemadji |  |  | 115 |  | Nemadji Cap Bank | Planned | 380000 | Engineering | 2014 | WI | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 380000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20947 | 2015-09-04 | TEQ | 2017-12-31 | Various Customer-Owned |  |  | 115 |  | Enbridge Substation Modifications | Planned | 1530000 | Engineering | 2014 | WI | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1530000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20948 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Stinson | 1 | 115 |  | Nemadji - Stinson 115 kV Line (double circuit with Nemadji - North - East) | Planned | 1500000 | Planning | 2014 | WI | 0 | 1.2 | 235 | 258.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1500000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20949 | 2015-09-04 | LN | 2014-12-31 | Nemadji | Enbridge North | 1 | 115 |  | Nemadji - North 115 kV Line (double ckt with Nemadji - Stinson) | Planned | 150000 | Planning | 2014 | WI | 0 | 0.64 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2014-12-31 | Planned | 150000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20950 | 2015-09-04 | LN | 2016-06-01 | Enbridge North | Enbridge East |  | 115 |  | North - East 115 kV Line (partial double ckt with Nemadji - Stinson) | Planned | 200000 | Planning | 2014 | WI | 0 | 0.72 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 200000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20951 | 2015-09-04 | LN | 2017-12-31 | Enbridge East | Enbridge South | 1 | 115 |  | Replace switch structure in East - South 115 kV Line | Planned | 150000 | Engineering | 2014 | WI | 0 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 150000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20952 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Enbridge South | 1 | 115 |  | Nemadji - South 115 kV Line | Planned | 100000 | Planning | 2014 | WI | 0 | 0.2 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 100000 | 0% |  | 0
A in MTEP16 | West | MP | 9625 | 2017-01-09 | 20953 | 2015-09-04 | LN | 2017-12-31 | Nemadji | Gary | 1 | 115 |  | Extend existing 115 kV line from Gary into Nemadji | Planned | 50000 | Planning | 2014 | WI | 0 | 0.08 | 235 | 258.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 50000 | 0% |  | 0
A in MTEP16 | West | MP | 10284 | 2017-01-09 | 21522 | 2016-09-29 | TEQ | 2017-05-01 | Boswell 115 |  |  | 115 |  | Disconnect switch, Jumpers, and wave Trap | Planned | 120000 | Engineering Preliminary |  | MN |  |  | 150 | 150 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 120000 | 0% |  | 0
A in MTEP16 | West | MP | 10284 | 2017-01-09 | 21523 | 2016-09-29 | LNup | 2017-05-01 | Boswell | Canisteo |  | 115 |  | Increase operating temperature from 65C to 90C | Planned | 670000 | Engineering Preliminary |  | MN |  |  | 144 | 158.4 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 670000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21570 | 2015-11-23 | BUS | 2017-12-31 | Laskin |  |  | 115 |  | Remove 138/115 kV transformer and bus through transformer position to reconnect Laskin - Hoyt Lakes 115 kV Line (43 Line) | Planned | 100000 | Planning | 2015 | MN | 0 | 0 | 144 | 158.4 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 100000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21571 | 2015-11-23 | TEQ | 2017-12-31 | Skibo |  |  | 115 |  | Replace 138 kV equipment with 115 kV | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21572 | 2015-11-23 | TX | 2017-12-31 | Skibo |  |  | 115 | 13.8 | Replace Skibo 138/13.8 kV transformer with a 115/13.8 kV transformer (Relocate existing) | Planned | 65000 | Planning | 2015 | MN | 0 | 0 | 33.6 |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 65000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21573 | 2015-11-23 | TX | 2017-12-31 | Hoyt Lakes |  |  | 115 | 13.8 | Replace existing Hoyt Lakes 138/13.8 kV transformer with 115/13.8 kV transformers (customer-funded) | Planned | 1000000 | Planning | 2015 | MN | 0 | 0 | 50 |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 1000000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21574 | 2015-11-23 | TEQ | 2017-12-31 | Hoyt Lakes |  |  | 115 |  | Replace 138 kV equipment with 115 kV | Planned | 250000 | Planning | 2015 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 250000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21575 | 2015-11-23 | BUS | 2017-12-31 | Taconite Harbor |  |  | 115 |  | Convert Taconite Harbor 138 kV Main Bus to 115 kV and connect to existing 115 kV bus | Planned | 419000 | Planning | 2014 | MN | 0 | 0 |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 419000 | 0% |  | 0
A in MTEP16 | West | MP | 10383 | 2017-01-09 | 21584 | 2015-12-02 | CAP | 2017-07-01 | Dunka Road |  |  | 115 |  | New 15 MVAr cap bank at Dunka Road Substation | Planned | 400000 | Planning | 2015 | MN | 0 | 0 | 15 | 15 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-07-01 | Planned | 400000 | 0% |  | 0
A in MTEP16 | West | OTP | 9990 | 2017-01-09 | 21415 | 2016-09-27 | RLY | 2017-12-31 | Devils Lake East 41.6 |  |  | 41.6 |  | Relay upgrades | Planned | 37500 | Planning |  | ND |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 37500 | 0% |  | 0
A in MTEP16 | West | OTP | 9995 | 2017-01-09 | 21417 | 2015-12-30 | RLY | 2017-12-31 | Devils Lake SW 41.6 kV |  |  | 41.6 |  | Relay upgrades | Planned | 37500 | Planning |  | ND |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 37500 | 0% |  | 0
A in MTEP16 | West | OTP | 10003 | 2017-01-23 | 21426 | 2016-12-20 | SUB | 2016-12-31 | Rugby 230/115/41.6 kV |  |  | 230 | 41.6 | Install four 41.6 kV Breakers in the Rugby area to re-terminate existing OTP-owned 41.6 kV circuits from CPEC-owned Rugby substation to 230 kV delivery. | M5_In Service | 2000000 | Planning |  | ND |  |  |  |  | Other |  | Non-Transferred | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 2000000 | 0% |  | 0
A in MTEP16 | West | OTP | 10007 | 2017-01-09 | 21431 | 2016-09-21 | LNrb | 2018-12-31 | Max 41.6 kV | Ryder 41.6 kV | 1 | 41.6 |  | To correct this material failure problem with the conductor, a project has been scoped and scheduled out for four years. The project will start in 2015 and be completed in 2018. The project will replace failing insulation, cross arms and poles identified through patrols and inspections and replace the failing 1/0 ACSR conductor for approximately 34 miles between Max, ND and Ryder, ND. | Planned | 2500000 | Planning | 2016 | ND | 34 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 2500000 | 0% | An additional 12 miles were added to the original project due to age and condition. | 0
A in MTEP16 | West | OTP | 11743 | 2017-01-23 | 21820 | 2016-09-29 | SwSta | 2016-12-31 | Coleharbor 41.6 kV |  |  | 41.6 |  | Single in-line circuit breaker addition | Planned | 175000 | Planning |  | ND |  |  |  |  | Other |  | Non-Transferred | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 175000 | 0% |  | 0
A in MTEP16 | West | OTP | 11743 | 2017-01-23 | 21821 | 2016-09-29 | SwSta | 2016-12-31 | Drake 41.6 |  |  | 41.6 |  | Single in-line circuit breaker addition | Planned | 175000 | Planning |  | ND |  |  |  |  | Other |  | Non-Transferred | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 175000 | 0% |  | 0
A in MTEP16 | West | OTP | 11743 | 2017-01-23 | 21822 | 2016-09-29 | SwSta | 2016-12-31 | Granville 41.6 |  |  | 41.6 |  | Three circuit breaker addition | Planned | 1150000 | Planning |  | ND |  |  |  |  | Other |  | Non-Transferred | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 1150000 | 0% |  | 0
A in MTEP16 | Central | PPI | 9564 | 2017-01-26 | 20930 | 2015-09-01 | SwSta | 2020-12-01 | 4Elkhart Jct (348950) | 4Turris Coal (348909) | 1 | 138 |  | 4 breaker ring bus at Turris Coal | Planned | 4124000 | Budgetary | 2015 | IL |  | 5 | 287 | 287 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 4124000 | 0% |  | 0
A in MTEP16 | Central | PPI | 9564 | 2017-01-26 | 20931 | 2015-09-01 | LN | 2019-12-01 | Turris W-ICG Viper Mine | Athens | 1 | 138 |  | New 138 kV transmission line | Planned | 5316000 | Budgetary | 2016 | IL |  |  | 229 | 229 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 5316000 | 0% |  | 0
A in MTEP16 | Central | PPI | 9564 | 2017-01-26 | 20932 | 2015-09-01 | SUB | 2020-12-01 | Athens 138 kV | Athens 69 kV |  | 138 | 69 | Athens 138/69 kV substation | Planned | 4653000 | Budgetary | 2015 | IL |  |  | 75 | 75 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2020-12-01 | Planned | 4653000 | 0% |  | 0
A in MTEP16 | Central | PPI | 9564 | 2017-01-26 | 20933 | 2015-09-01 | SwSta | 2020-12-01 | Athens Tap |  |  | 69 |  | Athens Tap 69 kV breaker station to sectionalize the Amos-Athens-East Lanesville 69 kV line | Planned | 2204000 | Budgetary | 2015 | IL |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2020-12-01 | Planned | 2204000 | 0% |  | 0
A in MTEP16 | West | RPU | 10443 | 2017-01-09 | 21585 | 2017-03-10 | SUB | 2017-05-31 | 161 KV Tap | Douglas Trail Substation |  | 161 |  | New 161kV Douglas Trail Substation fed from tapping the immediately adjacent Q5 161kV line | Planned | 7000000 |  |  | MN |  | 0.07 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 7000000 | 0% |  | 1
A in MTEP16 | South | SMEPA | 9957 | 2017-01-24 | 21378 | 2017-06-22 | SUB | 2017-12-02 | Origis Sub | Origis Gen | 1 | 69 | 26.4 | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. | M4_Pre-Construction | 1520000 |  |  | MS |  |  | 60 MVA |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-03-23 | Planned | 1590000 | -4.403% |  | 9
A in MTEP16 | South | SMEPA | 9957 | 2017-01-24 | 21715 | 2017-03-30 | GEN | 2017-12-02 | Origis Gen |  |  | 69 | 26.4 | The Origis Energy solar plant will tap SMEPA's existing 69kV Line 42 (Sumrall to Rawls Springs) approximately 5.6 miles from Sumrall with a new 69kV switching station and a 69/26.4 kV GSU. | M4_Pre-Construction |  |  |  | MS |  |  | 52MW |  | GIP |  |  | N | N | NT | Externally Driven | A | 2017-03-23 | Planned | 0 | 0% |  | 9
A in MTEP16 | South | SMEPA | 9969 | 2017-01-24 | 21382 | 2017-06-22 | LNrb | 2017-12-01 | Sumrall | Rawls Springs | 1 | 69 |  | Rebuild L42 to final conductor temperature of 100C. The existing conductor will be replaced with 795 ACSR conductor for a final conductor rating of 126 MVA. Rebuild L42A to final conductor temperature of 100C. The existing conductor will be replaced with 795 ACSR conductor for a final conductor rating of 126 MVA. | M4_Pre-Construction | 2353500 |  |  | MS |  |  | 126 MVA |  | GIP |  |  | N | N | NT | Externally Driven | A | 0 | Planned | 2202498 | 6.856% |  | 1415
A in MTEP16 | South | SMEPA | 9969 | 2017-01-24 | 21386 | 2017-06-22 | LNrb | 2017-12-01 | Sumrall | Columbia | 1 | 69 |  | Rebuild L43 to a final conductor temperature of 100C. The existing conductor will be replaced with 795 ACSR conductor for a final conductor rating of 126 MVA. | M4_Pre-Construction | 2353500 |  |  | MS |  |  | 126 MVA |  | GIP |  |  | N | N | NT | Externally Driven | A | 0 | Planned | 2579502 | -8.761% |  | 1415
A in MTEP16 | Central | Vectren | 4393 | 2017-06-30 | 8410 | 2017-06-30 | LNrb | 2023-12-31 | Dubois 69 | Huntingburg 69 | 67-2 | 69 |  | Rebuild and Reconductor approx. 3.5 miles | Planned | 2625000 | Planning | 2013 | IN | 3.54 | 0 | 103 MVA | 122 MVA | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 2625000 | 0% |  | 60
A in MTEP16 | Central | Vectren | 9940 | 2017-01-09 | 21379 | 2017-03-23 | LN | 2015-11-21 | Elliott | Sunbeam | Y52 | 69 |  | Y52 69kV loop from Elliott sub to Sunbeam sub | M5_In Service | 132186 | Engineering |  | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2015-12-31 | M2a_Pre-Project Approval | 150000 | -11.88% |  | -1
A in MTEP16 | Central | Vectren | 9940 | 2017-01-09 | 21381 | 2017-03-23 | Dist | 2015-11-24 | Elliott | Elliott Distribution | Y52 | 69 | 12 | New Distribution Substation with 9.375MVA 69kV/12kV transformer | M5_In Service | 2518821 | Engineering |  | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2015-12-31 | M2a_Pre-Project Approval | 1200000 | 109.9% | Original estimate was under estimated. The substation transformer was increased from 9.375MVA to 20MVA, and transitioned to contract services to install sub. | -1
A in MTEP16 | Central | Vectren | 9942 | 2017-06-30 | 21384 | 2017-06-30 | LNrl | 2017-08-01 | GRIMM ROAD | WARRICK NORTH | Z85 | 138 |  | Public Roadway relocation of 1.25 miles of Z85 138kV line | Under Construction | 1200000 | Budgetary |  | IN |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1200000 | 0% |  | 8
A in MTEP16 | Central | Vectren | 9946 | 2017-06-30 | 21392 | 2017-06-30 | Dist | 2019-12-31 | ANGEL MOUNDS | HEIDELBACH | Z85 | 138 | 12 | 138kV/69kV/12kV Substation | Planned | 4000000 | Budgetary |  | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 2100000 | 90.48% | Revised scope and estimate | 12
A in MTEP16 | Central | Vectren | 9948 | 2017-01-09 | 21395 | 2017-06-30 | LNrb | 2017-12-31 | Pelzer | Chrisney | Y56 | 69 |  | Rebuild of 14 miles of Y56 69kV line from Pelzer Sub to Chrisney Sub | Under Construction | 5000000 | Budgetary |  | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 6800000 | -26.47% | More detailed estimate provided | -24
A in MTEP16 | Central | Vectren | 9952 | 2017-06-30 | 21400 | 2017-06-30 | LN | 2019-12-31 | HEIDELBACH | PIGEON CREEK | Y43 | 69 |  | Y43 69kV loop to Berry substation | Planned | 1850000 | Budgetary |  | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 300000 | 516.7% | Revised scope and estimate | 12
A in MTEP16 | East | WPSC | 4385 | 2017-01-09 | 8400 | 2015-09-15 | LNrb | 2018-12-31 | Burnips | Drenthe | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 3150000 | Planning | 2015 | MI | 10.5 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 3150000 | 0% |  | 0
A in MTEP16 | East | WPSC | 4385 | 2017-01-09 | 8401 | 2013-12-16 | LNrb | 2018-12-31 | Drenthe | Fairview | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 350000 |  | 2013 | MI | 1.1 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 350000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9899 | 2017-01-09 | 21302 | 2015-09-15 | LNrb | 2018-12-31 | Redwood | Crystal Valley Junction | 1 | 69 |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | Planned | 3075000 | Budgetary | 2015 | MI | 6.92 |  | 143.4 | 143.4 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 3075000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9899 | 2017-01-09 | 21303 | 2015-09-15 | LNrb | 2018-12-01 | Crystal Valley Junction | Eden | 1 | 69 |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | Planned | 3600000 | Budgetary | 2015 | MI | 7.45 |  | 143.4 | 143.4 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 3600000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9899 | 2017-01-09 | 21304 | 2016-09-15 | LNrb | 2018-12-31 | Eden | Riverton | 1 | 69 |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | Planned | 3325000 | Budgetary | 2015 | MI | 6.12 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 3325000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9899 | 2017-01-09 | 21305 | 2015-09-15 | LNrb | 2018-12-31 | Riverton | Scottville | 1 | 69 |  | Rebuild the Redwood to Scottville 69kV line, install new poles and hardware with 795ACSS conductor | Planned | 500000 | Budgetary | 2015 | MI | 0.1 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 500000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9913 | 2017-01-09 | 21324 | 2015-09-15 | BAT | 2017-12-31 | System Need |  |  | 69 |  | 2017 Battery Bank replacement program | Planned | 70000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 70000 | 0% |  | 0
A in MTEP16 | East | WPSC | 9915 | 2017-01-09 | 21329 | 2015-09-15 | RLY | 2017-12-31 | Oden |  |  | 69 |  | Upgrade relaying at Oden on the Oden - Emmet terminal | Planned | 35000 | Budgetary | 2015 | MI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 35000 | 0% |  | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21704 | 2017-04-21 | SUB | 2016-05-16 | Advance |  |  | 138 | 69 | Add 138kV bus and 138/69kV transformer to Wolverine's Advance station | M5_In Service | 3912980.76 | Budgetary | 2016 | MI |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-05-16 | Under Construction | 4213420 | -7.131% |  | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21705 | 2017-04-21 | SUB | 2016-04-30 | Gaylord (WPSC) |  |  | 138 | 96 | Phase I - Convert 138kV bus to 4 terminal ring bus design. Additional terminal required to bring 3rd 138kV line into the bus. | M5_In Service | 2651737 | Budgetary | 2016 | MI |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-04-30 | Under Construction | 2545422 | 4.177% | Above expected labor costs | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21706 | 2017-03-07 | SUB | 2018-10-31 | Gaylord (WPSC) |  |  | 138 |  | Phase II - Convert Gaylord 138kV bus to 6 breaker ring bus design to accommodate 2nd 138/69kV transformer. | Planned | 2244651 | Budgetary |  | MI |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2018-10-31 | Under Construction | 2244651 | 0% |  | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21707 | 2017-04-21 | SUB | 2016-05-15 | Elmira |  |  | 138 | 13.09 | Upgrade the Elmira distribution station from 69kV to 138kV operation | M5_In Service | 3510269 | Budgetary | 2018 | MI |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-05-15 | Under Construction | 1234872 | 184.3% | Staging costs for materials. | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21708 | 2017-04-21 | SUB | 2016-05-15 | Alpine Distribution |  |  | 138 | 13.09 | Upgrade Alpine distribution substation from 69kV to 138kV operation | M5_In Service | 2697815 | Budgetary | 2016 | MI |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-05-15 | Under Construction | 1404228 | 92.12% | Weather reducing efficiency. | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21709 | 2017-04-21 | SUB | 2016-05-15 | Deer Lake |  |  | 138 | 13.09 | Upgrade Deer Lake distribution station from 69kV to 138kV operation | M5_In Service | 722137 | Budgetary | 2016 | MI |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2016-05-15 | Under Construction | 639544 | 12.91% | Weather reducing efficiency. | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21710 | 2017-04-21 | LNcnv | 2016-05-15 | Gaylord | Advance | 1 | 138 |  | Convert operating voltage on the the Gaylord to Advance line from 69kV to 138kV. Existing 23.74mi line in constructed for 138kV operation. New lines will be Gaylord - Van Tyle 138kV and Van Tyle - Advance 138kV | M5_In Service | 8417822.2 | Budgetary | 2016 | MI | 21.75 | 1 |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-05-15 | Under Construction | 806493 | 943.8% | Staging costs for interconnection. | 0
A in MTEP16 | East | WPSC | 11023 | 2017-01-09 | 21711 | 2017-04-21 | LNrb | 2016-04-30 | Gaylord (WPSC) | Livingston |  | 138 |  | Rebuild existing line with 795ACSS conductor | M5_In Service | 773002.69 | Budgetary | 2016 | MI | 2.03 |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-04-30 | Under Construction | 891442 | -13.29% |  | 0
A in MTEP16 | West | XEL | 4696 | 2017-01-09 | 8880 | 2017-06-25 | LNrb | 2021-05-31 | Prentice | Medford |  | 69 |  | Rebuild this line to 795 ACSR due to age and condition of the line | Planned | 4449013 |  |  | WI | 33.5 |  | 71.7 | 71.7 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-01-31 | Planned | 20145714 | -77.92% |  | 40
A in MTEP16 | West | XEL | 10045 | 2017-01-09 | 21484 | 2017-06-26 | SUB | 2018-12-01 | City of Chaska |  |  | 115 |  | This is the new substation associated with the City of Chaska's new interconnection. | Planned | 1200000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-30 | Planned | 1200000 | 0% |  | 30
A in MTEP16 | West | XEL | 10045 | 2017-01-09 | 21527 | 2017-03-02 | TAP | 2018-12-01 | Bluff Creek | City of Chaska |  | 115 |  | Install line tapping double circuit South of Bluff Creek to new City of Chaska Sub | Planned | 2000000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-30 | Planned | 2000000 | 0% |  | 30
A in MTEP16 | West | XEL | 10062 | 2017-01-09 | 21525 | 2017-03-02 | TAP | 2016-06-30 | Tyrone Tap |  |  | 69 |  | Install a 3-way switch on NSP’s St. Thomas Tap to Boright #2 69 kV line | M5_In Service | 375000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-06-30 | Planned | 375000 | 0% |  | 0
A in MTEP16 | West | XEL | 10063 | 2017-01-09 | 21528 | 2017-02-23 | LNrb | 2016-04-01 | Jackson Co | DPC Merrillan Tap | 1 | 69 |  | Rebuild 6.1 miles from Jackson Co to DPC Merrillan Tap to 565.3 ACSR/TW. | M5_In Service | 3300000 |  |  | WI | 6.1 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-07-30 | Planned | 3300000 | 0% |  | -3
A in MTEP16 | West | XEL | 10065 | 2017-01-09 | 21529 | 2017-03-02 | CB | 2016-04-30 | Rogers Lake |  |  | 115 |  | Replace the four existing gas 40 kA breakers at Rogers Lake with with gas 63 kA breakers. | M5_In Service | 940847 |  |  | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-04-30 | Planned | 940847 | 0% |  | 0
A in MTEP16 | West | XEL | 10066 | 2017-01-09 | 21547 | 2017-06-24 | TEQ | 2016-05-06 | Southtown | Cedarvale |  | 115 |  | Upgrade the Southtown-Cedarvale 115 kV line to a minimum of 290 MVA emergency. | M5_In Service | 518000 |  |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 750000 | -30.93% |  | -7
A in MTEP16 | West | XEL | 10066 | 2017-01-09 | 21548 | 2017-03-02 | TEQ | 2016-06-01 | Southtown | Shepard |  | 115 |  | Upgrade the Southtown-Shepard 115 kV line to a minimum of 270 MVA emergency. | M5_In Service | 750000 |  |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 750000 | 0% |  | 0
A in MTEP16 | West | XEL | 10066 | 2017-01-09 | 21549 | 2017-06-24 | CAP | 2017-06-09 | Hiawatha |  |  | 115 |  | Add a 80 MVAR cap to the Hiawatha substation. | M5_In Service | 1700000 |  |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-30 | Planned | 1995000 | -14.79% |  | -6
A in MTEP16 | West | XEL | 10067 | 2017-01-09 | 21526 | 2017-06-27 | SUB | 2019-01-15 | Prairie |  |  | 115 |  | Breaker and a half conversion to accomidate Fossum 115 kV interconnection | Withdrawn | 13000000 |  |  | ND |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-01-01 | Planned | 17261500 | -24.69% |  | 12
A in MTEP16 | West | XEL | 10068 | 2017-01-09 | 21546 | 2017-06-24 | SUB | 2017-11-20 | Baytown |  |  | 115 | 13.8 | Install a 2nd transformer and switchgear at Baytown substation. | Planned | 2192622 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 1625468 | 34.89% | Increased project scope not account for in original estimate | 5
A in MTEP16 | West | XEL | 10069 | 2017-01-09 | 21545 | 2017-06-24 | SUB | 2019-12-15 | Twin Creek |  |  | 69 |  | Install a 2 position 69 kV breaker station | Planned | 2866000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-11-01 | Planned | 2866000 | 0% |  | 1
A in MTEP16 | West | XEL | 10071 | 2017-01-09 | 21530 | 2017-06-26 | SUB | 2016-12-15 | Prescott |  |  | 69 |  | Install second 69/12.47 kV 28 MVA transformer | M5_In Service | 1354676 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-09-30 | Planned | 750000 | 80.62% | Cost increase due to local permitting during construction and scope expansion | 3
A in MTEP16 | West | XEL | 10071 | 2017-01-09 | 21532 | 2017-06-26 | CAP | 2016-12-15 | Prescott |  |  | 69 |  | Install a second 10 MVAR cap bank. | M5_In Service | 765845 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-09-30 | Planned | 424000 | 80.62% | Cost increase due to local permitting during construction and scope expansion | 3
A in MTEP16 | West | XEL | 10072 | 2017-01-09 | 21533 | 2017-06-26 | SUB | 2017-04-06 | Dean Lake |  |  | 115 |  | Add 4 new breakers to complete the ring bus. | M5_In Service | 6741926 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 4904100 | 37.48% | Increase in final spending due to resource availability. | 4
A in MTEP16 | West | XEL | 10072 | 2017-01-09 | 21534 | 2017-06-26 | TX | 2017-04-06 | Dean Lake |  |  | 115 | 13.8 | Install third distribution transformer (City of Shakopee) | M5_In Service | 0 |  |  | MN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-08-01 | Planned | 0 | 0% |  | 8
A in MTEP16 | West | XEL | 10073 | 2017-01-09 | 21538 | 2017-03-02 | SUBmisc | 2016-01-01 | Quarry |  |  | 345 | 115 | Install GIC monitoring | M5_In Service | 36664 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-04-30 | Planned | 37298 | -1.7% |  | -3
A in MTEP16 | West | XEL | 10073 | 2017-01-09 | 21539 | 2017-03-02 | SUBmisc | 2016-01-01 | Adams |  |  | 345 | 161 | Install GIC monitoring | M5_In Service | 0 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 250000 | -100% |  | -11
A in MTEP16 | West | XEL | 10073 | 2017-01-09 | 21540 | 2017-03-02 | SUBmisc | 2016-12-01 | Elm Creek |  |  | 345 | 115 | Install GIC monitoring | M5_In Service | 85000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-04-30 | Planned | 47852 | 77.63% | Cost increased due to need for RTU to be added | 8
A in MTEP16 | West | XEL | 10073 | 2017-01-09 | 21541 | 2017-03-02 | SUBmisc | 2016-12-31 | Eau Claire |  |  | 345 | 161 | Install GIC monitoring | M5_In Service | 175000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 250000 | -30% |  | 0
A in MTEP16 | West | XEL | 10074 | 2017-01-09 | 21536 | 2017-06-24 | LNrb | 2020-12-15 | Airport | Rogers Lake |  | 115 |  | rebuilds the Airport - Rogers Lake 115 kV line using 795 ACSS conductor. | Planned | 4092000 |  |  | MN | 3.4 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-05-30 | Planned | 4092000 | 0% |  | 19
A in MTEP16 | West | XEL | 10075 | 2017-01-09 | 21542 | 2017-06-24 | TX | 2018-04-20 | Waconia |  |  | 69 | 13.8 | Install a 2nd distribution transformer at Waconia substation. | Planned | 420000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-30 | Planned | 420000 | 0% |  | 4
A in MTEP16 | West | XEL | 10076 | 2017-01-09 | 21535 | 2016-06-15 | LNrb | 2019-05-30 | West St. Cloud | Milwood Tap |  | 69 |  | Rebuild 24 miles of line from West St. Cloud to Millwood Tap using 477 ACSR conductor. | Planned | 10400000 |  |  | MN | 24 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-05-30 | Planned | 10400000 | 0% |  | 0
A in MTEP16 | West | XEL | 10077 | 2017-01-09 | 21537 | 2017-02-23 | TAP | 2017-11-15 | St. James |  |  | 69 |  | Install a new three-way switch on line 0714. | Under Construction | 490000 |  |  | MN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-01 | Planned | 390800 | 25.38% | Due to Interconnection Requester not being able to complete their side of the project. | 11
A in MTEP16 | West | XEL | 10288 | 2017-01-09 | 21550 | 2017-02-23 | SUB | 2018-12-30 | Osprey |  |  | 69 |  | Install 69 kV straight bus with 3 x 69 kV breakers | Planned | 1850000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-09-01 | Planned | 1850000 | 0% |  | 3
A in MTEP16 | West | XEL | 10288 | 2017-01-09 | 21551 | 2017-02-23 | LN | 2018-12-30 | Osprey | Flambeau |  | 69 |  | Reterminate line from DPC Flambeau | Planned | 320000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-09-01 | Planned | 320000 | 0% |  | 3
A in MTEP16 | West | XEL | 10288 | 2017-01-09 | 21552 | 2017-06-24 | LN | 2018-12-30 | Osprey | Whitetail Tap |  | 69 |  | Reterminate line from Whitetail Tap into Osprey. Rebuild last 0.4 miles of 69 kV line | Planned | 710000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-09-01 | Planned | 710000 | 0% |  | 3
A in MTEP16 | West | XEL | 10289 | 2017-01-09 | 21553 | 2017-02-23 | LNrb | 2015-12-01 | Elmwood | Comfort | 1 | 69 |  | Rebuild the existing 2/0 conductor to 477 ACSR due to age and condition | M5_In Service | 1109095 |  |  | WI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2015-12-01 | Planned | 1109095 | 0% |  | 0
A in MTEP16 | West | XEL | 10289 | 2017-01-09 | 21554 | 2017-06-25 | LNrb | 2018-12-15 | Comfort | Eau Galle | 1 | 69 |  | Rebuild the existing 2/0 conductor to 477 ACSR due to age and condition | Planned | 1000000 |  |  | WI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-01 | Planned | 1000000 | 0% |  | 24
A in MTEP16 | West | XEL | 10290 | 2017-01-09 | 21555 | 2017-03-20 | SUB | 2015-12-01 | Gravel Island |  |  | 161 | 12.5 | Install a 28 MVA distribution TR and associated breaker and bus work | M5_In Service | 2983000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-08-30 | Planned | 2983000 | 0% |  | -20
A in MTEP16 | West | XEL | 10291 | 2017-01-09 | 21556 | 2017-02-23 | SUB | 2019-12-01 | Stasik | LCO Hydro |  | 34.5 | 23.9 | Install single 34.5/23.9 kV TR to connect the Lac Courte Oreilles (LCO) hydro facility to the NCP system near Radisson | Planned | 180000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 180000 | 0% |  | 12
A in MTEP16 | West | XEL | 11883 | 2017-01-09 | 21853 | 2017-06-26 | SUBmisc | 2022-01-01 | Wilmarth |  |  | 345 |  | Substation modifications at Wilmarth | Planned | 2471713 |  |  | MN |  |  |  |  | MEP | Shared |  | Y | Y | Y | Top-Down | A | 2022-01-01 | M2a_Pre-Project Approval | 2471713 | 0% |  | 0
A in MTEP15 | South | AECC | 8320 | 2015-12-28 | 20638 | 2016-05-26 | SwSta | 2017-10-01 | EAI El Dorado - Monticello East 115 kV line |  |  | 115 |  | Switching station needed to tap Entergy line | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-10-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8320 | 2015-12-28 | 20639 | 2016-05-26 | LN | 2017-10-01 | EAI El Dorado - Monticello East 115 kV line | Hermtage 115/13.2 kV substation |  | 115 |  | 1.6 miles of 115 kV line | Planned | 2060000 |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-10-01 | Planned | 2060000 | 0% |  | 0
A in MTEP15 | South | AECC | 8320 | 2015-12-28 | 20640 | 2016-05-26 | SUB | 2017-10-01 | 115 kV radial tap |  |  | 115 | 13.2 | Hermitage 115/13.2 kV substation | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-10-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8341 | 2015-12-28 | 20645 | 2015-07-09 | TX | 2015-08-01 | Corning North 115kV |  |  | 115 |  | Installing a second transformer at Corning North. Due to a possible line conversion in the area by EAI in the very near future (2020 or sooner), the second transformer have a 161/115kV dual wound high side. | Planned | 1500000 | Scoping |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-08-01 | Planned | 1500000 | 0% |  | 0
A in MTEP15 | South | AECC | 8342 | 2015-12-28 | 20646 | 2015-07-09 | LN | 2015-08-01 | Pocahontas East | Industrial Park |  | 161 |  | 3.5 mile radial tap from the current Pocahontas East substation to the new Industrial Park 161/24.9kV substation. | Planned | 2500000 | Planning Preliminary |  | AR |  | 3.5 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-08-01 | Planned | 2500000 | 0% |  | 0
A in MTEP15 | South | AECC | 8342 | 2015-12-28 | 20647 | 2015-07-09 | Dist | 2015-08-01 | Industrial Park |  |  | 161 |  | New 30MVA 161/24.9kV distribution substation | Planned | 2250000 | Planning Preliminary |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-08-01 | Planned | 2250000 | 0% |  | 0
A in MTEP15 | South | AECC | 8342 | 2015-12-28 | 20648 | 2015-07-09 | RLY | 2015-08-01 | Pocahontas East |  |  | 161 |  | AECC is installing an in-line breaker on the East side of the Pocahontas East substation. This breaker is intended to provide protection to Entergy's Jim Hill to Water Valley SPA 161kV Transmission Line. | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-08-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8400 | 2015-12-28 | 20658 | 2016-08-15 | SwSta | 2017-04-01 | Tap EAI El Dorado to Monticello 115kV line |  |  | 115 |  | 3 position ring bus | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8400 | 2015-12-28 | 20659 | 2016-08-15 | LN | 2017-04-01 | Tap EAI El Dorado to Monticello 115kV line |  |  | 115 |  | 13 mile 115kV line | Planned | 6400000 |  |  | AR |  | 13 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 6400000 | 0% |  | 0
A in MTEP15 | South | AECC | 8400 | 2015-12-28 | 20660 | 2016-08-15 | SUB | 2017-04-01 | 115 kV transmission line |  |  | 115 | 69 | 115/69 kV substation | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-04-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8402 | 2016-09-20 | 20661 | 2016-09-20 | LN | 2019-12-01 | Camden South |  |  | 115 |  | 7 mile 115kV transmission line from existing Camden South delivery point/substation to the proposed Camden West substation. | Planned | 3950000 |  |  | AR |  | 7 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 3950000 | 0% |  | 0
A in MTEP15 | South | AECC | 8402 | 2016-09-20 | 20662 | 2016-09-20 | SUB | 2019-12-01 | 115kV line |  |  | 115 | 13.2 | 115/13.2 kV substation | Planned |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | AECC | 8420 | 2016-02-22 | 20664 | 2016-02-22 | LN | 2017-12-01 | Pocahontas North | Ingram |  | 161 |  | 7 mile radial 161kV transmission line from Entergy's Pocahontas North station to the new Clay County Ingram substation | Planned | 3611500 | Planning Preliminary |  | AR |  | 7 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 3611500 | 0% |  | 0
A in MTEP15 | South | AECC | 8420 | 2016-02-22 | 20665 | 2016-02-22 | Dist | 2017-12-01 | Ingram |  |  | 161 | 24.9 | new 161/25kV substation with initial projected load of 12,000kW. Uncertain at the moment of the transformer size. Will likely be a 12/16/20 MVA. | Planned | 2250000 | Engineering Preliminary |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 2250000 | 0% |  | 0
A in MTEP15 | South | AECC | 8480 | 2015-12-28 | 20676 | 2015-07-09 | LN | 2017-01-01 | Marmaduke 161 kV | Gainesville | 1 | 161 |  | 10-mile, 336 ACSR 26/7 161 kV transmission line. | Planned | 2000000 | Planning Preliminary | 2016 | AR |  |  | 57.7 MVA | 69.0 MVA | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 2000000 | 0% |  | 0
A in MTEP15 | South | AECC | 8480 | 2015-12-28 | 20677 | 2015-07-09 | Dist | 2017-01-01 | Gainesville |  |  | 161 | 13.2 | 161/13.2 kV distribution substation | Planned | 5000000 | Planning Preliminary | 2016 | AR |  |  | 12/16/20 MVA |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-01-01 | Planned | 5000000 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 3689 | 2015-12-28 | 6966 | 2016-12-12 | CB | 2016-11-15 | Keystone Substation | Wallace |  | 138 |  | Keystone 138-13.8 kV Substation - Replace 138 kV circuit breaker 1396 in the Wallace-Keystone line with a minimum 2000 A continuous 40 kA interrupting circuit breaker | M5_In Service | 193007 | Planning |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-11-15 | Planned | 500000 | -61.4% |  | 0
A in MTEP15 | Central | AmerenIL | 4078 | 2015-12-28 | 7729 | 2016-10-19 | LN | 2015-11-03 | Sandburg | Monmouth | 1 | 138 |  | Rebuild approx. 4 miles of 477 kcmil ACSR conductor to meet or exceed the 1521 A summer emergency capability of the 1272 kcmil ACSR conductor which makes up the rest of this line. Replace wavetrap at Galesburg Monmouth Substation with equipment capable of carrying 2000 A continuously. | M5_In Service | 2100000 | Budgetary | 2014 | IL | 4 |  | 280 | 364 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-11-15 | Planned | 4200000 | -50% |  | -12
A in MTEP15 | Central | AmerenIL | 4079 | 2015-12-28 | 7730 | 2017-06-29 | SUB | 2017-06-01 | Huff | Connection for new 138-69 kV Sub |  | 138 | 69 | Establish new bulk substation connecting to the Havana-Danvers 138 kV Line 1352 between Powerton Jct. and Lilly Substation. (Tenttatively assume 3-position ring bus.) | M5_In Service | 7922634 | Planning |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 3000000 | 164.1% | Were not able to acquire land nearby. Now requires significant additional line work. | 0
A in MTEP15 | Central | AmerenIL | 4494 | 2015-12-28 | 8605 | 2016-12-12 | TX | 2016-12-01 | East Galesburg | Replace 161/138 kV XFMRS |  | 161 | 138 | Replace existing parallel 161/138 kV Transformers at East Galesburg with a single 161/138 kV Transformer at Sandburg 345/138 kV Substation. | M5_In Service | 2949385 | Planning Preliminary | 2015 | IL |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 3681580 | -19.89% |  | 0
A in MTEP15 | Central | AmerenIL | 7825 | 2015-12-28 | 20096 | 2016-10-19 | SwSta | 2019-12-01 | Mascoutah Municipal (Hilgard) |  |  | 138 |  | Install a 4-breaker 138 kV ring bus (2000 A, 40 kA) at or near the tap to Mascoutah Municipal on the existing Turkey Hill-Ashley 138 kV Line 1482. | Planned | 6761059 | Engineering | 2014 | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 5900000 | 14.59% | N/A | 0
A in MTEP15 | Central | AmerenIL | 8050 | 2015-12-28 | 20344 | 2015-04-01 | TX | 2015-06-01 | Baldwin 345kV |  |  | 345 | 138 | Replace existing transformer | Planned | 5650000 | Planning Preliminary | 2015 | IL |  |  | 560 MVA |  | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2015-06-01 | Planned | 5650000 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8054 | 2015-12-28 | 20351 | 2015-04-01 | LNrc | 2016-12-01 | Tilden Jct | Sparta |  | 138 |  | Reconductor 5.7 miles of line | Planned | 2710721 | Planning Preliminary | 2015 | IL | 5.7 |  |  | 1200A | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 2710721 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8055 | 2015-12-28 | 20352 | 2015-04-01 | LNrc | 2016-06-01 | Sparta Tap | Steelville |  | 138 |  | Reconductor 7.4 miles of line | Planned | 2318247 | Planning Preliminary | 2015 | IL | 7.4 |  |  | 1200A | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 2318247 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8060 | 2015-12-28 | 20485 | 2015-04-01 | LNrc | 2016-12-01 | Fayetteville South Tap | Tilden |  | 138 |  | Reconductor 1.5 miles of line | Planned | 1500000 | Planning Preliminary | 2015 | IL | 1.5 |  |  | 2000A | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 1500000 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8134 | 2015-12-28 | 20488 | 2015-04-01 | LNrc | 2015-12-01 | Tilden Jct | Tilden |  | 138 |  | Reconductor one span of line | Planned | 175920 | Planning Preliminary | 2015 | IL |  |  |  | 2000A | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2015-12-01 | Planned | 175920 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8137 | 2015-12-28 | 20491 | 2015-04-01 | LNrc | 2017-06-01 | Turkey Hill | Mascoutah |  | 138 |  | Reconductor 8.5 miles of line | Planned | 4250000 | Planning Preliminary | 2015 | IL | 8.5 |  |  | 1200A | Other |  | MP funded | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 4250000 | 0% |  | 0
A in MTEP15 | Central | AmerenIL | 8581 | 2015-12-28 | 20686 | 2016-10-19 | TEQ | 2017-03-02 | Vermillion |  |  | 138 |  | Increase of wind farm capacity to 250 MW | Planned |  | Engineering | 2015 | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-02 | Planned | 48000 | -100% |  | 0
A in MTEP15 | Central | AmerenMO | 7871 | 2015-12-28 | 20109 | 2016-12-12 | CB | 2016-12-01 | Keokuk |  |  | 69 |  | Install new 1200 A, 69 kV position to accommodate new 69 kV line to be constructed by ITC Midwest. | M5_In Service | 1240048 | Engineering | 2014 | IA |  |  | 72 | 72 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 460000 | 169.6% | N/A | 0
A in MTEP15 | Central | AmerenMO | 8840 | 2015-12-28 | 20747 | 2016-12-12 | LN | 2016-11-14 | Heritage | Hitt | 1 | 161 | 161 | Extend 0.2 mile 161 kV line from Heritage to Hitt 161-34.5 kV Substation. | M5_In Service | 619882 | Planning | 2014 | MO |  | 0.2 | 56 | 56 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-11-14 | Planned | 120000 | 416.6% | N/A | 0
A in MTEP15 | West | ATC | 3159 | 2016-10-03 | 5547 | 2017-06-30 | LN | 2017-11-15 | West Middleton | Timberlane Tap | 1 | 69 |  | Uprate West Middleton to Timberlane Tap 69 kV Line | Planned | 2000000 | Planning Preliminary |  | WI | 1.8 |  | 84 | 118 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2000000 | 0% | Project scope increase. | -1
A in MTEP15 | West | ATC | 3159 | 2016-10-03 | 5548 | 2013-09-10 | LN | 2018-12-31 | Timberlane Tap | Stage Coach | 1 | 69 |  | Uprate Timberlane Tap to Stage Coach 69 kV Line | Planned |  | Planning Preliminary |  | WI | 2.4 |  | 88 | 118 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4353 | 2015-12-28 | 8328 | 2016-12-29 | SUB | 2018-02-01 | Creekview |  |  | 138 |  | New 138kV Creekview substation | Planned | 25000000 | Planning |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 16000000 | 56.25% | Updated cost estimate. | 2
A in MTEP15 | West | ATC | 4353 | 2015-12-28 | 8329 | 2016-03-29 | LN | 2017-12-01 | Forward Energy Center | Creekview | 1 | 138 |  | Loop Forward Energy Center - South Fond Du Lac 138kV line into new Creekview SS | Planned |  | Planning |  | WI | 7.58 |  | 246 | 325 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4353 | 2015-12-28 | 8330 | 2016-03-29 | LN | 2017-12-01 | Creekview | South Fond Du Lac | 1 | 138 |  | Loop Forward Energy Center - South Fond Du Lac 138kV line into new Creekview SS | Planned |  | Planning |  | WI | 13.2 |  | 246 | 325 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 0 | 0% | Project schedule update. , | 0
A in MTEP15 | West | ATC | 4419 | 2015-12-28 | 8439 | 2017-06-30 | TEQ | 2016-05-17 | Sunset Point | Ellinwood | 1 | 138 |  | Uprate Sunset Point - Ellinwood (SPTG311) 138kV line at Sunset Point from 795 Drake ACSR and 500 Cu37 jumpers with 2156 ACSR Bluebird | Planned | 100000 |  |  | WI |  |  | 246 | 246 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 109000 | -8.257% | Updated estimate | -1
A in MTEP15 | West | ATC | 4421 | 2015-12-28 | 8441 | 2017-03-30 | LN | 2018-12-31 | Elkhorn | Williams Bay | 1 | 138 |  | Loop Elkhorn - Brick Church (X-44) 138kV line into Williams Bay | Planned |  | Engineering | 2016 | WI | 7.67 |  | 197 | 197 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-07-01 | Planned | 875000 | -100% | Updated estimate. | 17
A in MTEP15 | West | ATC | 4421 | 2015-12-28 | 8442 | 2017-03-30 | LN | 2018-12-31 | Brick Church | Williams Bay | 1 | 138 |  | Loop Elkhorn - Brick Church (X-44) 138kV line into Williams Bay | Planned |  |  |  | WI | 6.62 |  | 188 | 188 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-07-01 | Planned | 0 | 0% |  | 17
A in MTEP15 | West | ATC | 4421 | 2015-12-28 | 8443 | 2017-03-30 | CB | 2018-12-31 | Williams Bay |  |  | 138 |  | Add line breaker to Elkhorn - Williams Bay (X-44) 138kV line at Williams Bay | Planned | 4400000 | Engineering | 2016 | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-07-01 | Planned | 3575000 | 23.08% | Updated estimate. | 17
A in MTEP15 | West | ATC | 4421 | 2015-12-28 | 8444 | 2017-03-30 | CB | 2018-12-31 | Williams Bay |  |  | 138 |  | Add line breaker to Brick Church - Williams Bay (X-44) 138kV line at Williams Bay | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-07-01 | Planned | 0 | 0% |  | 17
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8445 | 2016-06-30 | TX | 2016-08-19 | Brillion Iron Works |  | 1 | 138 | 69 | New 138/69kV transformer at new Brillion Iron Works substation | Planned |  |  |  | WI |  |  | 60 | 100 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8446 | 2016-06-30 | SUB | 2016-08-19 | Brillion Iron Works |  |  | 138 |  | New Brillion Iron Works (BIW) substation | Planned |  | Engineering |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8447 | 2017-03-30 | LN | 2016-12-01 | Shoto | Brillion Iron Works | 1 | 138 |  | Loop Shoto - Glenview (L-90) 138kV line into Brillion Iron Works | M5_In Service | 12800000 | Engineering |  | WI | 22.43 |  | 105 | 139 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 12500000 | 2.4% | Costs for project rolled in to one facility | 4
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8448 | 2016-06-30 | LN | 2016-08-19 | Glenview | Brillion Iron Works | 1 | 138 |  | Loop Shoto - Glenview (L-90) 138kV line into Brillion Iron Works | Planned |  |  |  | WI | 1.09 |  | 174 | 174 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8449 | 2016-06-30 | LN | 2016-08-19 | Glenview | Brillion Iron Works | 1 | 69 |  | Expand Glenview - Brillion Iron (M-65) 69kV line to the new Brillion Iron Works 69kV bus | Planned |  |  |  | WI | 0.95 |  | 39 | 51 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8450 | 2016-06-30 | LN | 2016-08-19 | Brillion Iron Works | Brillion Iron Works Arc | 1 | 69 |  | Brillion Iron Works - Brillion Iron Works Arc 69kV line arc furnace service | Planned |  | Engineering |  | WI |  | 0.11 | 87 | 87 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4422 | 2015-12-28 | 8451 | 2017-06-29 | LN | 2016-08-19 | Forest Junction | Glenview | 1 | 138 |  | Uprate Forest Junction - Glenview (E-57) 138kV line | M5_In Service |  | Engineering | 2016 | WI | 4.62 |  | 174 | 184 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-19 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4732 | 2015-12-28 | 8969 | 2016-06-30 | LN | 2018-12-01 | Ogden St. | Bayshore | 1 | 69 |  | Construct a new 69kV line from Ogden St. - Bayshore | Planned | 10400000 | Engineering | 2012 | WI |  | 0.54 | 123 | 168 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 10400000 | 0% |  | 0
A in MTEP15 | West | ATC | 4732 | 2015-12-28 | 8970 | 2016-06-30 | LNrb | 2018-12-01 | Bayshore | 2nd St. | 1 | 69 |  | Rebuild Bayshore - 2nd St. (N-14) 69kV | Planned |  |  |  | WI | 0.15 |  | 123 | 168 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4732 | 2015-12-28 | 8971 | 2016-06-30 | LNrb | 2018-12-01 | 2nd St. | Fiber swtiching structure | 1 | 69 |  | Rebuild 2nd St. - Fiber switching structure (N-14) 69kV | Planned |  |  |  | WI | 0.59 |  | 123 | 168 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4732 | 2015-12-28 | 8972 | 2016-06-30 | CB | 2018-12-01 | Ogden St. |  |  | 69 |  | Odgen St. - Wells St. 69kV breaker | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 4732 | 2015-12-28 | 8973 | 2016-06-30 | CB | 2018-12-01 | Ogden St. |  |  | 69 |  | Odgen St. - Bayshore 69kV breaker | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7601 | 2015-12-28 | 20036 | 2017-06-30 | Remove | 2016-06-21 | Lakehead Portage |  |  | 69 |  | Remove 16 Mvar mobile capacitor bank at Lakehead Portage 69 kV | M5_In Service |  | Engineering |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-07-01 | Planned | 3400000 | -100% |  | -1
A in MTEP15 | West | ATC | 7602 | 2015-12-28 | 20037 | 2017-03-31 | LNup | 2019-11-01 | Bunker Hill | Kelly | 1 | 115 |  | Rerate Bunker Hill - Kelly 115 kV as part of Blackbrook/Bunker Hill retirment (PR05440) | Planned | 3800000 | Engineering |  | WI | 19.47 |  | 145 | 173 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-10-31 | Planned | 4800000 | -20.83% |  | 1
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20038 | 2014-09-08 | Remove | 2019-11-01 | Blackbrook |  |  | 115 |  | Retire Blackbrook 115 kV station | Planned | 25200000 | Engineering |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 25200000 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20039 | 2014-09-08 | Remove | 2019-11-01 | Bunker Hill |  |  | 115 |  | Retire Bunker Hill 115 kV station | Planned |  | Engineering |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20040 | 2014-09-08 | SwSta | 2019-11-01 | Roehring Rd |  |  | 115 |  | Build new 115 kV 4 position ring bus named Roehring Rd | Planned |  | Engineering |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20041 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Gardner Park | 1 | 115 |  | Rebuild A-313a Gardner Park - Roehring Rd 115kV with double circuit structures | Planned |  | Engineering |  | WI | 34.33 |  | 145 | 196 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20042 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Antigo | 1 | 115 |  | Rebuild A-313b Antigo - Roehring Rd 115kV | Planned |  | Engineering |  | WI | 5.85 |  | 145 | 189 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20043 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Kelly | 1 | 115 |  | Rebuild M-13a Kelly - Roehring Rd 115 kV | Planned |  | Engineering |  | WI | 19.47 |  | 145 | 173 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7603 | 2015-12-28 | 20044 | 2014-09-08 | LNrb | 2019-11-01 | Roehring Rd | Pine | 1 | 115 |  | Rebuild M-13b Pine - Roehring Rd 115 kV with double circuit structures | Planned |  | Engineering |  | WI | 10.89 |  | 145 | 196 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 7741 | 2015-12-28 | 20069 | 2017-03-30 | CAP | 2016-11-30 | Dellwood |  |  | 69 |  | Add 8.17 Mvar capacitor bank at Dellwood 69 kV station | M5_In Service | 3200000 | Engineering | 2014 | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-15 | Planned | 3100000 | 3.226% | Updated estimate. | -1
A in MTEP15 | West | ATC | 7741 | 2015-12-28 | 20070 | 2017-03-30 | Remove | 2016-11-30 | McKenna |  |  | 69 |  | Remove 15.3 Mvar mobile capacitor bank from McKenna station. | M5_In Service |  | Engineering | 2014 | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-15 | Planned | 0 | 0% |  | -1
A in MTEP15 | West | ATC | 7780 | 2015-12-28 | 20086 | 2017-03-31 | TX | 2017-01-28 | Esker View |  | 1 | 138 | 24.9 | Build 138/24.9 kV distribution transformer | M5_In Service | 4200000 | Engineering | 2014 | WI |  |  | 32 | 39 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-03-01 | Planned | 4500000 | -6.667% |  | -2
A in MTEP15 | West | ATC | 7981 | 2015-12-28 | 20252 | 2017-03-30 | CB | 2016-12-09 | Beardsley St |  |  | 69 |  | Add breakers at Beardsley St to sectionalize J-10 | M5_In Service | 2500000 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 2500000 | 0% | Initial estimate entry. | 0
A in MTEP15 | West | ATC | 8065 | 2015-12-28 | 20373 | 2015-07-24 | LNrb | 2020-12-31 | Pleasant Prairie | New Sub | 1 | 345 |  | Loop Arcadian - Pleasant Prairie (PLPL81) 345 kV into new New Sub switching station | Planned |  | Planning Preliminary |  | WI | 0 | 0.8 | 1146 | 1488 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 8065 | 2015-12-28 | 20375 | 2015-07-24 | LNrb | 2020-12-31 | Arcadian | New Sub | 1 | 345 |  | Loop Arcadian - Pleasant Prairie (PLPL81) 345 kV into new New Sub switching station | Planned |  | Planning Preliminary |  | WI | 14.8 | 0.8 | 928 | 928 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 8065 | 2015-12-28 | 20376 | 2016-03-30 | LNrb | 2020-12-31 | Zion | New Sub | 1 | 345 |  | Loop Zion - Libertyville (2224) 345 kV into new New Sub switching station | Planned | 52000000 | Planning Preliminary | 2015 | IL | 0 | 2 | 1201 | 1201 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 52000000 | 0% | Initial estimate. | 0
A in MTEP15 | West | ATC | 8065 | 2015-12-28 | 20377 | 2015-07-24 | LNrb | 2020-12-31 | Libertyville | New Sub | 1 | 345 |  | Loop Zion - Libertyville (2224) 345 kV into new New Sub switching station | Planned |  | Planning Preliminary |  | IL | 0 | 2 | 1201 | 1201 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 8065 | 2015-12-28 | 20378 | 2015-07-24 | SwSta | 2020-12-31 | New Sub |  |  | 345 |  | New 345 kV New Sub switching station | Planned |  | Planning Preliminary |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 8071 | 2015-12-28 | 20389 | 2016-09-29 | LN | 2023-12-31 | Plains | National | 1 | 138 |  | New 138 kV line from Plains - National | Planned | 124602000 | Planning |  | MI | 0 | 57 | 294 | 402 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2023-12-31 | Planned | 124602000 | 0% | Revised estimate. | 0
A in MTEP15 | West | ATC | 8660 | 2015-12-28 | 20719 | 2017-06-29 | TX | 2020-09-01 | Somers |  | 2 | 138 | 24.9 | 2nd Somers distribution transformer | Planned | 8000000 | Planning Preliminary | 2014 | WI |  |  | 66 | 74 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-09-01 | Planned | 2800000 | 185.7% | Updated estimate. | 0
A in MTEP15 | West | ATC | 8660 | 2015-12-28 | 20720 | 2016-06-30 | CB | 2020-09-01 | Albers |  | 1 | 138 |  | New line breaker for Bain - Albers | Planned |  | Planning Preliminary |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-09-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 8660 | 2015-12-28 | 20721 | 2016-06-30 | CB | 2020-09-01 | Albers |  |  | 138 |  | New line breaker from Albers to Somers. | Planned |  | Planning Preliminary | 2014 | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-09-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 9080 | 2016-12-30 | 20810 | 2016-09-29 | CB | 2018-12-31 | W. Marinette |  | 2 | 138 |  | Install high and low side breakers on existing 138/69 kV transformer on circuit 2. | Planned | 4500000 | Planning |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 4500000 | 0% | Re-entered to reflect planning estimate. | 0
A in MTEP15 | West | ATC | 9080 | 2016-12-30 | 20812 | 2016-09-29 | CB | 2018-12-31 | W. Marinette |  | 1 | 138 |  | Install W. Marinette 138-69 kV transformer high-side protection on circuit 1. | Planned |  | Planning |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | West | ATC | 9081 | 2015-12-28 | 20811 | 2017-06-30 | LNrc | 2018-03-01 | Depere | Glory Rd | 1 | 138 |  | Reconductor R122 De Pere - Glory Road 138 kV underground and overhead lines. | Planned | 950000 | Planning |  | WI | 1.14 |  | 290 | 381 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-01 | Planned | 736000 | 29.08% | Scope update | 0
A in MTEP15 | Central | BREC | 3435 | 2015-12-28 | 6338 | 2010-11-15 | LNrc | 2017-12-31 | Rome Junction | West Owensboro | 1 | 69 |  | reconductor line | Planned | 440000 | Planning | 2010 | KY | 5.8 | 0 | 72 MVA | 72 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 440000 | 0% |  | 0
A in MTEP15 | Central | BREC | 3436 | 2015-12-28 | 6339 | 2010-11-15 | LN | 2018-12-31 | Wilson | Sacremento | 1 | 69 |  | new line | Planned | 2100000 | Planning | 2010 | KY | 0 | 11 | 72 MVA | 72 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 2100000 | 0% |  | 0
A in MTEP15 | Central | BREC | 3437 | 2015-12-28 | 6340 | 2010-11-15 | LNrc | 2018-12-31 | Thruston Junction | East Owensboro | 1 | 69 |  | reconductor line | Planned | 40000 | Planning | 2010 | KY | 0.4 | 0 | 67 MVA | 67 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 40000 | 0% |  | 0
A in MTEP15 | Central | BREC | 3438 | 2015-12-28 | 6341 | 2010-11-15 | LNrc | 2018-12-31 | Daviess County | Philpot Tap | 1 | 69 |  | reconductor line | Planned | 580000 | Planning | 2010 | KY | 7.7 | 0 | 72 MVA | 72 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 580000 | 0% |  | 0
A in MTEP15 | Central | BREC | 3441 | 2015-12-28 | 6344 | 2014-06-10 | LNrc | 2015-12-31 | Olivet Church Road | Olivet Church Road Tap | 1 | 69 |  | reconductor line | Planned | 150000 | Planning | 2010 | KY | 1.4 | 0 | 72 MVA | 72 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2015-12-31 | Planned | 150000 | 0% |  | 0
A in MTEP15 | Central | BREC | 3444 | 2015-12-28 | 6347 | 2014-06-10 | TX | 2015-12-31 | Meade County 161 kV | Meade County 69 kV |  | 161 | 69 | new transformers | Planned | 4000000 | Planning | 2010 | KY |  |  | 56 MVA | 56 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 4000000 | 0% |  | 0
A in MTEP15 | Central | BREC | 9420 | 2015-12-28 | 21557 | 2015-11-05 | LINE | 2017-03-31 | Coleman EHV | Aleris (LAM1) |  | 161 |  | Construction of a 1.7 mile long 161 kV radial circuit from Coleman EHV to serve the 28 MW load at the existing 161/13.8 kV delivery point. | Planned | 640000 | Planning |  | KY |  | 1.7 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | Planned | 640000 | 0% |  | 0
A in MTEP15 | Central | BREC | 9420 | 2015-12-28 | 21558 | 2015-11-05 | LINE | 2017-03-31 | Coleman EHV | Aleris (LAM2) |  | 161 |  | Construction of a 2 mile 161 kV circuit to provide service to a new 161/13.8 kV delivery point necessary to serve the expanded load . | Planned | 760000 | Planning |  | KY |  | 2 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | Planned | 760000 | 0% |  | 0
A in MTEP15 | Central | BREC | 9420 | 2015-12-28 | 21561 | 2015-11-05 | SUB | 2017-03-31 | Aleris (LAM2) | Coleman EHV |  | 161 |  | This substation will provide the planned 33 MW direct-serve load expansion at Aleris (LAM2). The existing 28 MW direct-serve load will be served from the existing Aleris (LAM1) substation. Both circuits will normally be fed from Coleman EHV 161 kV. In the event of an emergency, existing backup service feeds from the Hancock 161 kV substation remain available. | Planned | 7000000 | Planning |  | KY |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | Planned | 7000000 | 0% |  | 0
A in MTEP15 | Central | BREC | 9420 | 2015-12-28 | 21562 | 2016-01-12 | TEQ | 2017-03-31 | Coleman EHV |  |  | 161 |  | Terminal equipment and breakers will be installed at Coleman EHV 161 kV to accommodate service to the direct-serve Aleris loads (LAM1 & LAM2). | Planned | 1150000 | Planning |  | KY |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | Planned | 1150000 | 0% |  | 0
A in MTEP15 | Central | BREC | 10142 | 2015-12-28 | 21472 | 2017-05-22 | TEQ | 2021-01-01 | Coleman |  |  | 345 |  | Sub upgrades at Coleman | Planned | 5200000 | Planning Preliminary |  | KY |  |  |  |  | MEP | Shared |  | Y | Y | Y | Top-Down | A | 2021-01-01 | Planned | 5232998 | -0.6306% |  | 0
A in MTEP15 | Central | BREC, Vectren | 10142 | 2015-12-28 | 21471 | 2016-01-13 | LN | 2021-01-01 | Duff | Coleman |  | 345 |  | New Duff-Coleman 345 kV, single circuit. MISO portion is 2 segments - 24.5 and 4 miles, cut into by double circuit PJM section to Rockport | Planned | 59117869 | Planning Preliminary |  | IN,KY |  | 28.5 |  |  | MEP | Shared |  | Y | Y | Y | Top-Down | A | 2021-01-01 | Planned | 59117869 | 0% |  | 0
A in MTEP15 | South | CLECO | 7988 | 2015-12-28 | 20260 | 2016-09-15 | SUB | 2018-06-01 | Bayou Vista 230 | Bayou Vista 138 kV | 1 | 230 | 138 | CLECO will expand Bayou Vista substation to 230 kV and install 230-138 kV autotransformer | Planned |  | Planning |  | LA |  |  | 500 MVA | 550 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | CLECO | 8980 | 2015-12-28 | 20867 | 2015-07-10 | BUS | 2015-10-30 | West Fork |  |  | 230 |  | Replace the Existing 230 kV high side bus at West Fork with a 3 terminal Ring bus with Breakers. | Under Construction | 2308708 | Budgetary |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-10-30 | Under Construction | 2308708 | 0% |  | 0
A in MTEP15 | South | CLECO | 9042 | 2015-12-28 | 20864 | 2015-07-10 | CB | 2015-10-01 | Coughlin |  |  | 138 |  | Replace Breakers 8000, 8128, 8006, 8115, 8009 due to available fault current exceeding the short circuit rating of the existing breakers. | Under Construction | 725008 | Budgetary |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-10-01 | Under Construction | 725008 | 0% |  | 0
A in MTEP15 | South | CLECO | 9340 | 2015-12-28 | 20873 | 2015-07-17 | SUB | 2016-12-01 | Longville |  |  | 138 |  | Build a new 138 kV substation Longville tapped into the Deridder to Nelson 138 kV line. 18.3 miles from Deridder & 24.3 miles from Nelson. | Planned | 4400000 | Budgetary |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 4400000 | 0% |  | 0
A in MTEP15 | South | CLECO | 9421 | 2015-12-28 | 20898 | 2015-07-28 | SUB | 2017-06-01 | Plaisance | Veazie | 1 | 138 |  | New substation tapped into the Plaisance to Veazie 138 kV line | Planned | 4360000 | Budgetary |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 4360000 | 0% |  | 0
A in MTEP15 | South | CLECO | 9421 | 2015-12-28 | 20900 | 2015-07-28 | LN | 2017-06-01 | Plaisance | Veazie | 1 | 138 |  | Build 138 kV line from existing transmission line to customers location 0.7 miles. | Planned | 1040000 | Budgetary |  | LA |  | 0.7 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1040000 | 0% |  | 0
A in MTEP15 | South | CLECO, Entergy-LA | 7988 | 2015-12-28 | 20258 | 2017-06-26 | LN | 2018-06-01 | Terrebonne 230 kV | Bayou Vista 230 kV | 1 | 230 |  | Construct approximately 30.33 miles from Terrebonne to Bayou Vista 230 kV line using conductor ACSS 954 cardinal rated at 640 MVA. | Planned | 75950235 | Planning |  | LA |  | 30.33 | 640 | 640 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 75900000 | 0.06619% | Schedule | 0
A in MTEP15 | Central | CWLD | 8300 | 2017-04-12 | 20634 | 2017-04-11 | LN | 2021-06-01 | Perche | Mill Creek | 1 | 161 |  | New 161 kV line from Perche to Mill Creek | Planned | 12000000 |  |  | MO |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 12000000 | 0% |  | 48
A in MTEP15 | Central | CWLD | 8300 | 2017-04-12 | 20635 | 2017-04-11 | LN | 2021-06-01 | Grindstone | Mill Creek | 1 | 161 |  | New 161 kV line from Grindstone to Mill Creek | Planned | 6000000 |  |  | MO |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 6000000 | 0% |  | 48
A in MTEP15 | Central | CWLD | 8300 | 2017-04-12 | 20636 | 2017-04-11 | LN | 2026-06-01 | McBaine | Mill Creek | 1 | 161 |  | New 161 kV line from McBain to Mill Creek | Planned | 9000000 |  |  | MO |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2022-06-01 | Planned | 9000000 | 0% |  | 48
A in MTEP15 | Central | CWLD | 8300 | 2017-04-12 | 20637 | 2017-04-11 | SUB | 2021-06-01 | Mill Creek |  |  | 161 | 13.8 | New Mill Creek 161/13.8 kV substation | Planned | 5000000 |  |  | MO |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 5000000 | 0% |  | 48
A in MTEP15 | Central | DEI | 2144 | 2015-12-28 | 2930 | 2016-12-16 | LNrc | 2017-12-31 | Franklin 230 | Earlywood | 1 | 69 |  | Franklin 230kV sub to Earlywood sub reconductor 1.06 mile - 69kV - 69165 line with 954ACSR@100C | M4_Pre-Construction | 1170000 | Engineering w/AFUDC | 2013 | IN | 1.06 |  | 143 | 143 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-30 | M3_Long Lead Materials | 1170000 | 0% |  | 6
A in MTEP15 | Central | DEI | 7882 | 2015-12-28 | 20111 | 2017-06-02 | LN | 2018-10-01 | Bloomington Rogers St. | Bloomington Dunn St. | 1 | 69 |  | Construct new 69kV line from Bloomington Rogers St. to Bloomington Dunn St. (also includes Dunn St. bus work - AMIN1046) 954ACSR@100C | Under Construction | 4820000 | Engineering w/AFUDC | 2014 | IN |  | 3 | 153 | 153 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 4820000 | 0% |  | 16
A in MTEP15 | Central | DEI | 7883 | 2015-12-28 | 20112 | 2017-06-02 | Dist | 2018-06-01 | Bloomington Downtown | new distribution sub |  | 69 | 12 | Construct new 22.4MVA - 69/12kV sub near downtown Bloomington in the new line established by project AMIN1047 / 7882. | Under Construction | 602000 | Engineering w/AFUDC | 2014 | IN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-02 | M3_Long Lead Materials | 602000 | 0% |  | 12
A in MTEP15 | Central | DEI | 7885 | 2015-12-28 | 20115 | 2017-04-28 | LNrc | 2017-11-28 | Frankfort Burlington St. | Middlefork | 1 | 69 |  | Frankfort Burlington St to Middlefork 69kV - 69133 ckt: Reconductor 12.4 miles with 954ACSR@100C | Under Construction | 6636000 | Engineering w/AFUDC | 2014 | IN | 12.4 |  | 153 | 153 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-03-31 | M4_Pre-Construction | 6636000 | 0% |  | 8
A in MTEP15 | Central | DEI | 7903 | 2015-12-28 | 20140 | 2015-12-01 | LNrc | 2025-06-01 | Martinsville SE | HE Park Ave | 1 | 69 |  | Martinsville SE - HE Park Ave 69kV - 6903 ckt: Reconductor 3.4 miles with 954ACSR@100C | M1_Final SPM or OOC | 2102000 | Engineering w/AFUDC | 2014 | IN | 3.4 |  | 153 | 153 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2025-06-01 | M1_Final SPM or OOC | 2102000 | 0% |  | 0
A in MTEP15 | Central | DEI | 7911 | 2015-12-28 | 20155 | 2017-03-08 | SUB | 2018-12-31 | Frankfort 230kV |  |  | 230 | 69 | Frankfort 230kV: complete 4-brkr ring bus; 69kV: complete 6-brkr ring bus and retire Jefferson Jct with new line terminal for 69kV line to Frankfort Muni. | M3_Long Lead Materials | 5109020 | Engineering w/AFUDC | 2014 | IN |  |  | 2000A | 2000A | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 5109020 | 0% |  | 0
A in MTEP15 | Central | DEI | 7946 | 2015-12-28 | 20197 | 2017-06-02 | LN | 2018-08-31 | Speed | Jeffersonville | 1 | 138 |  | Loop existing 138kV line from Speed to Clark Maritime to Jeffersonville. Add 2.52 mile 138kV line section from Speed to Memphis Jct and tie into existing 13890 circuit. Add .01 mile 138kV line section from Jeffersonville Jct. to Jeffersonville sub. Install 138kV line terminals at Speed and Jeffersonville. | Under Construction | 5472000 | Engineering w/AFUDC | 2014 | IN |  | 2.53 | 306 | 306 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 5472000 | 0% |  | 8
A in MTEP15 | Central | DEI | 7953 | 2015-12-28 | 20213 | 2017-06-02 | LN | 2017-07-01 | Mohawk Industrial | Mohawk 138 | 1 | 69 |  | New 1.2 mile 69kV line to complete 69130 ckt. loop through Mohawk Industrial 69/12kV sub. | Under Construction | 1309000 | Engineering w/AFUDC | 2014 | IN |  | 1.2 | 153 | 153 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 1309000 | 0% |  | 7
A in MTEP15 | Central | DEI | 7957 | 2015-12-28 | 20218 | 2017-06-02 | Dist | 2017-10-01 | Kokomo S. Main St. |  |  | 69 | 12 | Relocate Kokomo S. Main St. 69/12kV distribution sub to higher ground (rename sub Kokomo Apperson) | Under Construction | 1261000 | Engineering w/AFUDC | 2014 | IN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 1261000 | 0% |  | 4
A in MTEP15 | Central | DEI | 7961 | 2016-06-14 | 20225 | 2017-03-08 | CB | 2017-12-31 | Fairview 138 |  |  | 138 |  | Fairview 138kV Breaker Replacements: replace OCB 13858, 13854, and relays at line terminals 13854, 13855, 13858 | M4_Pre-Construction | 4211000 | Engineering w/AFUDC | 2014 | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 4211000 | 0% | scope increase - ring bus (see comments) | 0
A in MTEP15 | Central | DEI | 7963 | 2015-12-28 | 20226 | 2017-03-08 | CB | 2018-12-31 | New Castle 138 |  |  | 138 |  | New Castle 138kV Breaker Replacements: replace OCB 13805, 13835, 13842, 13873, 13869-1, 13869-2, and relays at line terminals 13805, 13835, 13842, 13873, 13843 | M3_Long Lead Materials | 2516322 | Engineering w/AFUDC | 2014 | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 2516322 | 0% |  | 0
A in MTEP15 | Central | DEI | 7964 | 2015-12-28 | 20227 | 2017-03-08 | CB | 2018-12-31 | Kokomo Highland Park |  |  | 138 | 69 | Kokomo Highland Park Equipment: Replace OCB 69230-4, -5, -6, -7, OCB BK 7 CAP, 69kV primary UG cables, relays at terminals 6910, 6911, 6913, 6928, 6992, 13879, 13887, 138kV TRANSFER | M3_Long Lead Materials | 3351124 | Engineering w/AFUDC | 2014 | IN |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 3351124 | 0% |  | 0
A in MTEP15 | Central | DEI | 7969 | 2015-12-28 | 20232 | 2017-03-08 | LNup | 2017-12-31 | Edwardsport | Amo |  | 345 |  | Edwardsport - Amo 345kV - 34528 ckt. replace intermediate tansient structures with deadend structures - every 2.5 miles (22 structures). | M4_Pre-Construction | 16052359 | Engineering w/AFUDC | 2015 | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 16052359 | 0% |  | 0
A in MTEP15 | Central | DEI | 7974 | 2015-12-28 | 20237 | 2017-03-08 | LNrc | 2018-12-31 | Lafayette 230kV | Attica |  | 230 | 138 | Lafayette 230 - Attica 230kV - 23027 ckt: Reconductor 5.4 miles at Lafayette 230 end with 900ACSR-OVAL@100C; also reconductor portions of double-circuited 13877 and 13878 circuits with 954ACSR-OVAL@100C - total of 9.9 miles. | M3_Long Lead Materials | 3684530 | Engineering w/AFUDC | 2014 | IN | 15.3 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 3684530 | 0% |  | 0
A in MTEP15 | Central | DEI | 7982 | 2015-12-28 | 20251 | 2017-03-08 | LNrc | 2018-12-31 | Advance | Dover | 1 | 69 |  | Advance - Dover 69kV - 69134 ckt: Rebuild 7.9 mile line with 477ACSR@100C - replacing all structures with steel poles. | M3_Long Lead Materials | 6765874 | Engineering w/AFUDC | 2014 | IN | 7.9 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 4903384 | 37.98% | increased cost for new standard steel pole construction | 12
A in MTEP15 | Central | DEI | 7984 | 2015-12-28 | 20254 | 2017-03-08 | LNup | 2018-12-31 | Medora | Brownstown | 1 | 69 |  | Medora - Brownstown 69kV - 6952 ckt: Rebuild 4.85 mile line transferring existing 477ACSR conductor - replacing all structures with steel poles. | M3_Long Lead Materials | 2590705 | Engineering w/AFUDC | 2015 | IN | 4.85 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 2590705 | 0% |  | 0
A in MTEP15 | Central | DEI | 7987 | 2015-12-28 | 20257 | 2016-10-04 | LNrc | 2020-12-31 | New Pekin Jct | Salem | 1 | 69 |  | New Pekin Jct - Salem 69kV - 69153 ckt: Rebuild 9.4 mile line with 477ACSR@100C - replacing all structures with steel poles. | M1_Final SPM or OOC | 4028000 | Engineering w/AFUDC | 2014 | IN | 9.4 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 4028000 | 0% |  | 24
A in MTEP15 | Central | DEI | 7989 | 2015-12-28 | 20259 | 2016-11-23 | LNrc | 2016-11-07 | Edwardsport | Odon Jct | 1 | 69 |  | Edwardsport - HE Rogers Jct 69kV - 6951 ckt: Rebuild 9.8 mile line with 477ACSR@100C - replacing all structures with steel poles. (HE Rogers Jct is located between Edwpt and Odon Jct) | M5_In Service | 7391505 | Engineering w/AFUDC | 2014 | IN | 9.8 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 7391505 | 0% |  | -1
A in MTEP15 | Central | DEI | 7991 | 2015-12-28 | 20261 | 2017-04-11 | LNrc | 2017-03-29 | Rushville | HE Milroy | 1 | 69 |  | Rushville - HE Milroy 69kV - 6920 ckt: Rebuild 7.2 mile line with 477ACSR@100C - replacing all structures with steel poles. | M5_In Service | 6699202 | Engineering w/AFUDC | 2015 | IN | 7.2 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 6699202 | 0% |  | 3
A in MTEP15 | Central | DEI | 7992 | 2015-12-28 | 20265 | 2016-10-04 | LNrc | 2020-12-31 | Hillenbrand Jct | Andersonville Jct | 1 | 69 |  | Hillenbrand Jct - Batesville North - Andersonville Jct 69kV - 6919 ckt: Rebuild 7.93 mile line with 477ACSR@100C - replacing all structures with steel poles. | M1_Final SPM or OOC | 6472095 | Engineering w/AFUDC | 2015 | IN | 7.93 |  | 100 | 100 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 6472095 | 0% |  | 24
A in MTEP15 | Central | DEI | 9246 | 2015-12-28 | 20849 | 2016-11-04 | LN | 2019-06-01 | Lafayette Southeast | Lafayette South Jct 2 | 1 | 138 |  | Lafayette SE to new Lafayette S Jct 2 (in existing 13808 ckt.) - build new 138kV - 1.75 mile - 954acsr@100c - 13899 ckt.; add new breaker in Laf SE ring; add (2) line switches at new jct and operate Laf S Jct to Laf S Jct 2 N.O. | M3_Long Lead Materials | 3976181 | Engineering w/AFUDC | 2015 | IN |  | 1.75 | 301 | 301 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 3976181 | 0% |  | 24
A in MTEP15 | Central | DEI | 9247 | 2015-12-28 | 20850 | 2016-11-04 | SUB | 2018-12-31 | Lafayette 230kV | bus tie brkr |  | 138 |  | Lafayette 230 sub - insert a redundant 138kV bus tie breaker in series with existing breaker; add redundant bus differential relays to both 138kV bus 1 and 2. Scope also includes (5) 138Kv antiquated breaker and relay replacements, disconnect switches and misc buswork. | M3_Long Lead Materials | 3400000 | Planning Preliminary | 2015 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | M1_Final SPM or OOC | 4500000 | -24.44% |  | 18
A in MTEP15 | Central | DEI, HE | 7940 | 2015-12-28 | 20191 | 2017-06-02 | LNrb | 2018-05-07 | Bedford | HE Worthington | 1 | 138 |  | Bedford - Owensburg - HE Buena Vista - HE Worthington 138kV - 13840 ckt: Reconductor 33 miles with 954ACSR and replace all structures. Also reconductor 2.29 miles of 13823 where it is double circuited with 954ACSR near the Bedford end. Upgrade Bedford 13840 brkr and terminal equipment to 2000A. New ROW will be required. | M3_Long Lead Materials | 36169000 | Engineering w/AFUDC | 2014 | IN | 35 |  | 230 | 230 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-07-31 | M3_Long Lead Materials | 36169000 | 0% |  | -2
A in MTEP15 | West | DPC | 7664 | 2015-12-28 | 20663 | 2017-06-01 | LNrb | 2017-04-11 | Briggs Road | La Crosse Tap switch | 1 | 161 |  | DPC will rebuild the existing 161 kV line following existing ROW between the Briggs Road substation to the 3-way switch called La Crosse Tap that looks towards Genoa, XEL La Crosse and XEL Briggs Road | M5_In Service | 11000000 | Planning | 2014 | WI | 13.3 | 0 | 414 | 445 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-04-21 | Planned | 12000000 | -8.333% |  | 0
A in MTEP15 | South | Entergy-AR | 4666 | 2015-12-28 | 8847 | 2017-06-23 | LNrc | 2019-12-01 | Mabelvale 115 kV Substation | Bryant 115 kV Substation | 1 | 115 |  | Reconductor Line | Planned | 6234161 | Planning |  | AR | 5 |  | 390 MVA | 390 MVA | Other |  | Economic | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 6371120 | -2.15% | Scoping | 0
A in MTEP15 | South | Entergy-AR | 4666 | 2015-12-28 | 21439 | 2016-09-14 | LNrb | 2019-12-01 | Bryant | Bryant South | 1 | 115 |  | 115 kV line | Planned |  |  |  | AR |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 4669 | 2016-02-16 | 8850 | 2017-06-26 | LNcnv | 2019-05-01 | Jim Hill 161 kV substation | Datto 161 kV Substation | 1 | 161 |  | rebuild line and convert from 115kV to 161kV operation | Planned | 59591806 | Planning |  | AR | 39.3 |  | 363 MVA | 363 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-05-01 | Planned | 43729766 | 36.27% | After scoping planned cost increased. | 0
A in MTEP15 | South | Entergy-AR | 4669 | 2016-02-16 | 8851 | 2016-12-15 | CB | 2019-05-01 | Datto 161 kV Substation |  | 1 | 161 |  | Install breakers at Datto | Planned |  |  |  | AR |  |  | 363MVA | 363MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-05-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7925 | 2015-12-28 | 20180 | 2017-01-18 | LN | 2017-01-04 | Black Rock 69kV substation (AECC) | Imboden 69kV substation | 1 | 69 |  | Construct 0.4 mile 69kV transmission line from Black Rock 69kV substation to Imboden 69 kV substation. | M5_In Service | 2689530 | Engineering Preliminary |  | AR |  | 0.4 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-10-15 | Under Construction | 3133719 | -14.17% | Construction | 3
A in MTEP15 | South | Entergy-AR | 7925 | 2015-12-28 | 20181 | 2017-01-18 | CB | 2017-01-04 | Black Rock 69kV Substation (AECC) |  |  | 69 |  | new 69kV circuit breaker to be added at Black Rock 69kV substation. | M5_In Service |  |  |  | AR |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-10-15 | Under Construction | 0 | 0% |  | 3
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20198 | 2017-06-26 | SUB | 2017-11-30 | New EHV 500kV substation |  |  | 500 | 161 | Build a 500/161kV substation where the ISES - Dell 500kV line crosses the Jonesboro-Hergett and Hergett-Trumann West 161kV lines. Cut the 500kV line and the two 161kV lines into the new station. 500kV bus needs to be a 4 breaker ring bus and the terminals need to be layed out such that the two 500kV lines do not share a common breaker. | Under Construction | 78018053 |  |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 74965393 | 4.072% | Increased cost due to more equipment upgrades. | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20199 | 2017-02-13 | SUB | 2017-11-30 | New EHV 161kV substation |  |  | 500 | 161 | Build a 500/161 kV station where the ISES -Dell 500kV line crosses the Jonesboro-Hergett and Hergett - Trumann West 161kV lines. Cut the 500kV line and the two 161kV linesinto the new station. Install an 800MVA 500/161kV auto transformer. | Under Construction |  |  |  | AR |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20200 | 2017-02-13 | TX | 2017-11-30 | New EHV 500kV substation | New EHV 161kV substation |  | 500 | 161 | Install an 800MVA 500/161kV autotransformer (10%Z on 480MVA base.) | Under Construction |  |  |  | AR |  |  | 800 | 800 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20203 | 2017-02-13 | TEQ | 2017-11-30 | Hergett 161kV substation | New EHV 161kv substation | 1 | 161 |  | replace terminal equipment on teh Hergett - new EHV station - Jonesboro 161kV line to achieve a minimum rating of 1300 A or 363MVA. | Under Construction |  |  |  | AR |  |  | 363MVA | 363MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20205 | 2017-02-13 | TEQ | 2017-11-30 | New EHV 161kV substation | Jonesboro 161kV substation | 1 | 161 |  | Upgrade terminal equipment on the Hergett - new EHV station - Jonesboro 161 kV line to achieve a rminimum rating of 1300A or 363MVA. | Under Construction |  |  |  | AR |  |  | 363MVA | 363MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20207 | 2017-02-13 | LNrb | 2017-11-30 | Jonesboro 161KV substation | Jonesboro (SPA) 161kV substation | 1 | 161 |  | rebuild the Jonesboro - Jonesboro (SPA) 161 kV line to a minimum rating of 1950 A or 544MVA. | Under Construction |  |  |  | AR | 0.9 |  | 544MVA | 544MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 7928 | 2015-12-28 | 20208 | 2017-03-23 | LNrb | 2017-11-30 | Hergett 161kV substation | Trumann West 161kV substation | 1 | 161 |  | Rebuild the Hergett - new EHV 161kV substation - Trumann West 161kV line to a minimum rating of 1300A or 363MVA. | M5_In Service |  |  |  | AR | 8.3 |  | 363MVA | 363MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-AR | 8680 | 2015-12-28 | 20729 | 2016-10-05 | TAP | 2016-09-20 | Conway Middle Road |  |  | 161 |  | New 161 kV substation | M5_In Service | 786000 | Planning |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-09-20 | Under Construction | 786000 | 0% | Scoping/Design | 0
A in MTEP15 | South | Entergy-AR | 8681 | 2015-12-28 | 20730 | 2016-10-18 | SUB | 2016-11-01 | Jefferson Industrial |  |  | 115 |  | New 115 kV substation | M5_In Service | 5100110 | Facility Study |  | AR |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-01 | Under Construction | 5257000 | -2.984% |  | 0
A in MTEP15 | South | Entergy-AR | 8860 | 2015-12-28 | 20764 | 2016-10-05 | CB | 2016-12-01 | Paragould |  |  | 115 |  | New circuit bkr | M5_In Service | 256005 | Engineering |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 256005 | 0% | Scoping/Design | 0
A in MTEP15 | South | Entergy-LA | 4604 | 2015-12-28 | 8749 | 2017-06-22 | LNrc | 2017-10-24 | Port Hudson 69 kV substation | Zachary REA substation | 1 | 69 |  | Reconductor Line | Under Construction | 14575634 | Planning |  | LA | 5.76 |  | 143 MVA | 143 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-02-24 | Under Construction | 11202000 | 30.12% | Cost | 8
A in MTEP15 | South | Entergy-LA | 4604 | 2015-12-28 | 8750 | 2017-03-23 | TEQ | 2017-10-24 | Port Hudson 69 kV substation | Zachary REA substation | 1 | 69 |  | Upgrade terminal equipment | Under Construction |  | Planning |  | LA |  |  | 143 MVA | 143 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-02-24 | Under Construction | 0 | 0% |  | 8
A in MTEP15 | South | Entergy-LA | 4606 | 2015-12-28 | 8754 | 2017-06-22 | TX | 2019-03-31 | Fancy Point 500 kV substation | Fancy Point 230 kV substation | 2 | 500 | 230 | Add transformer | Planned | 45641074 | Planning |  | LA |  |  | 1200 MVA | 1200 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-03-01 | Planned | 92000000 | -50.39% | Protracted construction duration driven by scheduling conflicts with nuclear plant. | 0
A in MTEP15 | South | Entergy-LA | 4630 | 2015-12-28 | 8793 | 2017-06-22 | LNrc | 2017-09-30 | Francis 69 kV substation | Marydale 69 kV substation | 1 | 69 |  | Reconductor Line | Under Construction | 12268793 | Planning |  | LA | 7.47 |  | 105 MVA | 105 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 13283208 | -7.637% | Cost | 3
A in MTEP15 | South | Entergy-LA | 7919 | 2015-12-28 | 20174 | 2016-12-22 | CAP | 2016-12-01 | Vincent 230 kV |  |  | 230 |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. Low voltages will occur at the Boudoin, Calcasieu, Pecan Grove, Vincent, Graywood, and Solac 230 kV substations during the single contingency (P1-2) breaker to breaker loss of either Carlyss to Boudoin, Boudoin to Calcasieu, or Calcasieu to Pecan Grove 230 kV line. This project will provide the needed voltage support in the area to mitigate the single contingency events." | M5_In Service | 2245244 | Planning |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 1324421 | 69.53% | Cost | 0
A in MTEP15 | South | Entergy-LA | 7923 | 2015-12-28 | 20178 | 2017-06-22 | LNrc | 2017-12-22 | Lake Charles Bulk 69 kV | Chlomal 69 kV | 1 | 69 |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Lake Charles Bulk to Chlomal 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Calcasieu to Pecan Grove 230 kV line or the Lake Charles Bulk to East Broad 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading line conductor and station equipment at Lake Charles Bulk." | Planned | 7990756 | Planning Preliminary |  | LA | 3.07 |  | 117 MVA | 117 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 2905700 | 175% | Schedule | 6
A in MTEP15 | South | Entergy-LA | 7923 | 2015-12-28 | 20236 | 2017-03-23 | TEQ | 2017-12-22 | Lake Charles Bulk |  |  | 69 |  | LC Bulk-Cholmal Upgrade 600 A switches to 1200 A and upgrade line conductor. | Planned |  | Planning |  | LA |  |  | 117 MVA | 117 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 0 | 0% |  | 6
A in MTEP15 | South | Entergy-LA | 7948 | 2015-12-28 | 20202 | 2017-06-22 | LNrc | 2017-04-13 | 335346 Scott 69 | 335435 Carencro 69 | 1 | 69 |  | "NERC TPL-001-4 Reliability Standards and Entergy's Planning Guidelines. The Scott to Carencro 69 kV line will exceed its thermal rating during the single contingency (P1-2) breaker to breaker loss of the Champagne to Sunset 69 kV line. This project will result in an increase in the thermal rating of the circuit by upgrading line conductor and relay settings at Carencro." | M5_In Service | 6194719 | Planning |  | LA | 6.84 |  | 143 MVA | 143 MVA | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 6822535 | -9.202% | Construction | -2
A in MTEP15 | South | Entergy-LA | 7988 | 2015-12-28 | 20262 | 2016-09-15 | SUB | 2018-06-01 | Terrebonne |  |  | 230 |  | Breakers and switches addition to accomodate new line | Planned |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-LA | 8585 | 2015-12-28 | 20690 | 2017-06-26 | SwSta | 2018-03-01 | Rhodes 500kV Substation |  |  | 500 |  | Construction of a new 500 kV, 3000 A, three breaker ring bus switching station west of Nelson on the Nelson to Hartburg 500 kV line. | Under Construction | 160775919 |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 28070000 | 472.8% | Combine project dollars | 0
A in MTEP15 | South | Entergy-LA | 8586 | 2015-12-28 | 20691 | 2017-03-23 | SUB | 2018-03-01 | TBD |  |  | 500 | 230 | Construct a new 500-230 kV substation west of the existing Carlyss 230 kV substation. This includes the installation of a new 500-230 kV, 1200 MVA autotransformer bank at the new 500-230 kV bulk station comprised of (3) single phase units. | Under Construction |  |  |  | LA |  |  | 1200 MVA | 1200 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 31530000 | -100% | Adjustments | 0
A in MTEP15 | South | Entergy-LA | 8587 | 2015-12-28 | 20692 | 2017-03-23 | LN | 2018-03-01 | Rhodes | TBD | 1 | 500 |  | Construct approximately 11.5 miles of new 500 kV transmission line from the new Rhodes 500 kV switching station to a new 500-230 kV bulk station west of the existing Carlyss 230 kV substation. | Under Construction |  |  |  | LA |  | 7 | 2598 MVA | 2598 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 43000000 | -100% |  | 0
A in MTEP15 | South | Entergy-LA | 8588 | 2015-12-28 | 20693 | 2017-03-23 | LN | 2018-03-01 | TBD | Carlyss | 1 | 230 |  | Construct approximately 1.5 miles of new 230 kV transmission line from the new 500-230 kV bulk substation west of Carlyss to the existing Carlyss 230 kV substation. | Under Construction |  |  |  | LA |  | 4 | 1195 MVA | 1195 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 8690000 | -100% |  | 0
A in MTEP15 | South | Entergy-LA | 8589 | 2015-12-28 | 20694 | 2017-03-23 | CB | 2018-03-01 | Carlyss |  |  | 230 |  | Expand the existing Carlyss 230 kV substation into a breaker and a half operating scheme. Replace the underrated 230 kV breakers with ones having sufficient short circuit interrupting due to the increase in fault currents. The breakers to be replaced are: 8775-IC 13145-CO 13150-CO 13155-CO 13480-CO 13500-CO 13580-CO | Under Construction |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 14050000 | -100% |  | 0
A in MTEP15 | South | Entergy-LA | 8589 | 2015-12-28 | 20696 | 2017-03-23 | BUS | 2018-03-01 | Carlyss |  |  | 230 |  | Expand the existing Carlyss 230 kV substation into a breaker and a half operating scheme. Replace the underrated 230 kV breakers with ones having sufficient short circuit interrupting due to the increase in fault currents. The breakers to be replaced are: 8775-IC 13145-CO 13150-CO 13155-CO 13480-CO 13500-CO 13580-CO | Under Construction |  |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-LA | 8590 | 2015-12-28 | 20695 | 2017-03-23 | LN | 2018-03-01 | Carlyss | Solac | 1 | 230 |  | Construct approximately 12 miles of new 230 kV transmission line from Carlyss to the Solac 230 kV substation. The line will be designed and routed to accommodate a future cut-in into the Calcasieu substation. Add a 230 kV line bay terminal at Carlyss and the Solac 230 kV substation to facilitate the termination of the new line. | Under Construction |  |  |  | LA |  | 12 | 779 MVA | 779 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-03-18 | Under Construction | 33160000 | -100% |  | 0
A in MTEP15 | South | Entergy-LA | 9284 | 2015-12-28 | 20862 | 2017-06-22 | CAP | 2017-12-29 | Bayou Verret |  |  | 230 |  | Install two 40.7 MVAR 230 kV cap banks at Bayou Verret substation. | Planned | 3003163 |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-08-31 | Planned | 1684477 | 78.28% | Schedule | 4
A in MTEP15 | South | Entergy-LA | 9285 | 2015-12-28 | 20863 | 2017-06-22 | LNrb | 2018-10-31 | Waterford | Vacherie | 1 | 230 |  | Reconductor Waterford to Vacherie 230 kV line. | Planned | 18558105 |  |  | LA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 19732950 | -5.954% | Scoping | -8
A in MTEP15 | South | Entergy-MS | 7898 | 2015-12-28 | 20135 | 2016-12-15 | SUBmisc | 2016-11-21 | Greenville |  |  | 115 |  | Upgrade 600A switches to minimum 810A rating (conductor) | M5_In Service | 463871 | Planning |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 463871 | 0% |  | -1
A in MTEP15 | South | Entergy-MS | 7901 | 2015-12-28 | 20137 | 2016-12-15 | RLY | 2016-11-02 | Natchez SES |  |  | 115 |  | upgrade relaying and CTs at Natchez on line 168 and 169 | M5_In Service | 796791 | Planning |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 796791 | 0% |  | -1
A in MTEP15 | South | Entergy-MS | 7901 | 2015-12-28 | 20138 | 2016-12-15 | RLY | 2016-11-02 | Natchez |  |  | 115 |  | Upgrade relaying and CTs on line 168 and 169 | M5_In Service |  | Planning |  | MS |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 0 | 0% |  | -1
A in MTEP15 | South | Entergy-TX | 4617 | 2015-12-28 | 8771 | 2017-06-22 | LNrc | 2017-04-24 | Egypt 138 kV Substatiion | Panorama 138 kV Substation | 1 | 138 |  | Reconductor Line | M5_In Service | 2442780 |  |  | TX | 1.16 |  | 287 MVA | 287 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-05-01 | Under Construction | 3347942 | -27.04% | Schedule | -1
A in MTEP15 | South | Entergy-TX | 4617 | 2015-12-28 | 8772 | 2017-06-22 | TEQ | 2017-04-24 | Panorama 138 kV Substation |  |  | 138 |  | Upgrade Terminal Equipment | M5_In Service |  |  |  | TX |  |  | 287 MVA | 287 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-05-01 | Under Construction | 0 | 0% |  | -1
A in MTEP15 | South | Entergy-TX | 4653 | 2015-12-28 | 21600 | 2017-06-22 | IND | 2017-12-01 | Port Neches |  |  | 138 |  | Install reactor on Sabine Bay Line 516 | Planned | 5442868 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 4358791 | 24.87% | Schedule | 0
A in MTEP15 | South | Entergy-TX | 7947 | 2015-12-28 | 21599 | 2017-06-22 | IND | 2017-12-01 | Sabine |  |  | 138 |  | Install Reactor at Sabine on the Port Neches bay | Planned | 5484740 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 4363775 | 25.69% | Scope | 0
A in MTEP15 | South | Entergy-TX | 8582 | 2015-12-28 | 20687 | 2016-12-22 | SVC | 2016-11-10 | Alden |  |  | 138 |  | Add a 200 MVAR SVC at the existing Alden 138 kV substation. | M5_In Service | 31754451 |  |  | TX |  |  | +200/-100 MVAR |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-03 | Under Construction | 31593000 | 0.511% | Design and Scoping | 1
A in MTEP15 | South | Entergy-TX | 8583 | 2015-12-28 | 20688 | 2017-03-23 | CAP | 2016-12-03 | Oakridge |  |  | 138 |  | Add a 25.1 MVAR Capacitor bank to the Oakridge 138 kV bus. | M5_In Service |  |  |  | TX |  |  | 25.1 | 25.1 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-03 | Planned | 912000 | -100% |  | 2
A in MTEP15 | South | Entergy-TX | 9241 | 2015-12-28 | 20856 | 2017-03-23 | SUB | 2017-02-21 | Deer Lake | Fish Creek | 1 | 138 |  | New 138 kV substation between Fish Creek and Spring Branch on line number 96. | M5_In Service | 675465 | Planning |  | TX |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 675157 | 0.04562% | Customer | 2
A in MTEP15 | South | Entergy-TX | 9242 | 2015-12-28 | 20855 | 2016-12-22 | SUB | 2016-12-14 | Wildcat | Nitro | 1 | 69 |  | New 69 kV substation between South Beaumont and Nitro on line 98. | M5_In Service | 5150892 |  |  | TX |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-11-01 | Under Construction | 5159000 | -0.1572% |  | 1
A in MTEP15 | South | Entergy-TX | 9280 | 2015-12-28 | 20858 | 2017-06-22 | TX | 2020-06-01 | Cypress 500 | Cypress 138 | 2 | 500 | 138 | 2nd Cypress 500/138 kV Auto. | Planned | 13121159 |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 14392680 | -8.834% | Schedule | 0
A in MTEP15 | South | Entergy-TX | 9281 | 2015-12-28 | 20859 | 2017-06-22 | LNrb | 2018-06-01 | Cleveland | Tarkington | 1 | 138 |  | Reconductor 9.3 miles and upgrade all related equipment. | Planned | 9266490 |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-08-31 | Planned | 9451175 | -1.954% | Scoping and Design | -2
A in MTEP15 | South | Entergy-TX | 9282 | 2015-12-28 | 20860 | 2017-06-22 | LNrc | 2017-11-01 | South Beaumont | Carroll St | 1 | 138 |  | Reconductor 3.3 miles and upgrade all related equipment | Planned | 3158633 |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1636587 | 93% | Scoping | 5
A in MTEP15 | South | Entergy-TX | 9283 | 2015-12-28 | 20861 | 2017-06-22 | LNrc | 2017-11-01 | South Beaumont | Carroll St | 2 | 138 |  | Reconductor 3.3 miles and upgrade all related equipment. | Planned | 3030778 |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 1767746 | 71.45% | Scoping and Design | 5
A in MTEP15 | South | Entergy-TX | 9460 | 2015-12-28 | 20909 | 2017-06-22 | TX | 2017-11-01 | South Beaumont 138 | South Beaumont 69 | 1 | 138 | 69 | Upgrade Transformer to 200 MVA | Under Construction | 17260017 |  |  | TX |  |  | 200 | 200 | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-11-01 | Planned | 16559809 | 4.228% | Scoping and Design | 0
A in MTEP15 | South | Entergy-TX | 9460 | 2015-12-28 | 20910 | 2017-06-22 | TX | 2017-11-01 | South Beaumont 138 | South Beaumont 69 | 2 | 138 | 69 | Upgrade Auto to 200 MVA | Under Construction |  |  |  | TX |  |  | 200 | 200 | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2017-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-TX | 9460 | 2015-12-28 | 20911 | 2017-06-22 | BUS | 2017-11-01 | South Beaumont 138 |  |  | 138 |  | Reconfigure station | Under Construction |  |  |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-TX | 9482 | 2015-12-28 | 20916 | 2017-06-26 | LN | 2019-06-01 | China 230 | Stowell 230 | 1 | 230 |  | New 230 kV line from China to Stowell | Planned | 58683795 | Planning |  | TX |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 57300000 | 2.415% | Combine with 20917 | 0
A in MTEP15 | South | Entergy-TX | 9482 | 2015-12-28 | 20917 | 2016-03-30 | TX | 2019-06-01 | Stowell 230 | Stowell 138 | 1 | 230 | 138 | 230/138 kV Auto Transformer | Planned |  | Planning |  | TX |  |  | 400 | 400 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-TX | 10487 | 2016-01-06 | 21596 | 2017-06-26 | TX | 2020-06-01 | Grimes 345 | Grimes 230 | 2 | 345 | 230 | Install 2nd 345/230 Auto | Planned | 102930932 | Planning |  | TX |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 121920000 | -15.58% | Schedule | 0
A in MTEP15 | South | Entergy-TX | 10487 | 2016-01-06 | 21597 | 2015-12-17 | LN | 2020-06-01 | Grimes | Lewis Creek | 1 | 230 |  | New 230 kV line from Grimes to Lewis Creek | Planned |  |  |  | TX |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | South | Entergy-TX | 10487 | 2016-01-06 | 21598 | 2017-06-22 | LNrc | 2019-06-01 | Newton Bulk | Leach | 1 | 138 |  | Rebuild Newton Bulk to Leach 138 kV line | Planned | 24340673 | Planning |  | TX |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 33900000 | -28.2% | Schedule | 0
A in MTEP15 | South | ETEC | 8208 | 2015-12-28 | 20596 | 2016-01-12 | LN | 2017-12-31 | TBD | TBD |  | 138 |  | Cut into Tarkington-Long John 138 kV line and extend line to Luce Bayou substation. | Planned | 10800000 |  |  | TX |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 10800000 | 0% |  | 0
A in MTEP15 | South | ETEC | 8208 | 2015-12-28 | 20597 | 2016-01-12 | SUB | 2017-12-31 | TBD |  |  | 138 |  | Install new Luce Bayou 138 kV in-and-out substation. | Planned | 5500000 |  |  | TX |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 5500000 | 0% |  | 0
A in MTEP15 | West | GRE | 3782 | 2015-12-28 | 7085 | 2016-12-29 | LN | 2016-11-01 | Long Lake | Mantrap | 1 | 115 |  | 115 kV line | M5_In Service | 4463269.15 | Planning |  | MN | 0.33 | 6.25 | 142 | 142 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-10-27 | Planned | 4463269.15 | 0% |  | 1
A in MTEP15 | West | GRE | 4377 | 2015-12-28 | 8889 | 2016-12-29 | CB | 2016-11-01 | Yankee Doodle North | Yankee Doodle South | 1 | 115 |  | Install bus tie breaker to allow closure of normally open point | M5_In Service | 891673.78 | Planning |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-11-03 | Planned | 891673.78 | 0% | Engineering estimate | 0
A in MTEP15 | West | GRE | 7894 | 2015-12-28 | 20131 | 2016-04-14 | LN | 2017-10-02 | Stockade |  | 1 | 115 | 115 | GRE proposes to tap the GRE-owned Wakefield ? Big Swan 115 kV line and build a new, ~6 mile, 115 kV transmission to the proposed pumping station. | Planned | 3812779 | Planning Preliminary |  | MN |  | 6 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-10-02 | Planned | 3812779 | 0% | Engineering estimate | 0
A in MTEP15 | West | GRE | 7899 | 2015-12-28 | 20136 | 2016-09-15 | LN | 2017-10-19 | Cedar Lake Pumping Station |  | 1 | 115 | 115 | Install a transmission line to connect to MVEC?s Cedar Lake pump station sub. Line to be built to 115kV specs but initially energized at 115kV. Line length is undetermined at this point. 6 miles are assumed. | Planned | 4989151.97 | Planning Preliminary |  | MN |  | 6 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-10-19 | Planned | 4989151.97 | 0% |  | 0
A in MTEP15 | West | GRE | 7912 | 2015-12-28 | 20152 | 2016-09-15 | LNrb | 2021-05-01 | Bass Lake | Lawndale | 1 | 115 | 115 | Construct two miles of 115 kV line with 795 ACSS conductor from the 3 way switch to the high side structure of new Wright Hennepin Electric Cooperative?s Lawndale #2 distribution substation. | Planned | 2000000 | Planning Preliminary |  | MN | 2 |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 2000000 | 0% |  | 0
A in MTEP15 | Central | HE | 10343 | 2015-12-28 | 21569 | 2015-11-16 | SUB | 2016-06-01 | Hubbell |  |  | 138 |  | Construct a 138kV ring bus and add a second 138/69kV transformer | Planned | 10047000 |  |  | IN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 10047000 | 0% |  | 0
A in MTEP15 | Central | IPL | 4262 | 2015-12-28 | 8040 | 2017-01-12 | LNup | 2016-12-31 | Pritchard | Centerton-Honey Creek-Southport | 1 | 138 |  | Increase line rating from 242 to 302 MVA | M5_In Service |  | Planning | 2012 | IN | 21.6 |  | 302 | 302 | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 4263 | 2015-12-28 | 8041 | 2017-01-12 | LNup | 2016-12-31 | Pritchard | Heartland Crossing-Mooresville | 1 | 138 |  | Increase line rating from 191 to 242 MVA | M5_In Service |  | Planning | 2012 | IN | 15.8 |  | 242 | 242 | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 4264 | 2015-12-28 | 8042 | 2017-01-12 | LN | 2016-12-31 | Pritchard | Franklin Township | 1 | 138 |  | New 138 kV transmission line rated 322 MVA on spare position of existing double circuit tower line | M5_In Service |  | Planning | 2012 | IN | 23 |  | 322 | 322 | GIP |  |  | N | N | Y | Externally Driven | A | 2016-12-31 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 7701 | 2015-12-28 | 20063 | 2017-01-12 | CB | 2016-06-01 | Thompson | Breakers |  | 138 |  | Two new breakers | M5_In Service |  |  |  | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 7704 | 2015-12-28 | 20065 | 2017-01-12 | CB | 0 | Rockville | Breaker |  | 345 |  | New breaker | Planned |  |  |  | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 0 | Planned | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 7704 | 2015-12-28 | 20066 | 2017-01-12 | CB | 0 | Rockville | Breaker |  | 138 |  | New breaker | Planned |  |  |  | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 0 | Planned | 0 | 0% |  | 0
A in MTEP15 | Central | IPL | 9402 | 2015-12-28 | 20892 | 2015-07-27 | LNup | 2017-07-15 | Guion | Westlane | 40 | 138 |  | Increase line rating to 298 MVA by increased clearance. | Planned |  |  |  | IN | 2.2 |  | 298 |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-07-15 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8042 | 2015-12-28 | 20325 | 2015-01-23 | LN | 2016-12-31 | Burlington South |  |  | 69 |  | ITC will build new 69kV line taps for the new Burlington South Alliant Energy distribution sub. | Planned | 60000 | Engineering |  | IA |  |  |  |  | Other |  | Relaying | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 60000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8043 | 2015-12-28 | 20326 | 2017-02-24 | LN | 2017-12-31 | Blanket for Customer Interconnections under $1 million for 2017 | Throughout system |  | 345 | 69 | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | Under Construction | 2400000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 2400000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8043 | 2015-12-28 | 20327 | 2014-12-02 | LN | 2018-12-31 | Blanket for Customer Interconnections under $1 million for 2018 | Throughout system |  | 345 | 69 | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | Planned | 2400000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 2400000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8048 | 2015-12-28 | 20337 | 2017-06-29 | SUB | 2016-12-31 | Cntrl Enclosure Blanket for 2016 | Throughout system |  | 345 | 69 | Replace control enclosures due to age & condition | M5_In Service | 1860000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 1860000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8049 | 2015-12-28 | 20341 | 2017-06-29 | SUB | 2016-12-31 | NERC Com Mitigation for 2016 | Throughout system |  | 345 | 69 | New proposed NERC Reliability Standards will also impact the need to upgrade substations equipment to meet the standards. NERC Reliability Standards continue to evolve and issues like relay encroachment/loadability, scheme redundancy, protective relay testing, fault recording and stability analysis upgrades continually are being identified. | M5_In Service | 180000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 180000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8051 | 2015-12-28 | 20346 | 2017-06-29 | SUB | 2016-12-31 | Normal & Emergeny Retirement Unit Change-out for 2016 | Throughout system |  | 345 | 69 | The need for replacing miscellaneous aged, broken, or failed equipment in the field ? primarily in substations. Equipment replacements identified from maintenance inspections, such as batteries, field capacitors, control building HVAC units, transformer t | M5_In Service | 9000000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 9000000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8053 | 2015-12-28 | 20387 | 2017-06-29 | LN | 2016-12-31 | Poor Performing Circuits for 2016 | Throughout system |  | 69 | 34 | Rebuild poor performing circuits that have been identified as a system reliability issue | M5_In Service | 4800000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 4800000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8057 | 2015-12-28 | 20358 | 2017-06-29 | SUB | 2016-12-31 | SCADA Blanket for 2016 | Throughout system |  | 345 | 69 | Perform SCADA upgrades | M5_In Service | 360000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | SCADA | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 360000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8058 | 2015-12-28 | 20362 | 2017-06-29 | LN | 2016-12-31 | Signage Blanket for 2016 | Throughout system |  | 345 | 69 | Add pole signage to transmission towers and poles that are not currently numbered to aid field personnel in troubleshooting activities and performing scheduled inspections and maintenance. | M5_In Service | 1200000 | Engineering | 2014 | IA,MN,IL |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 1200000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8074 | 2015-12-28 | 20398 | 2015-01-20 | CAP | 2017-06-30 | Fairfax | Capacitor |  | 161 |  | Add a 42 MVAR 161 kV capacitor bank and new breaker at Fairfax substation. | Planned | 1687896 | Engineering | 2014 | IA |  |  | 42 MVAR |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-30 | Planned | 1687896 | 0% |  | 0
A in MTEP15 | East | ITCM | 8086 | 2015-12-28 | 20409 | 2015-12-29 | CAP | 2016-02-29 | Radio | Capacitor |  | 69 |  | Add a 13.2MVAR 69kV capacitor bank | Under Construction | 524804 | Engineering | 2014 | IA |  |  | 13.2 MVAR |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-02-29 | Under Construction | 524804 | 0% |  | 0
A in MTEP15 | East | ITCM | 8088 | 2015-12-28 | 20412 | 2015-01-20 | CAP | 2018-12-31 | Hiawatha | Capacitor |  | 161 |  | Move the 115kV cap bank and change the size to a 42MVAR 161kV cap bank at Hiawatha. | Planned | 193795.2 | Engineering | 2014 | IA |  |  | 42 MVAR |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 193795.2 | 0% |  | 0
A in MTEP15 | East | ITCM | 8093 | 2015-12-28 | 20420 | 2016-12-22 | TX | 2016-12-01 | PCI | Transformer | 2 | 161 | 69 | Add a 200 MVA 161/69 kV transformer at Prairie Creek Industrial substation. | M5_In Service | 3617594 | Engineering | 2014 | IA |  |  | 200 | 200 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 3617594 | 0% |  | 0
A in MTEP15 | East | ITCM | 8106 | 2015-12-28 | 20437 | 2017-06-30 | CAP | 2022-12-31 | Heron Lake | Capacitor |  | 161 |  | Install two 21MVAR 161kV cap banks | Planned | 0 | Engineering | 2014 | MN |  |  | 42 MVAR | 42 MVAR | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 36
A in MTEP15 | East | ITCM | 8106 | 2015-12-28 | 20440 | 2017-06-30 | SUB | 2022-12-31 | Heron Lake | Substation |  | 161 | 69 | Rebuild the Heron Lake 161kV to a ring bus (convertable to bkr and 1/2) | Planned | 16929252 | Engineering | 2014 | MN |  |  |  |  | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 16929252 | 0% |  | 36
A in MTEP15 | East | ITCM | 8125 | 2015-12-28 | 20478 | 2016-06-28 | LN | 2017-12-31 | Anita | Thompson | 1 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 11159322 | Engineering | 2014 | IA | 17.6 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 11159322 | 0% |  | 0
A in MTEP15 | East | ITCM | 8128 | 2015-12-28 | 20490 | 2015-01-21 | LN | 2017-12-31 | Redfield | Panora REC Tap | 1 | 69 |  | Build new 69 kV line (operate at 34kV until 69kV/dist subs are ready) | Planned | 8852758.8 | Engineering | 2014 | IA | 10 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 8852758.8 | 0% |  | 0
A in MTEP15 | East | ITCM | 8128 | 2015-12-28 | 20502 | 2016-06-28 | LN | 2019-12-31 | Bagley | Perry | 1 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 11841000 | Engineering | 2014 | IA | 19 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 11841000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8129 | 2015-12-28 | 20511 | 2015-01-21 | LN | 2018-12-31 | Jefferson WCC | Scranton Distribution | 1 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 11837228.4 | Engineering | 2014 | IA | 14.5 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 11837228.4 | 0% |  | 0
A in MTEP15 | East | ITCM | 8132 | 2015-12-28 | 20516 | 2015-01-21 | LN | 2019-12-31 | Bagley Jct | Scranton | 1 | 69 |  | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 8104200 | Engineering | 2014 | IA | 16 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 8104200 | 0% |  | 0
A in MTEP15 | East | ITCM | 8150 | 2015-12-28 | 20534 | 2015-01-20 | SUB | 2025-12-31 | Belle Plaine | Substation |  | 161 | 69 | Add four 69kV breakers that are needed at Belle Plaine and add a 100MVA 161/69kV transformer. | Planned | 4891935.6 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 4891935.6 | 0% |  | 0
A in MTEP15 | East | ITCM | 8150 | 2015-12-28 | 20535 | 2014-09-15 | TX | 2025-12-31 | Belle Plaine | Transformer |  | 161 | 69 | Add a 161/69kV 100MVA transformer at Belle Plaine | Planned | 0 | Planning Preliminary |  | IA |  |  | 100 MVA | 100 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8150 | 2015-12-28 | 20536 | 2015-01-20 | SwSta | 2025-12-31 | Belle Plaine South (River Valley) | Switch Station |  | 69 | 69 | Belle Plaine South (now named River Valley) Three (3) Terminal 69kV Switch Station | Planned | 3043446 | Engineering | 2014 | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 3043446 | 0% |  | 0
A in MTEP15 | East | ITCM | 8150 | 2015-12-28 | 20537 | 2015-01-20 | SwSta | 2025-12-31 | Haven | Switch Station |  | 69 | 69 | Haven Three (3) Terminal 69kV Switch Station | Planned | 3043446 | Engineering | 2014 | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 3043446 | 0% |  | 0
A in MTEP15 | East | ITCM | 8150 | 2015-12-28 | 20724 | 2015-01-20 | SUB | 2025-12-31 | 34.5kV substation retirements |  |  | 34.5 |  | Retire the 34.5kV substation equipment that is no longer needed. | Planned | 600000 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 600000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8151 | 2015-12-28 | 20538 | 2015-01-21 | SUB | 2025-12-31 | Vinton | Substation |  | 69 |  | Two additional 69kV breakers are needed at the Vinton substation. | Planned | 1164487.2 | Engineering | 2014 | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 1164487.2 | 0% |  | 0
A in MTEP15 | East | ITCM | 8151 | 2015-12-28 | 20539 | 2015-01-21 | SUB | 2025-12-31 | Traer | Substation |  | 69 |  | One additional 69kV breaker is needed at the Traer substation. | Planned | 768123.6 | Engineering | 2014 | IA |  |  | 143 MVA | 143 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 768123.6 | 0% |  | 0
A in MTEP15 | East | ITCM | 8152 | 2015-12-28 | 20542 | 2015-01-21 | SUB | 2025-12-31 | Parnell | Substation |  | 161 | 69 | Three 69kV breakers are needed at the Parnell Substation. | Planned | 3812623.2 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 3812623.2 | 0% |  | 0
A in MTEP15 | East | ITCM | 8152 | 2015-12-28 | 20543 | 2014-09-15 | TX | 2025-12-31 | Parnell | Transformer | 1 | 161 | 69 | A new 161/69kV 100MVA transformer is needed at the Parnell Substation. | Planned | 0 | Planning Preliminary |  | IA |  |  | 100 MVA | 100 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8153 | 2015-12-28 | 20544 | 2015-01-21 | SwSta | 2025-12-31 | Keswick | Switch Station |  | 69 |  | Add a Keswick 3 terminal switch station | Planned | 2931082.8 | Engineering | 2014 | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 2931082.8 | 0% |  | 0
A in MTEP15 | East | ITCM | 8154 | 2015-12-28 | 20545 | 2014-12-02 | SUB | 2025-12-31 | Fairfax | Substation |  | 69 |  | Two 69kV breakers are needed at the Fairfax Substation. | Planned | 1278863 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 1278863 | 0% |  | 0
A in MTEP15 | East | ITCM | 8154 | 2015-12-28 | 20546 | 2014-12-02 | SUB | 2025-12-31 | Marengo | Substation |  | 69 |  | Four 69kV breakers need to be installed at the Marengo Substation. | Planned | 4198943 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 4198943 | 0% |  | 0
A in MTEP15 | East | ITCM | 8154 | 2015-12-28 | 20727 | 2015-01-21 | SUB | 2025-12-31 | various 34.5 kV subs |  |  | 34.5 |  | retire 34.5kV subs | Planned | 180000 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 180000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8154 | 2015-12-28 | 20728 | 2015-01-21 | LN | 2025-12-31 | various 34.5kV | various 34.5kV |  | 34.5 |  | retire 34.5kV lines that are no longer needed | Planned | 974404.8 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 974404.8 | 0% |  | 0
A in MTEP15 | East | ITCM | 8155 | 2015-12-28 | 20547 | 2015-01-21 | SUB | 2025-12-31 | Fletcher | Substation |  | 69 |  | One (1) 69kV Terminal at Fletcher Substation | Planned | 367443.6 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 367443.6 | 0% |  | 0
A in MTEP15 | East | ITCM | 8155 | 2015-12-28 | 20548 | 2015-01-21 | SwSta | 2025-12-31 | Tama Paper | Switch Station |  | 69 |  | Three 69kV line breakers and one 69kV bus tie breaker are needed at the Tama Breaker Substation. | Planned | 2817202.8 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 2817202.8 | 0% |  | 0
A in MTEP15 | East | ITCM | 8155 | 2015-12-28 | 20549 | 2015-01-21 | SwSta | 2025-12-31 | Laurel | Switch Station |  | 69 |  | Three 69kV breakers and one 69kV bus tie breaker are needed at the Laurel switch station. | Planned | 2817202.8 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 2817202.8 | 0% |  | 0
A in MTEP15 | East | ITCM | 8155 | 2015-12-28 | 20726 | 2015-01-21 | LN | 2025-12-31 | new switch stations |  |  | 69 |  | Perform the 69kV line work for new switch stations for the conversion. | Planned | 600060 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2025-12-31 | Planned | 600060 | 0% |  | 0
A in MTEP15 | East | ITCM | 8157 | 2015-12-28 | 20551 | 2014-09-15 | SUB | 2015-12-31 | Marshalltown | Substation |  | 161 |  | Three new terminals are needed at the Marshalltown substation to accommodate interconnection to the generating facilities 3 GSUs. | Planned | 3850000 | Engineering | 2014 | IA |  |  | 558 MVA | 558 MVA | GIP |  |  | N | N | Y | Externally Driven | A | 2015-12-31 | Planned | 3850000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8158 | 2015-12-28 | 20552 | 2016-06-30 | SwSta | 2017-03-31 | DAEC | Switch Station |  | 69 |  | Construct a new three (3) terminal, three (3) breaker 69 kV switch station northwest of the city of Palo, Iowa in order to eliminate the coordination and system protection issues. The existing Vinton ? DAEC ? Hiawatha 69 kV transmission lines will need to be tapped and re-routed into the new substation. | Planned | 3062831 | Engineering | 2014 | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-03-31 | Planned | 3062831 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20554 | 2016-06-29 | SwSta | 2021-05-01 | Morgan Valley | Switch Station |  | 345 | 345 | Add a new Morgan Valley 345kV three terminal switch station on the Duane Arnold-Tiffin 345kV line. | Planned | 0 | Engineering | 2014 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20555 | 2016-06-29 | LN | 2021-05-01 | Morgan Valley | New Beverly 345/161kV | 1 | 345 |  | Add a new 6.5 mile 345 kV line from the new Morgan Valley Switchstation to a new 345/161 kV substation adjacent to the existing Beverly 161/69/34.5 kV substation. | Planned | 23292051.6 | Engineering | 2014 | IA |  | 6.5 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 23292051.6 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20557 | 2016-06-29 | SUB | 2021-05-01 | New Beverly 345/161 kV | Substation |  | 345 | 161 | Add a new Beverly 345/161kV substation adjacent to the existing Beverly 161kV sub. | Planned | 0 | Planning Preliminary |  | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20558 | 2016-06-29 | TX | 2021-05-01 | New Beverly 345/161kV | Substation | 1 | 345 | 161 | New Beverly 345/161kV 450MVA autotransformer | Planned | 0 | Planning Preliminary |  | IA |  |  | 450 MVA | 450 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20559 | 2016-06-29 | SUB | 2021-05-01 | Beverly | Substation |  | 345 | 161 | Add a new Beverly 345/161kV substation adjacent to the existing Beverly 161kV sub. Add a 161kV terminal at the existing Beverly sub to tie to the low side (161kV) of the new 345/161kV substation. | Planned | 14864540.4 | Engineering | 2014 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2021-05-01 | Planned | 14864540.4 | 0% |  | 0
A in MTEP15 | East | ITCM | 8160 | 2015-12-28 | 20737 | 2016-06-29 | CAP | 2021-05-01 | Beverly | Capacitor |  | 69 |  | Add a 33 MVAR cap on the Beverly 69kV bus | Planned |  | Engineering |  | IA |  |  | 33 MVAR | 33 MVAR | BaseRel |  |  | N | N | NT | Bottom-Up | A | 2021-05-01 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8161 | 2015-12-28 | 20562 | 2014-12-02 | LN | 2016-12-31 | Ames Mine | Ames NADC | 1 | 69 |  | Buiid Ames Mine NADC 69lV | Planned | 2004000 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 2004000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8162 | 2015-12-28 | 20563 | 2015-08-28 | LNcnv | 2017-12-31 | Ames Mine | New Ames 69kV Substation | 1 | 69 |  | Converrt the line from Ames Mine to the new Ames 69kV Substation to 69kV operation. | Planned | 0 | Planning Preliminary |  | IA | 1.9 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8164 | 2015-12-28 | 20565 | 2015-01-21 | SwSta | 2017-12-31 | new Ames | Substation |  | 69 |  | Construct a new 4 terminal switch station | Planned | 6255831.6 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 6255831.6 | 0% |  | 0
A in MTEP15 | East | ITCM | 8164 | 2015-12-28 | 20566 | 2015-08-28 | LNcnv | 2017-12-31 | new Ames Substation | Barilla | 1 | 69 |  | Convert the line from the new Ames Substation to Barilla to 69kV operation. Ames Ckt 4930 - reterminate Ames tap. | Planned | 705000 | Engineering | 2014 | IA | 5.1 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 705000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8164 | 2015-12-28 | 20725 | 2015-01-21 | LN | 2017-12-31 | Boone Jct | Barilla | 1 | 34.5 |  | Retire 0.4 miles | Planned | 132000 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 132000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8166 | 2015-12-28 | 20568 | 2016-11-08 | SUB | 2017-07-01 | Hiawatha | Substation |  | 69 |  | Add a 69kV terminal at the Hiawatha sub | Planned | 554400 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-08-05 | Under Construction | 554400 | 0% |  | 11
A in MTEP15 | East | ITCM | 8166 | 2015-12-28 | 20569 | 2016-11-08 | SUB | 2017-07-01 | Vinton | Substation |  | 69 |  | Add a 69kV terminal at Vinton | Planned | 554400 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-08-05 | Under Construction | 554400 | 0% |  | 11
A in MTEP15 | East | ITCM | 8167 | 2015-12-28 | 20570 | 2016-11-08 | SUB | 2016-07-05 | Doud | Substation |  | 161 | 69 | The existing 69 kV terminals at Boone Jct will be re-terminated to breaker positions at Doud. A 161/69 kV transformer will be installed at Doud, and the existing 161/69 kV transformer at Boone Jct. will be removed. | M5_In Service | 5496000 | Engineering | 2014 | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-07-19 | Under Construction | 5496000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8167 | 2015-12-28 | 20571 | 2016-11-08 | TX | 2016-07-05 | Doud | Transformer | 1 | 161 | 69 | Add a Doud 161/69kV transformer | M5_In Service | 0 | Engineering | 2014 | IA |  |  | 100 MVA | 100 MVA | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-07-19 | Under Construction | 0 | 0% |  | 0
A in MTEP15 | East | ITCM | 8167 | 2015-12-28 | 20572 | 2016-11-08 | LN | 2016-07-05 | Doud | Squaw Valley REC | 1 | 69 |  | Convert the line from Doud to Squaw Valley REC to 69kV operation. | M5_In Service | 633000 | Engineering | 2014 | IA | 8.6 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-07-19 | Under Construction | 633000 | 0% |  | 0
A in MTEP15 | East | ITCM | 8168 | 2015-12-28 | 20573 | 2015-12-30 | LN | 2017-03-31 | Squaw Valley REC | Ames Transmission |  | 69 |  | Convet the line to 69kV operation | Planned | 1380600 | Engineering | 2014 | IA | 6.5 |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-03-31 | Planned | 1380600 | 0% |  | 0
A in MTEP15 | East | ITCT | 7891 | 2017-06-27 | 20322 | 2017-06-27 | LNug | 2017-08-01 | Cato | Stone Pool | 1 | 120 |  | New 120 kV underground cable to loop in Stone Pool Substation | Under Construction | 6047000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | Under Construction | 6047000 | 0% |  | 3
A in MTEP15 | East | ITCT | 7891 | 2017-06-27 | 20323 | 2017-06-27 | LNug | 2017-08-01 | Midtown | Stone Pool | 1 | 120 |  | New 120 kV underground cable to loop in Stone Pool. | Under Construction | 6047000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | Under Construction | 6047000 | 0% |  | 3
A in MTEP15 | East | ITCT | 7891 | 2017-06-27 | 20324 | 2017-06-27 | TAP | 2017-08-01 | Stone Pool |  |  | 120 |  | New Stone Pool Substation | Under Construction | 4323000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | M4_Pre-Construction | 4323000 | 0% |  | 3
A in MTEP15 | East | ITCT | 7891 | 2017-06-27 | 20454 | 2017-06-27 | RLY | 2017-08-01 | Cato |  |  | 120 |  | Relay upgrades at Cato | Under Construction | 54000 |  | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | M4_Pre-Construction | 54000 | 0% |  | 3
A in MTEP15 | East | ITCT | 7891 | 2017-06-27 | 20455 | 2017-06-27 | RLY | 2017-08-01 | Midtown |  |  | 120 |  | Relay Upgrades at Midtown | Under Construction | 54000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | M4_Pre-Construction | 54000 | 0% |  | 3
A in MTEP15 | East | ITCT | 7892 | 2016-03-22 | 20319 | 2016-03-22 | LN | 2019-06-13 | Hood | Bartlett |  | 120 |  | New 120 kV transmission line to loop in Bartlett. | M2a_Pre-Project Approval | 2490000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-13 | M2a_Pre-Project Approval | 2490000 | 0% |  | 0
A in MTEP15 | East | ITCT | 7892 | 2016-03-22 | 20320 | 2016-03-22 | LN | 2019-06-13 | Bloomfield | Bartlett | 1 | 120 |  | New 120 kV transmission line to loop in Bartlett Substation | M2a_Pre-Project Approval | 2490000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-13 | M2a_Pre-Project Approval | 2490000 | 0% |  | 0
A in MTEP15 | East | ITCT | 7892 | 2016-03-22 | 20321 | 2016-03-22 | TAP | 2019-06-13 | Bartlett |  |  | 120 |  | New distribution substation | M2a_Pre-Project Approval | 2910000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-13 | M2a_Pre-Project Approval | 2910000 | 0% | Refined Engineering Estimate. | 0
A in MTEP15 | East | ITCT | 7892 | 2016-03-22 | 20844 | 2016-03-22 | RLY | 2019-06-13 | Hood |  |  | 120 |  | Relay Upgrades at Hood Substation | M2a_Pre-Project Approval | 15000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-13 | M2a_Pre-Project Approval | 15000 | 0% |  | 0
A in MTEP15 | East | ITCT | 7892 | 2016-03-22 | 20845 | 2016-03-22 | RLY | 2019-06-13 | Bloomfield |  |  | 120 |  | Relay Upgrades at Bloomfield | M2a_Pre-Project Approval | 15000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-13 | M2a_Pre-Project Approval | 15000 | 0% |  | 0
A in MTEP15 | East | ITCT | 8083 | 2017-06-27 | 20408 | 2017-06-27 | RLY | 2017-12-01 | Cortland |  |  | 120 |  | Upgrade limiting relay at Cortland. | M3_Long Lead Materials | 300000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 300000 | 0% |  | 6
A in MTEP15 | East | ITCT | 8087 | 2017-03-29 | 20411 | 2017-03-29 | CAP | 2021-12-31 | Stratford |  |  | 120 |  | 33.3 MVAR capacitor bank at Stratford 120 kV station. | M2a_Pre-Project Approval | 820000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 820000 | 0% |  | 42
A in MTEP15 | East | ITCT | 8094 | 2015-12-28 | 20422 | 2016-12-20 | TX | 2018-06-01 | Fitz |  | 301 | 345 | 120 | Add a 345/120 kV transformer at Fitz Substation | M3_Long Lead Materials | 5500000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 5500000 | 0% |  | 0
A in MTEP15 | East | ITCT | 8094 | 2015-12-28 | 20426 | 2016-12-20 | LN | 2018-06-01 | Adams | Fitz | 1 | 120 |  | 120 kV line created by looping the Adams-Bunce 120 kV line into Fitz. This requires approx. 0.1 miles of new double circuit structures in new ROW utilizing 1431 ACSR Conductor. | M3_Long Lead Materials | 600000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 600000 | 0% |  | 0
A in MTEP15 | East | ITCT | 8094 | 2015-12-28 | 20427 | 2016-12-20 | LN | 2018-06-01 | Fitz | Bunce | 1 | 120 |  | 120 kV line created by looping the Adams-Bunce 120 kV line into Fitz. This requires approx. 0.1 miles of new double circuit structures in new ROW utilizing 1431 ACSR Conductor. | M3_Long Lead Materials | 600000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 600000 | 0% |  | 0
A in MTEP15 | East | ITCT | 8094 | 2015-12-28 | 20431 | 2016-12-20 | SUB | 2018-06-01 | Fitz |  |  | 345 | 120 | Install 345 and 120 kV substation equipment at Fitz to accomodate the installation of the new 345/120 kV transformer and looping the 120 kV Adams to Bunce line into Fitz. | M3_Long Lead Materials | 6500000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 6500000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9245 | 2016-07-05 | 20848 | 2016-10-11 | SUB | 2016-08-31 | Rapson |  |  | 120 |  | Add two breakers, disconnects, and relays. | M5_In Service | 1330000 | Engineering | 2015 | MI |  |  |  |  | GIP | Shared |  | Y | N | Y | Externally Driven | A | 2016-09-02 | Under Construction | 1330000 | 0% |  | -1
A in MTEP15 | East | ITCT | 9360 | 2017-05-16 | 20874 | 2017-05-16 | SUB | 2019-10-01 | Scio 120/13.2 kV |  |  | 120 | 13.2 | Install 2-120 kV line breakers and 1-120 kV section breaker w/ associated disconnects laid out in a straight bus configuration. | M3_Long Lead Materials | 2775000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 2775000 | 0% |  | 10
A in MTEP15 | East | ITCT | 9360 | 2017-05-16 | 20875 | 2017-05-16 | LN | 2019-10-01 | Lark | Scio | 1 | 120 |  | New 120 kV line created by constructing approx. 2 miles of 120 kV, double circuit structures in new ROW and looping the existing Lark-Spruce line into Scio. | M3_Long Lead Materials | 3787500 | Engineering | 2015 | MI |  | 2 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 3787500 | 0% | Added cost for the relay upgrades at the Lark and Dorset 120 kV stations. | 10
A in MTEP15 | East | ITCT | 9360 | 2017-05-16 | 20876 | 2017-05-16 | LN | 2019-10-01 | Scio | Spruce | 1 | 120 |  | New 120 kV line created by constructing approx. 2 miles of 120 kV, double circuit structures in new ROW and looping the existing Lark-Spruce line into Scio. | M3_Long Lead Materials | 3787500 | Engineering | 2015 | MI |  | 2 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 3787500 | 0% | Added cost for the relay upgrades at the Lark and Dorset 120 kV stations. | 10
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20880 | 2016-12-20 | SUB | 2018-12-31 | Apex (formerly “Blue”) 120/41.6 kV |  |  | 120 | 41.6 | Install 3-120 kV breakers w/ associated disconnects in a straight bus configuration, a control house, and all other 120 kV equipment owned by ITCT at Apex (formerly “Blue”) substation. | M3_Long Lead Materials | 2600000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 2600000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20881 | 2017-03-29 | SUB | 2019-05-01 | State 120/41.6 kV |  |  | 120 | 41.6 | Install 3-120 kV breakers w/ associated dsconnects in a straight bus configuration, a control house, and all other 120 kV equipment owned by ITCT at State (formerly "Maize") substation. | M2a_Pre-Project Approval | 2420000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-05-01 | M2a_Pre-Project Approval | 2420000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20882 | 2017-03-29 | SUB | 2019-05-01 | Pioneer 120/41.6 kV |  |  | 120 | 41.6 | Install 2-120 kV line breakers at ITC's existing Pioneer substation | M2a_Pre-Project Approval | 1428000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-05-01 | M2a_Pre-Project Approval | 1428000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20883 | 2016-08-11 | SUB | 2018-12-31 | Phoenix 120/41.6 kV |  |  | 120 | 41.6 | Install 2-120 kV line breakers and 1-120 kV section breaker at ITC's existing Phoenix substation. Also reterminate the Phoenix end of the Lark-Phoenix circuit to a different bus inside of Phoenix | M2a_Pre-Project Approval | 2492000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 2492000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20884 | 2017-03-29 | LN | 2019-05-01 | Pioneer | State | 1 | 120 |  | Construct 2.7 miles of new double circuit structures and string 954 ACSR on both sides between Pioneer and State (formerly "Maize") to create the State (formerly "Maize") - Pioneer #1 and #2 lines. | M2a_Pre-Project Approval | 5252000 | Engineering | 2015 | MI |  | 2.7 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-05-01 | M2a_Pre-Project Approval | 5252000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20885 | 2017-03-29 | LN | 2019-05-01 | Pioneer | State | 2 | 120 |  | Construct 2.7 miles of new double circuit structures and string 954 ACSR on both sides between Pioneer and State (formerly "Maize")to create the State (formerly "Maize") - Pioneer #1 and #2 lines. | M2a_Pre-Project Approval | 5252000 | Engineering | 2015 | MI |  | 2.7 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-05-01 | M2a_Pre-Project Approval | 5252000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20886 | 2016-12-20 | LNug | 2018-12-31 | Phoenix | Apex (formerly “Blue”) | 1 | 120 |  | Construct a 2.6 mile underground line using 2500 XLPE cable between Phoenix and Apex (formerly “Blue”) to create the Apex-Phoenix #1 line. | M3_Long Lead Materials | 39060000 | Engineering | 2015 | MI |  | 2.6 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 39060000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 20887 | 2016-12-20 | LNug | 2018-12-31 | Phoenix | Apex (formerly “Blue”) | 2 | 120 |  | Construct a 2.6 mile underground line using 2500 XLPE cable between Phoenix and Apex (formerly “Blue”) to create the Apex-Phoenix #2 line. | M3_Long Lead Materials | 39060000 | Engineering | 2015 | MI |  | 2.6 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 39060000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9362 | 2017-03-29 | 21449 | 2016-08-11 | SUBmisc | 2018-12-31 | Lark 120 kV |  |  | 120 |  | Upgrade relaying associated with position HI at Lark | M3_Long Lead Materials | 309000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 309000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9440 | 2017-03-29 | 20901 | 2016-12-20 | LNrl | 2016-11-11 | Waterman | Cato | 1 | 120 |  | Relocate a portion of the underground circuit exiting Waterman station | M5_In Service | 8500000 | Engineering Preliminary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Under Construction | 8500000 | 0% |  | -13
A in MTEP15 | East | ITCT | 9440 | 2017-03-29 | 20902 | 2017-03-29 | LNrl | 2017-12-31 | Waterman | Frisbie | 1 | 120 |  | Relocate portion of the undergound circuit exiting Waterman station | Under Construction | 8000000 | Engineering Preliminary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 8000000 | 0% |  | 0
A in MTEP15 | East | ITCT | 9440 | 2017-03-29 | 20903 | 2016-12-20 | LNrl | 2016-11-11 | Waterman | St. Antoine | 1 | 120 |  | Relocate a portion of the underground circuit exiting Waterman station | M5_In Service | 8500000 | Engineering Preliminary | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Under Construction | 8500000 | 0% |  | -13
A in MTEP15 | East | ITCT | 9440 | 2017-03-29 | 20904 | 2017-03-29 | LNrl | 2020-06-30 | Waterman | Zug | 1 | 120 |  | Relocate a portion of the overhead circuit exiting Waterman station | M3_Long Lead Materials | 0 | Engineering Preliminary |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 30
A in MTEP15 | East | ITCT | 9440 | 2017-03-29 | 20905 | 2017-03-29 | LNrl | 2020-06-30 | Waterman | DIG-Navarre | 1 | 230 |  | Relocate a portion of the overhead circuit exiting Waterman station | M3_Long Lead Materials | 0 | Engineering Preliminary |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 0 | M3_Long Lead Materials | 0 | 0% |  | 1445
A in MTEP15 | South | LAFA | 8820 | 2015-12-28 | 20743 | 2017-06-05 | TX | 2018-12-31 | Pont Des Mouton |  |  | 230 | 69 | 230-69 autotransformer to feed new 69kv station | Planned | 3750000 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 3750000 | 0% |  | 0
A in MTEP15 | South | LAFA | 8820 | 2015-12-28 | 20744 | 2017-06-05 | LN | 2018-12-31 | Pont Des Mouton | Northeast |  | 69 |  | New 69kv line from Pont Des Mouton to Peck stations. | Planned | 2500000 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 2500000 | 0% |  | 0
A in MTEP15 | South | LAFA | 8820 | 2015-12-28 | 20745 | 2017-06-05 | SUB | 2018-12-31 | Northeast |  |  | 69 |  | Station to alleviate distribution loading. | Planned | 4250000 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2018-12-31 | Planned | 4250000 | 0% |  | 0
A in MTEP15 | West | MEC | 8020 | 2015-12-28 | 20294 | 2016-09-16 | LN | 2019-12-01 | Pleasant Corner | Beacon | 1 | 161 |  | New 161 kV Line from Pleasant Corner to Beacon | Planned | 14500000 | Planning | 2014 | IA | 0 | 16 | 410 MVA | 410 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 14500000 | 0% |  | 0
A in MTEP15 | West | MEC | 8020 | 2015-12-28 | 20295 | 2016-09-16 | TEQ | 2019-12-01 | Beacon |  |  | 161 |  | New 161 kV Line Terminal at the Beacon Substation | Planned | 765000 | Planning | 2014 | IA |  |  | 2000A | 2000A | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-01 | Planned | 765000 | 0% |  | 0
A in MTEP15 | West | MEC | 8028 | 2016-06-30 | 20304 | 2016-07-01 | TX | 2023-06-01 | Hastings |  |  | 161 | 69 | Replace the Hastings transformer with a 125 MVA transformer. | Planned | 2000000 | Planning | 2014 | IA |  |  | 125 MVA | 125 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2023-06-01 | Planned | 2000000 | 0% |  | 0
A in MTEP15 | West | MEC | 8030 | 2015-12-28 | 20305 | 2017-06-27 | LN | 2017-11-01 | Clarksville East | Waverly West | 1 | 69 |  | New 69 kV Line from Clarksville East to Waverly West. Retire Clarksville East - Waverly Junction. | Planned | 2600000 | Planning | 2014 | IA | 0 | 3 |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 2600000 | 0% |  | 5
A in MTEP15 | West | MEC | 8035 | 2015-12-28 | 20372 | 2016-03-21 | TEQ | 2017-04-01 | Sub 78 |  |  | 161 |  | Replace limiting terminal equipment | Planned | 207000 | Planning | 2014 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 207000 | 0% |  | 0
A in MTEP15 | West | MEC | 8036 | 2015-12-28 | 20371 | 2016-03-21 | TEQ | 2017-04-01 | Sub 56 |  |  | 161 |  | Replace limiting terminal equipment. | Planned | 91000 | Planning | 2014 | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 91000 | 0% |  | 0
A in MTEP15 | West | MEC | 8037 | 2015-12-28 | 20430 | 2016-04-06 | CB | 2017-11-15 | Sub 93 |  |  | 345 |  | Replace Sub 93 345 kV circuit breakers 954 and 964 with new 3,000 Amp breakers. | Planned | 853000 | Planning | 2016 | IA |  |  | 3000A | 3000A | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-11-15 | Planned | 853000 | 0% |  | 0
A in MTEP15 | West | MEC | 8038 | 2015-12-28 | 20381 | 2016-07-01 | LNup | 2017-06-01 | Sub S | Sub G & Sub R |  | 69 |  | Replace two 69 kV line switches near Sub 41 on the G-R-S 3-terminal 69 kV line. | Planned | 153000 | Planning | 2016 | IL | 3.5 |  | 1200 A | 1200A | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | Planned | 153000 | 0% |  | 0
A in MTEP15 | West | MEC | 8039 | 2016-09-16 | 20379 | 2016-09-14 | LNup | 2020-11-01 | Sub R | GRS Tap |  | 69 |  | Rebuild the 69 kV line from Sub R to the three way GRS tap (FAC N38) in Rock Island. Replace underground cable and upgrade overhead section as needed to match cable rating. | Planned | 3325000 | Planning | 2018 | IL | 1.55 | 0 | 119 MVA | 119 MVA | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2020-11-01 | Planned | 3325000 | 0% | Updated and more detailed cost estimate. | 0
A in MTEP15 | West | MEC | 8059 | 2015-12-28 | 20364 | 2016-03-30 | CB | 2017-12-01 | DPS |  |  | 69 |  | Replace eight 69 kV circuit breakers and associated 69 kV switches at DPS Substation | Planned | 850000 | Planning | 2014 | IA |  |  | 2000A | 2000A | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 850000 | 0% |  | 0
A in MTEP15 | West | MEC | 8340 | 2015-12-28 | 20642 | 2016-03-30 | LNrc | 2015-06-15 | Ashawa | Army Post Road | 1 | 161 |  | Reconductor and rebuild the 161 kV line from Ashawa to Army Post Road with T-2 556.5 MCM ACSR conductor. | Planned | 1977833 | Planning | 2014 | IA | 4.28 | 0 | 410 | 410 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-06-15 | Planned | 1977833 | 0% | Additional work completed associated with the project. | 0
A in MTEP15 | West | MEC | 8340 | 2015-12-28 | 20643 | 2015-07-09 | LNrc | 2014-06-15 | Army Post | Willow Creek | 1 | 161 |  | Rebuild and reconductor 1.0 mile of 161 kV line from Army Post to Willow Creek with T-2 556.5 MCM ACSR conductor. | Planned | 390000 | Planning | 2014 | IA | 1 | 0 | 410 | 410 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2014-06-15 | Planned | 390000 | 0% |  | 0
A in MTEP15 | West | MEC | 8340 | 2015-12-28 | 20644 | 2016-03-30 | LNrc | 2017-06-15 | Willow Creek | Greenfield Plaza | 1 | 161 |  | Rebuild and reconductor the Willow Creek to Greenfield Plaza 161 kV line with T-2 556.5 MCM ACSR conductor. | Planned | 1850000 | Planning | 2014 | IA | 4.78 | 0 | 410 | 410 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-15 | Planned | 1850000 | 0% |  | 0
A in MTEP15 | West | MEC | 8740 | 2015-12-28 | 20739 | 2016-03-30 | LN | 2016-12-01 | Brooks | Adams County | 1 | 161 |  | New 10-mile 161 kV line from Brooks Substation to Adams County Substation. | Planned | 7500000 | Planning | 2015 | IA | 0 | 10 | 410 | 410 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 7500000 | 0% |  | 0
A in MTEP15 | West | MEC | 8740 | 2015-12-28 | 20740 | 2016-03-30 | SUB | 2016-12-01 | Brooks |  |  | 161 |  | Add two new 161 kV line circuit breakers at the existing Brooks Substation to terminate the 161 kV lines from Clarinda and Adams County Substations. | Planned | 1750000 | Planning | 2015 | IA |  |  | 2000 |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 1750000 | 0% | Revised estimate based on updated input data. | 0
A in MTEP15 | West | MEC | 8880 | 2015-12-28 | 20768 | 2015-07-09 | TX | 2015-05-01 | Sycamore | Sycamore | 1 | 161 | 69 | Replace failed transformer AG8T1 | Planned | 1645000 | Planning | 2015 | IA | 0 | 0 | 167 | 208 | Other |  | Condition | N | N | NT | Bottom-Up | A | 2015-05-01 | Planned | 1645000 | 0% |  | 0
A in MTEP15 | West | MEC | 9160 | 2015-12-28 | 20829 | 2016-09-30 | CAP | 2015-04-19 | Hastings |  |  | 69 |  | Reduce reactive capability of the 69 kV capacitor bank at Hastings Substation from 33.6 MVAR to 21.6 MVAR. Voltage step change upon switching the bank is too large during certain outage conditions. | Planned | 51657 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2015-04-19 | Planned | 51657 | 0% |  | 0
A in MTEP15 | East | METC | 2810 | 2015-12-28 | 4941 | 2016-12-20 | LNrb | 2018-12-31 | Delhi | Canal Jct | 1 | 138 |  | Rebuild 7.2 miles of 4/0 ACSR and 336.4 ACSR to 954 ACSR on new 138 kV structures. | M3_Long Lead Materials | 7500000 | Engineering |  | MI | 7.2 |  | 303 MVA | 348 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 7500000 | 0% |  | 0
A in MTEP15 | East | METC | 2810 | 2015-12-28 | 8629 | 2016-12-20 | TEQ | 2018-12-31 | Delhi |  |  | 138 |  | Terminal equipment upgrade at Delhi station. | M3_Long Lead Materials |  |  |  | MI |  |  | 303 MVA | 348 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 0 | 0% |  | 0
A in MTEP15 | East | METC | 3926 | 2017-06-28 | 7488 | 2017-06-28 | TEQ | 2017-11-28 | Dort | Pasadena | 1 | 138 |  | Replace/reset relay equipment and replace trainers in the Dort station | M4_Pre-Construction | 225000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 225000 | 0% |  | 5
A in MTEP15 | East | METC | 4506 | 2015-12-28 | 8632 | 2016-06-07 | LNrb | 2018-12-31 | Four Mile | Wealthy Street | 1 | 138 |  | Rebuild 0.96 miles of 266.8 ACSR + 3/0 Cu, 6.75 miles of 2-3/0 Cu, and 0.49 miles of 795 ACSR conductor utilizing 954 ACSR on new 138 kV structures. Install OPGW along the entire length of the circuit. | M3_Long Lead Materials | 8200000 | Engineering |  | MI | 7.71 |  | 304 MVA | 329 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 8200000 | 0% |  | 0
A in MTEP15 | East | METC | 4506 | 2015-12-28 | 8633 | 2016-06-07 | TEQ | 2018-12-31 | Four Mile |  |  | 138 |  | Station equipment upgrade at Four Mile. | M3_Long Lead Materials | 270000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 270000 | 0% |  | 0
A in MTEP15 | East | METC | 4506 | 2015-12-28 | 8634 | 2016-06-07 | TEQ | 2018-12-31 | Wealthy Street |  |  | 138 |  | Station equipment upgrade at Wealthy Street. | M3_Long Lead Materials | 130000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 130000 | 0% |  | 0
A in MTEP15 | East | METC | 4508 | 2015-12-28 | 8636 | 2016-06-07 | LNup | 2018-06-01 | Broadmoor | Plaster Creek | 1 | 138 |  | Remediate the sag on the 795 ACSR from the Broadmoor - Plaster Creek 138 kV circuit to the conductor limit. | M3_Long Lead Materials | 190000 | Engineering |  | MI | 1.1 |  | 287 MVA | 359 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | M3_Long Lead Materials | 190000 | 0% |  | 0
A in MTEP15 | East | METC | 4509 | 2015-12-28 | 8637 | 2017-06-28 | LNup | 2017-12-31 | Argenta | Battle Creek | 1 | 345 |  | Remediate sag limit to SEMER 2350 Amps. | M4_Pre-Construction | 2500000 | Engineering |  | MI | 27.9 | 0 | 1239 MVA | 1404 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 2500000 | 0% |  | 0
A in MTEP15 | East | METC | 4509 | 2015-12-28 | 8638 | 2017-06-28 | TEQ | 2017-12-31 | Battle Creek |  |  | 345 |  | Upgrade terminal equipment at Battle Creek. | M4_Pre-Construction | 68000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 68000 | 0% |  | 0
A in MTEP15 | East | METC | 4524 | 2016-01-04 | 8665 | 2016-06-07 | LNup | 2017-12-31 | Emmet | Livingston | 1 | 138 |  | Remediate sag on the Emmet - Livingston 138 kV line to bring its rating up to the conductor limit (208 MVA). | M3_Long Lead Materials | 182000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 182000 | 0% |  | 0
A in MTEP15 | East | METC | 8066 | 2017-03-29 | 20374 | 2017-03-29 | LNrb | 2019-02-28 | Amber | Donaldson Creek | 1 | 138 |  | Rebuild approx. 19.8 miles of 336 ACSR conductor utilizing 954 ACSR and OPGW on 138kV future double circuit structures. | M3_Long Lead Materials | 23000000 | Engineering | 2015 | MI | 19.8 | 0 | 199 | 259 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | M3_Long Lead Materials | 23000000 | 0% | Installation of 2nd shield wire to accommodate future expansion. | 8
A in MTEP15 | East | METC | 8067 | 2017-06-28 | 20380 | 2017-06-28 | CB | 2017-07-31 | Beals Road |  |  | 138 |  | Replace the limiting equipment on the Beals Road 138 kV bus tie at positions 500, 505, and 506. | M4_Pre-Construction | 400000 | Engineering | 2014 | MI | 0 | 0 | 430 MVA | 478 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 400000 | 0% |  | 1
A in MTEP15 | East | METC | 8070 | 2015-12-28 | 20388 | 2017-01-18 | TEQ | 2017-01-14 | North Belding | Vergennes | 1 | 138 |  | Replace limiting terminal equipment at North Belding. | M5_In Service | 120000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 120000 | 0% |  | -5
A in MTEP15 | East | METC | 8072 | 2015-12-28 | 20394 | 2017-03-29 | LNrb | 2019-12-31 | Riggsville | Port Calcite | 1 | 138 |  | Rebuild 45 miles of 336.4 ACSR strung on 138 kV single circuit wood poles installed in 1960. | M3_Long Lead Materials | 62048000 | Engineering Preliminary |  | MI | 45 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M2a_Pre-Project Approval | 62048000 | 0% |  | 0
A in MTEP15 | East | METC | 8072 | 2015-12-28 | 20396 | 2017-03-29 | LNrb | 2019-12-31 | Port Calcite | Rockport | 1 | 138 |  | Rebuild 24 miles of 266.8 ACSR strung on 138 kV single circuit wood poles installed in 1958. | M3_Long Lead Materials | 34457000 | Engineering Preliminary |  | MI | 24 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M2a_Pre-Project Approval | 34457000 | 0% |  | 0
A in MTEP15 | East | METC | 8077 | 2017-05-17 | 20418 | 2017-05-17 | LNrb | 2020-12-31 | Vestaburg | Alma | 1 | 138 |  | Rebuild the Vestaburg - Alma 138 kV circuit utilizing 138 kV single circuit steel poles and 954 ACSR conductor. Install OPGW along the entire length of the circuit. Also reconductor 2.9 miles of the Eureka – Vestaburg 138 kV circuit using 954 ACSR. | M2a_Pre-Project Approval | 22900000 | Engineering |  | MI | 16.7 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 18200000 | 25.82% | Refined Engineering level estimate and added installation of OPGW to the scope of work. Cost estimate also increased with the replacement of 18 condemned wood poles which have been included to the scope of the rebuild project. (When this project was initially submitted in MTEP15, those wood poles were planned to be replaced under the blanket Wood Pole Replacement Project.) Also updated estimate to include 954 ACSR for the double circuit portion of Eureka-Vestaburg. Matting costs were raised significantly based on recent projects as well. | 24
A in MTEP15 | East | METC | 8078 | 2017-02-23 | 20401 | 2017-02-23 | CAP | 2019-06-01 | Donaldson Creek |  |  | 138 |  | 33.3 MVAR Capacitor | M2a_Pre-Project Approval | 1200000 | Engineering | 2014 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | M2a_Pre-Project Approval | 1200000 | 0% |  | 24
A in MTEP15 | East | METC | 8080 | 2017-06-28 | 20404 | 2017-06-28 | CAP | 2017-09-30 | Coldwater |  |  | 138 |  | Install a 3 x 18 MVAR capacitor and associated station equipment at the 138 kV Coldwater Substation. | Under Construction | 3900000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 3900000 | 0% |  | 3
A in MTEP15 | East | METC | 8090 | 2015-12-28 | 20416 | 2016-06-07 | LNup | 2018-06-01 | Cornell | Blue Water Jct. | 1 | 138 |  | Remediate the sag limit to at least 760 A. | M3_Long Lead Materials | 320000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | M3_Long Lead Materials | 320000 | 0% |  | 0
A in MTEP15 | East | METC | 8091 | 2016-03-22 | 20417 | 2016-03-22 | LNup | 2018-06-01 | Donaldson Creek | White Lake | 1 | 138 |  | Remediate sag limit. | M2a_Pre-Project Approval | 360000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | M2a_Pre-Project Approval | 360000 | 0% |  | 0
A in MTEP15 | East | METC | 8096 | 2015-12-28 | 20421 | 2016-06-07 | LNup | 2017-12-31 | Roosevelt | Gaines | 1 | 345 |  | Remediate sag limit. | M3_Long Lead Materials | 380000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 380000 | 0% |  | 0
A in MTEP15 | East | METC | 8109 | 2017-05-25 | 20446 | 2017-05-25 | LNup | 2017-12-31 | Gaylord | Livingston | 1 | 138 |  | Remediate the sag limit on the Gaylord - Livingston 138 kV line. | M4_Pre-Construction | 75000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 75000 | 0% |  | 6
A in MTEP15 | East | METC | 8118 | 2015-12-28 | 20466 | 2016-12-20 | TEQ | 2018-12-31 | Beecher |  |  | 138 |  | Replace overloaded terminal equipment at Beecher. | M3_Long Lead Materials | 350000 | Planning |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 350000 | 0% |  | 0
A in MTEP15 | East | METC | 8118 | 2015-12-28 | 20468 | 2016-12-20 | LNrb | 2018-12-31 | Beecher | Samaria | 1 | 138 |  | Rebuild the 636 ACSR portion of the Beecher to Samaria 138 kV circuit utilizing 954 ACSR on 138 kV double circuit steel poles. | M3_Long Lead Materials | 21000000 | Engineering |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 21000000 | 0% |  | 0
A in MTEP15 | East | METC | 8118 | 2015-12-28 | 20800 | 2016-12-20 | RLY | 2018-12-31 | Morocco |  |  | 138 |  | Upgrade relays at Morocco station. | M3_Long Lead Materials | 250000 | Engineering |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 250000 | 0% |  | 0
A in MTEP15 | East | METC | 8118 | 2015-12-28 | 20801 | 2016-12-20 | LNrc | 2018-12-31 | Beecher | Whiting | 1 | 138 |  | Relocate the Beecher-Whiting 138 kV line to the open side of the new structures. | M3_Long Lead Materials | 4000000 | Engineering |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 4000000 | 0% |  | 0
A in MTEP15 | East | METC | 8119 | 2016-08-30 | 20470 | 2017-03-29 | LNup | 2017-12-31 | METC Pole Top Switches Additions-Replacement Program - 2017 |  |  | 138 |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points across the METC system. | Under Construction | 3600000 |  | 2017 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 3600000 | 0% |  | 0
A in MTEP15 | East | METC | 8121 | 2015-12-28 | 20472 | 2016-06-07 | LNup | 2018-12-31 | Hackett Jct. | Laundra Jct. | 1 | 138 |  | Remediate the sag limit on the Hackett Jct. to Laundra Jct. section of the Bullock to Saginaw River 138 kV circuit. | M3_Long Lead Materials | 90000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 90000 | 0% |  | 0
A in MTEP15 | East | METC | 8122 | 2016-08-30 | 20474 | 2015-12-28 | LNup | 2018-12-31 | METC Pole Top Switches Additions-Replacement Program |  |  | 138 |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at various tap points across the METC system. | M2a_Pre-Project Approval | 3600000 |  | 2018 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 3600000 | 0% |  | 0
A in MTEP15 | East | METC | 8124 | 2015-12-28 | 20476 | 2016-06-07 | LNrb | 2018-12-31 | Argenta | Morrow | 1 | 138 |  | Rebuild approximately 10 miles of existing 138 kV steel lattice towers with wood cross arms to double circuit capable 230 kV construction steel monopoles and string one side with 954 ACSR. | M3_Long Lead Materials | 13900000 | Engineering |  | MI | 10.5 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M3_Long Lead Materials | 13900000 | 0% |  | 0
A in MTEP15 | East | METC | 8126 | 2016-10-11 | 20477 | 2016-10-11 | IND | 2016-08-26 | Kenowa |  |  | 345 |  | Replace reactor 28R | M5_In Service | 3500000 | Engineering |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-08-15 | Under Construction | 3500000 | 0% |  | 0
A in MTEP15 | East | METC | 8127 | 2016-08-30 | 20484 | 2016-12-20 | CB | 2017-12-31 | Ludington |  |  | 345 |  | Replace Ludington 345 kV circuit breakers 22H9, 24H9, 25H9 and 22F7, 24F7, 25F7 with 345 kV live tank circuit breakers containing 400 OHM pre-insertion resistors. | M3_Long Lead Materials | 8640000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 8640000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20521 | 2016-03-22 | TX | 2018-05-31 | Meyer (formerly “Hayes Street”) |  |  | 345 | 138 | Install a 345/138 kV transformer at the new Meyer substation. | M3_Long Lead Materials | 4500000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M3_Long Lead Materials | 4500000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20523 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Tallmadge | 1 | 345 |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Ludington-Tallmadge #2 345 kV line into Meyer utilizing 2-954 ACSR conductor. Also remediate the sag limit on the Meyer -Tallmadge #1 345 kV circuit to a minimum of 2007 MVA | M2a_Pre-Project Approval | 1200000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 1200000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20524 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Ludington | 1 | 345 |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Ludington-Tallmadge #2 345 kV line into Meyer utilizing 2-954 ACSR conductor. | M2a_Pre-Project Approval | 1200000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 1200000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20525 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Argenta | 1 | 345 |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Kenowa - Argenta 345 kV line into Meyer utilizing 2-954 ACSR conductor. Also remediate the sag limit on the Meyer - Argenta 345 kV circuit to a minimum of 1524 MVA. | M2a_Pre-Project Approval | 1300000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 1300000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20526 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Kenowa | 1 | 345 |  | Construct approx. 0.1 miles of new 345 kV, double circuit structures, and loop the Kenowa - Argenta 345 kV line into Meyer utilizing 2-954 ACSR conductor. | M2a_Pre-Project Approval | 1300000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 1300000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20527 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Tallmadge | 2 | 138 |  | Construct approx. 0.25 miles of new 138 kV, double circuit structures, and loop the Cobb-Tallmadge #1 138 kV line into Meyer utilizing 954 ACSR conductor. | M2a_Pre-Project Approval | 900000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 900000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20528 | 2016-03-22 | LN | 2018-05-31 | Meyer (formerly “Hayes Street”) | Cobb | 1 | 138 |  | Construct approx. 0.25 miles of new 138 kV, double circuit structures, and loop the Cobb-Tallmadge #1 138 kV line into Meyer utilizing 954 ACSR conductor. | M2a_Pre-Project Approval | 960000 | Engineering |  | MI |  | 0.1 |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 960000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20529 | 2016-03-22 | SUB | 2018-05-31 | Meyer (formerly “Hayes Street”) |  |  | 345 | 138 | Construct the Meyer substation and install all 345 and 138 kV terminal equipment to accommodate the new transformer and looping in the Ludington - Tallmadge #2 345 kV, Argenta-Kenowa 345 kV, and Cobb-Tallmadge #1 138 kV circuits. | M2a_Pre-Project Approval | 20200000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 20200000 | 0% |  | 0
A in MTEP15 | East | METC | 8144 | 2016-03-22 | 20531 | 2016-03-22 | SUB | 2018-05-31 | Tallmadge |  |  | 345 |  | Replace 345 kV terminal equipment at Talmadge substation | M2a_Pre-Project Approval | 140000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 140000 | 0% |  | 0
A in MTEP15 | East | METC | 8170 | 2017-03-29 | 20575 | 2017-03-29 | RLY | 2017-10-31 | Leoni | Page Ave | 1 | 138 |  | Install the second relay component on the Leoni to Page Ave. 138 kV circuit at Leoni end so that, for faults on the Page Ave. end, the Leoni breaker will trip and clear the fault with one relay component failure. | M4_Pre-Construction | 75000 |  | 2016 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 75000 | 0% |  | 10
A in MTEP15 | East | METC | 8171 | 2016-12-20 | 20576 | 2016-12-20 | RLY | 2018-01-01 | Croton | Felch Road | 1 | 138 |  | 1. Install dual pilot relay protection system on Croton to Felch Road 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 7 cycles. 2. Remove the sparing scheme of using Croton 138 kV breaker 500 to spare breaker 388 for Croton to Felch Road 138 kV circuit. 3. Remove Felch Road 138 kV BK 188 Bypassing | M3_Long Lead Materials | 540000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 540000 | 0% |  | 7
A in MTEP15 | East | METC | 8460 | 2015-12-28 | 20675 | 2017-06-28 | LNup | 2017-12-31 | Hemphill | Sabine | 1 | 138 |  | Remediate the sag limit on the Sabine - Hemphill 138 kV line to increase its summer emergency rating to the 336 ACSR conductor rating of 208 MVA (871 Amps). | M4_Pre-Construction | 140000 | Engineering | 2014 | MI |  |  | 180 | 208 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 140000 | 0% |  | 0
A in MTEP15 | East | METC | 8461 | 2017-06-28 | 20674 | 2017-06-28 | LNup | 2017-06-30 | Cobb | Sternberg | 1 | 138 |  | Remediate the sag limit on the Cobb-Sternberg 138 kV line to bring its rating up to 174 MVA (730 Amp). | Under Construction | 480000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 480000 | 0% |  | 0
A in MTEP15 | East | METC | 8540 | 2015-12-28 | 20680 | 2016-06-07 | LNup | 2017-12-31 | Claremont | Layton | 1 | 138 |  | Remediate the sag limit on the Claremont-Layton section of the Claremont - Cornell #1 138 kV line to a rating 209 MVA (874 Amps). | M3_Long Lead Materials | 520000 | Engineering | 2015 | MI | 17.2 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 520000 | 0% |  | 0
A in MTEP15 | East | METC | 9361 | 2016-03-23 | 20877 | 2016-10-06 | SwSta | 2016-09-30 | Green 138 kV |  |  | 138 |  | Install 4-138 kV breakers with associated disconnects laid out in a ring bus configuration. | M5_In Service | 4483000 | Engineering | 2015 | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-10-01 | Under Construction | 4483000 | 0% |  | -1
A in MTEP15 | East | METC | 9361 | 2016-03-23 | 20878 | 2016-10-06 | LN | 2016-09-30 | Delhi | Green | 1 | 138 |  | New line created by looping the Delhi-College 138 kV circuit into Green. METC will construct approx. 0.1 miles of new double circuit structures to loop the existing line into Green | M5_In Service | 412000 | Engineering | 2015 | MI |  | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-10-01 | Under Construction | 412000 | 0% |  | -1
A in MTEP15 | East | METC | 9361 | 2016-03-23 | 20879 | 2016-10-06 | LN | 2016-09-30 | College | Green | 1 | 138 |  | New line created by looping the Delhi-College 138 kV circuit into Green. METC will construct approx. 0.1 miles of new double circuit structures to loop the existing line into Green | M5_In Service | 412000 | Engineering | 2015 | MI |  | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-10-01 | Under Construction | 412000 | 0% |  | -1
A in MTEP15 | West | MP | 7995 | 2015-12-28 | 20268 | 2015-05-13 | TX | 2015-12-31 | Maturi |  | 1 | 115 | 23 | New 115/23 kV transformer | Planned | 1426000 | Scoping | 2014 | MN | 0 | 0 | 18.6 | 23.3 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 1426000 | 0% |  | 0
A in MTEP15 | West | MP | 7998 | 2015-12-28 | 20278 | 2015-03-20 | CB | 2017-12-31 | Dog Lake |  |  | 115 |  | Add three new breakers plus bus expansion at existing Dog Lake Substation | Planned | 2100000 | Engineering Preliminary | 2014 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2100000 | 0% |  | 0
A in MTEP15 | West | MP | 7998 | 2015-12-28 | 20279 | 2015-03-20 | LN | 2017-12-31 | Scearcyville | Dog Lake | 1 | 115 |  | Extend line to expanded substation | Planned | 330000 | Engineering Preliminary | 2014 | MN | 0 | 0.5 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 330000 | 0% |  | 0
A in MTEP15 | West | MP | 7998 | 2015-12-28 | 20280 | 2015-03-20 | LN | 2017-12-31 | Verndale | Dog Lake | 1 | 115 |  | Extend line to expanded Dog Lake Substation | Planned | 330000 | Engineering Preliminary | 2014 | MN | 0 | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 330000 | 0% |  | 0
A in MTEP15 | West | MP | 7998 | 2015-12-28 | 20281 | 2015-03-20 | LN | 2017-12-31 | Badoura | Dog Lake | 1 | 115 |  | Extend line to expanded Dog Lake Substation | Planned | 330000 | Engineering Preliminary | 2014 | MN | 0 | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 330000 | 0% |  | 0
A in MTEP15 | West | MP | 7999 | 2015-12-28 | 20282 | 2015-06-10 | SUB | 2016-10-01 | Straight River |  |  | 115 | 34.5 | New 115/34.5 kV Substation | Planned | 2140000 | Engineering | 2014 | MN | 0 | 0 | 10 | 12.5 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 2140000 | 0% |  | 0
A in MTEP15 | West | MP | 7999 | 2015-12-28 | 20283 | 2015-06-10 | TAP | 2016-10-01 | Straight River |  |  | 115 |  | Tap in Hubbard - Blueberry 115 kV Line | Planned | 620000 | Engineering | 2014 | MN | 0 | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 620000 | 0% |  | 0
A in MTEP15 | West | MP | 7999 | 2015-12-28 | 20821 | 2015-06-10 | Dist | 2016-10-01 | Straight River | Park Rapids Pump Station |  | 34.5 |  | 34.5 kV feeder extension from Straight River to pump station | Planned | 50000 | Engineering | 2014 | MN |  | 0.1 | 20 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-10-01 | Planned | 50000 | 0% |  | 0
A in MTEP15 | West | MP | 8000 | 2015-12-28 | 20284 | 2015-04-02 | LNrl | 2018-05-01 | Arrowhead | 16L Tap | 1 | 115 |  | Relocate line segment | Planned | 4740000 | Engineering | 2015 | MN | 0 | 3 | 55 | 60.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 4740000 | 0% |  | 0
A in MTEP15 | West | MP | 8001 | 2015-12-28 | 20285 | 2015-05-12 | TAP | 2015-10-01 | Enbridge East | New Line Tap | 1 | 115 |  | New line tap in Stinson - Gary 115 kV line | Planned | 802541 | Engineering | 2014 | WI | 0 | 0.25 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-10-01 | Planned | 802541 | 0% |  | 0
A in MTEP15 | West | MP | 8002 | 2015-12-28 | 20286 | 2015-06-12 | TAP | 2015-07-15 | South | New Line Tap | 1 | 115 |  | New line tap in existing Nemadji Tap (part of Gary - Stinson 115 kV Line) | Under Construction | 1229500 | Construction | 2015 | WI | 0 | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-07-15 | Under Construction | 1229500 | 0% |  | 0
A in MTEP15 | West | MP | 8003 | 2015-12-28 | 20287 | 2015-05-12 | TAP | 2015-12-31 | Hawthorne | Rebuilt Line Tap | 1 | 161 |  | Rebuild existing Hawthorne Tap in Stinson - Gordon 161 kV Line | Planned | 530000 | Engineering Preliminary | 2014 | WI | 0 | 0.1 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 530000 | 0% |  | 0
A in MTEP15 | West | MP | 9060 | 2015-12-28 | 20802 | 2015-05-08 | TX | 2016-10-01 | Forbes |  |  | 230 | 115 | Addition of a second 230/115 kV Transfomer to relieve loading off the existing 230/115 kV under post contingent events. | Planned | 4000000 | Planning |  | MN |  |  | 373 | 466.25 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 4000000 | 0% |  | 0
A in MTEP15 | West | MP | 9061 | 2015-12-28 | 20803 | 2015-05-08 | CB | 2016-10-01 | Minntac |  |  | 230 |  | Adding 3 additional cirucit breakers and associated equipment to change the existing substation into a ring bus design. | Planned | 3000000 | Planning |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 3000000 | 0% |  | 0
A in MTEP15 | West | MP | 9061 | 2015-12-28 | 20804 | 2015-05-08 | LNrl | 2016-10-01 | Minntac | Forbes |  | 230 |  | Relocating line entrance at Minntac substation to fit into new ring bus design. | Planned | 1000000 | Planning |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 1000000 | 0% |  | 0
A in MTEP15 | West | MP | 9062 | 2015-12-28 | 20805 | 2015-05-08 | TX | 2016-05-01 | Maturi |  | 1 | 115 | 34.5 | Transformer swap | Planned | 400000 | Planning | 2015 | MN | 0 | 0 | 18.6 | 23.4 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-05-01 | Planned | 400000 | 0% |  | 0
A in MTEP15 | West | MP | 9063 | 2015-12-28 | 20806 | 2015-05-08 | LN | 2016-12-31 | Hat Trick | Laskin | 1 | 115 |  | Extend existing 115 kV line to new substation | Planned | 499000 | Engineering | 2015 | MN | 0 | 0.1 | 98 | 107.8 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 499000 | 0% |  | 0
A in MTEP15 | West | MP | 9063 | 2015-12-28 | 20807 | 2015-05-08 | LN | 2016-12-31 | Hat Trick | 37 Line Tap | 1 | 115 |  | Extend existing line to new substation | Planned | 499000 | Engineering | 2015 | MN | 0 | 0.1 | 98 | 107.8 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 499000 | 0% |  | 0
A in MTEP15 | West | MP | 9063 | 2015-12-28 | 20808 | 2015-05-08 | SUB | 2016-12-31 | Hat Trick |  |  | 115 | 23 | New 115/23 kV Substation | Planned | 4836850 | Engineering | 2015 | MN | 0 | 0 | 39.2 | 49 | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 4836850 | 0% |  | 0
A in MTEP15 | East | NIPS | 8500 | 2015-12-28 | 20678 | 2016-03-15 | BUS | 2018-12-31 | Lagrange | Lagrange |  | 138 | 138 | Make necessary upgrades at Lagrange 138kV Substation to create ring bus. | Planned | 2715000 | Planning | 2014 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 2715000 | 0% |  | 0
A in MTEP15 | East | NIPS | 9405 | 2015-12-28 | 20896 | 2016-04-28 | SUBmisc | 2018-05-01 | Kosciusko |  |  | 138 |  | Replace Line switch and substation Conductor | Planned | 147845 | Planning | 2015 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 147845 | 0% |  | 0
A in MTEP15 | East | NIPS | 9406 | 2015-12-28 | 20897 | 2016-03-15 | SUBmisc | 2018-05-01 | Reynolds |  |  | 138 |  | Replace (2) 138kV Switches at Reynolds | Planned | 112665 | Planning | 2015 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 112665 | 0% |  | 0
A in MTEP15 | East | NIPS | 9461 | 2016-01-05 | 20915 | 2015-11-25 | RLY | 2018-12-31 | 17HIPLE |  |  | 138 |  | Add Redundant 138kV Bus Differential Relay | Planned | 50000 | Planning | 2014 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 50000 | 0% |  | 0
A in MTEP15 | West | OTP | 8240 | 2015-12-28 | 20614 | 2015-09-22 | TX | 2016-10-31 | Jamestown 345 |  |  | 345 | 115 | Replace existing 345/115/41.6 kV transformers #1 and #2 at Jamestown with two larger 336 MVA transformers. | Planned | 7000000 | Planning |  | ND |  |  | 336 MVA |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2016-10-31 | Planned | 7000000 | 0% |  | 0
A in MTEP15 | West | OTP | 8240 | 2015-12-28 | 21440 | 2015-09-22 | SUB | 2016-10-31 | Jamestown 345kV |  |  | 115 |  | Install 115 kV ring bus breaker and bus work. | Planned | 850000 | Planning | 2015 | ND |  |  |  |  | GIP | Shared |  | N | N | Y | Externally Driven | A | 2016-10-31 | Planned | 850000 | 0% |  | 0
A in MTEP15 | West | OTP | 8240 | 2015-12-28 | 21468 | 2015-10-13 | SUB | 2016-10-31 | Jamestown 345 |  |  | 345 |  | Install 345 kV Breaker as a tie breaker between the transformers. | Planned | 1700000 | Planning |  | ND |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2016-10-31 | Planned | 1700000 | 0% |  | 0
A in MTEP15 | West | OTP | 8281 | 2017-03-28 | 20627 | 2017-03-28 | SUB | 2018-11-30 | Donaldson 115 | Drayton 115 |  | 115 |  | Add a new 115 kV breaker at Donaldson to the Donaldson to Drayton 115 kV line to improve reliability of area loads. This breaker will reduce fault exposure to Donaldson loads by 17 miles and improve operations, maintenance, and relaying flexibility at Donaldson. | Planned | 370000 | Planning Preliminary |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-07-31 | Planned | 370000 | 0% | Project Delay causes cost increase in labor and materials | 4
A in MTEP15 | Central | PPI | 7881 | 2017-06-02 | 20113 | 2017-02-21 | LN | 2019-12-31 | Fishhook | Pittsfield | 1 | 138 |  | 14.5 mile single pole 138 kV line constructed with 795 MCM ACSR conductor. Portions of the line will be double circuited with the Fishhook-Liberty 138 kV line and the Pittsfield-Pittsfield Distribution 69 kV line. | Planned | 6887747 | Engineering | 2018 | IL |  | 14.5 | 229 | 229 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 6887747 | 0% |  | 12
A in MTEP15 | Central | PPI | 7881 | 2017-06-02 | 20121 | 2017-02-21 | LNrb | 2019-12-31 | Pittsfield | Pittsfield Distribution | 1 | 69 | 69 | 69 kV Underbuild on portion of Fishhook-Pittsfield 138 kV line. Replace approximately 2.5 miles of 4/0 conductor from Pittsfield-Pittsfield Distribution 69 kV with 336.4 MCM ACSR conductor. | Planned | 750000 |  | 2017 | IL | 2.5 |  | 50 | 50 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 750000 | 0% |  | 24
A in MTEP15 | Central | PPI | 7889 | 2017-06-02 | 20123 | 2015-03-12 | LN | 2019-12-31 | Fishhook 138 kV | Liberty 138 kV |  | 138 | 138 | Construct 12 mile 138 kV line from Fishhook substation to Liberty substation. | Planned | 5819909 | Engineering | 2019 | IL |  | 12 | 229 | 229 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 5819909 | 0% |  | 0
A in MTEP15 | Central | PPI | 7889 | 2017-06-02 | 20124 | 2016-09-09 | SUB | 2019-12-31 | Liberty 138 kV | Liberty 69 kV | 1 | 138 | 69 | New 138/69 kV substation including 75 MVA 138/69 kV transformer. | Planned | 4653000 | Engineering | 2019 | IL |  |  | 75 | 75 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 4653000 | 0% | Updated budgetary estimate | 0
A in MTEP15 | Central | PPI | 7889 | 2017-06-02 | 20125 | 2016-09-09 | TX | 2019-12-31 | St. Anthony 138 kV | St. Anthony 69 kV |  | 138 | 69 | Replace 50 MVA delta-wye 138/69 kV transformer with 75 MVA wye-wye transformer with LTC. | Planned | 1251800 | Engineering | 2019 | IL |  |  | 75 | 75 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-12-31 | Planned | 1251800 | 0% | Updated budgetary estimates | 0
A in MTEP15 | South | SMEPA | 8120 | 2016-09-26 | 20518 | 2017-03-30 | LNrb | 2016-10-31 | Ellisville | Glade GOAB | 1 | 69 |  | Rebuild L18 (Ellisville - Glade GOAB) using 759 ACSR conductor and 48-fiber OPGW. | M5_In Service | 1242195 | Planning | 2013 | MS | 4.63 |  | 71 | 71 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-10-31 | Planned | 1242195 | 0% |  | 0
A in MTEP15 | South | SMEPA | 8120 | 2016-09-26 | 20520 | 2017-03-30 | LNrb | 2017-01-01 | Glade GOAB | Cleo | 1 | 69 |  | Rebuild L18A (Glade GOAB - Cleo) using 795 ACSR conductor with 48-fiber OPGW. | M5_In Service | 1617805 | Planning | 2013 | MS | 6.03 |  | 71 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-04-30 | Planned | 1617805 | 0% |  | -3
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20682 | 2017-06-22 | LNcnv | 2018-08-01 | Waynesboro | Missionary | 1 | 230 |  | Convert Waynesboro - Missionary 161kV line to 230kV operation. | Planned | 535000 | Engineering | 2014 | MS | 38.31 |  | 501 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-08-01 | Planned | 500000 | 7% | Changes in construction | 0
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20683 | 2017-06-22 | BUS | 2018-08-01 | Missionary |  |  | 230 |  | Add 230kV Bay with Breaker at Missionary | Planned | 670000 | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 670000 | 0% |  | 2
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20684 | 2017-06-22 | BUS | 2018-08-01 | Waynesboro |  |  | 230 |  | Add 230kV Breaker to existing bay at Waynesboro | Planned | 230000 | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 230000 | 0% |  | 2
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20685 | 2017-06-22 | BUS | 2018-08-01 | Waynesboro |  |  | 230 |  | Add 230kV bay with breaker at Waynesboro (Create Ring Bus Configuration) | Planned | 670000 | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 670000 | 0% |  | 2
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20697 | 2017-06-22 | SwSta |  | Waynesboro - Missionary | Laurel East - Enterprise |  | 230 |  | Tap the existing SMEPA owned Waynesboro - Missionary and MPCo owned Laurel East - Enterprise lines at the point of intersection and construct a 230kV switching station. | Withdrawn_AltOrScope |  | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 365000 | -100% |  | -1421
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20698 | 2017-06-22 | SUB |  | Waynesboro - Missionary | Laurel East - Enterprise |  | 230 |  | Add 230kV Bay with Breakers at switching station. | Withdrawn_AltOrScope |  | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 2680000 | -100% |  | -1421
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20699 | 2017-06-22 | SUB | 2018-08-01 | Missionary |  |  | 230 | 161 | Add 230/161kV Transformer (250 MVA) at existing SMEPA owned Missionary substation. | Planned | 2900000 | Engineering | 2014 | MS |  |  | 250 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 2900000 | 0% |  | 2
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20700 | 2016-07-01 | BUS | 2018-06-01 | Missionary |  |  | 161 |  | Add 161kV breaker to existing bay at Missionary substation. | Planned | 165000 | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 165000 | 0% |  | 0
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20701 | 2017-06-22 | BUS | 2019-01-01 | Homewood |  |  | 161 |  | Add 161kV Bay with Breaker at Homewood. | Planned | 545000 | Engineering | 2014 | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 545000 | 0% |  | 13
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20702 | 2017-06-22 | LN | 2020-12-01 | Homewood | Missionary | 1 | 161 |  | Add additional 161kV circuit to existing double circuit line. | Planned | 3874000 | Engineering | 2014 | MS | 31 |  | 296 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-02-01 | Planned | 3410000 | 13.61% | Public Service Commission | 10
A in MTEP15 | South | SMEPA | 8560 | 2016-02-03 | 20703 | 2017-06-22 | LNrb | 2020-12-01 | Homewood | Missionary |  | 161 |  | Rebuild existing 69kV lines from span from Homewood - Missionary using double circuit provisions for the addition of the 161kV path from Homewood - Missionary. | Planned | 7289000 | Engineering | 2014 | MS | 19.5 |  | 296 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-09-01 | Planned | 6825000 | 6.799% | Changes in constrction | 3
A in MTEP15 | South | SMEPA | 9000 | 2015-12-28 | 20792 | 2017-03-30 | LNrb | 2016-06-01 | Benndale | Benndale GT | 1 | 69 |  | Rebuild line using 795 ACSR and 48-fiber OPGW. | M5_In Service | 370000 | Planning | 2015 | MS | 1.2 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-07-15 | Planned | 370000 | 0% |  | -1
A in MTEP15 | South | SMEPA | 9020 | 2017-01-24 | 20793 | 2017-03-30 | LNrb | 2017-09-01 | Wiggins GOAB | Big Level | 1 | 69 |  | Rebuild the existing Big Level - Wiggins GOAB 69kV line using 795 ACSR conductor and 48-fiber. | M4_Pre-Construction | 1875000 | Planning | 2015 | MS | 8.4 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 1875000 | 0% |  | -3
A in MTEP15 | Central | Vectren | 4391 | 2016-05-19 | 8408 | 2017-03-31 | CAP | 2019-12-31 | Pigeon Creek 69 | Capacitor |  | 69 |  | Add a 15.6 MVAR cap bank at the Pigeon Creek Sub | Planned | 770000 | Planning | 2013 | IN | 0 | 0 | 15.6 MVAR | 15.6 MVAR | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 600000 | 28.33% | Adjusted for later year budget estimate | 0
A in MTEP15 | Central | Vectren | 10142 | 2015-12-28 | 21473 | 2016-01-13 | TEQ | 2021-01-01 | Duff |  |  | 345 |  | Sub upgrades at Duff | Planned | 3092381 |  |  | IN |  |  |  |  | MEP | Shared |  | Y | N | Y | Top-Down | A | 2021-01-01 | Planned | 3092381 | 0% |  | 0
A in MTEP15 | East | WPSC | 3567 | 2015-12-28 | 6651 | 2015-09-15 | LNrb | 2017-12-31 | Hersey | Osceola Jct | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 2100000 | Budgetary | 2015 | MI | 4.02 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2100000 | 0% |  | 0
A in MTEP15 | East | WPSC | 3567 | 2015-12-28 | 6652 | 2015-09-15 | LNrb | 2017-12-31 | Osceola Jct | Barryton | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 4700000 | Budgetary | 2015 | MI | 9.69 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4700000 | 0% |  | 0
A in MTEP15 | East | WPSC | 3567 | 2015-12-28 | 6653 | 2015-09-15 | LNrb | 2017-12-31 | Barryton | Martiny | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 500000 | Budgetary | 2015 | MI | 1 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 500000 | 0% |  | 0
A in MTEP15 | East | WPSC | 3567 | 2015-12-28 | 6654 | 2015-09-15 | LNrb | 2017-12-31 | Martiny | Weidman | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 4200000 | Budgetary | 2015 | MI | 8.37 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4200000 | 0% |  | 0
A in MTEP15 | East | WPSC | 4086 | 2015-12-28 | 7739 | 2015-09-15 | LNrb | 2016-12-31 | Fountain Junction | Scottville | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 4650000 | Planning | 2016 | MI | 9.15 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 4650000 | 0% | Updated estimated cost in 2015 planning review. | 0
A in MTEP15 | East | WPSC | 4384 | 2015-12-28 | 8399 | 2014-09-25 | SUB | 2017-12-31 | Airport | Substation Upgrade |  | 138 | 69 | 138kV Breaker Replacement and Protective Equipment Upgrade | Planned | 4100000 | Budgetary | 2017 | MI |  |  |  |  | Other |  | Reconfig | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 4100000 | 0% |  | 0
A in MTEP15 | East | WPSC | 4384 | 2015-12-28 | 21502 | 2015-10-28 | SUB | 2017-01-01 | Airport |  |  | 138 |  | Airport Substation zoning costs | Planned | 40000 | Budgetary | 2016 | MI |  |  |  |  | Other |  | Reconfig | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 40000 | 0% |  | 0
A in MTEP15 | East | WPSC | 4384 | 2015-12-28 | 21503 | 2015-10-28 | SUB | 2018-12-31 | Airport |  |  | 138 |  | Landscaping costs | Planned | 50000 | Budgetary | 2018 | MI |  |  |  |  | Other |  | Reconfig | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 50000 | 0% |  | 0
A in MTEP15 | East | WPSC | 7660 | 2015-12-28 | 20047 | 2017-04-21 | BUS | 2016-12-31 | Advance Transmission |  |  | 69 |  | New 69KV switching station | M5_In Service | 3791084 | Planning | 2016 | MI |  |  |  |  | Other |  | Relocation | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 2250000 | 68.49% | Above expected excavation costs | 0
A in MTEP15 | East | WPSC | 7661 | 2015-12-28 | 20048 | 2016-09-15 | BUS | 2017-12-31 | Vestaburg Transmission |  |  | 69 |  | Switch and bus upgrades, including a sparing scheme addition | Planned | 170000 | Planning | 2016 | MI |  |  |  |  | Other |  | Reconfig | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 170000 | 0% |  | 0
A in MTEP15 | East | WPSC | 7662 | 2015-12-28 | 20049 | 2016-09-15 | BUS | 2017-12-31 | Atlanta Transmission |  |  | 69 |  | Replace equipment | Planned | 250000 | Budgetary | 2016 | MI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 250000 | 0% |  | 0
A in MTEP15 | East | WPSC | 7663 | 2015-12-28 | 20050 | 2016-09-15 | BUS | 2017-12-31 | Gaylord OCB |  |  | 69 |  | Replace breaker and upgrade control system | Planned | 300000 | Planning | 2017 | MI |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 300000 | 0% |  | 0
A in MTEP15 | East | WPSC | 8220 | 2016-08-30 | 20608 | 2017-04-21 | LNup | 2016-05-31 | Casnovia | White Cloud |  | 69 |  | 1.93 miles of line has been requested by GLE to be raised to accommodate distribution underbuild. This project will rebuild a total of 2.5 miles to gradually tie the new taller poles into the existing line. The existing conductor is planned to be used for this project. | M5_In Service | 967006 | Budgetary | 2016 | MI | 2.5 |  |  |  | Other |  | Relocation | N | N | NT | Bottom-Up | A | 2016-05-31 | Planned | 800000 | 20.88% | Weather reducing efficiency. | 0
A in MTEP15 | East | WPSC | 8221 | 2015-12-28 | 20609 | 2014-10-30 | LN | 2017-12-31 | Airport 138kV & 69kV |  |  | 138 | 69 | This project will construct the line modifications required to route lines into the new Airport station. | Planned | 1000000 | Budgetary | 2017 | MI |  |  |  |  | Other |  | Relocation | N | N | NT | Bottom-Up | A | 2017-12-31 | Planned | 1000000 | 0% |  | 0
A in MTEP15 | East | WPSC | 8380 | 2015-12-28 | 20653 | 2014-11-04 | LN | 2016-12-31 | Advance Transmission |  |  | 69 |  | Line modifications to support the Advance Transmission station project | Planned | 1250000 | Budgetary |  | MI |  |  |  |  | Other |  | Relocation | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 1250000 | 0% |  | 0
A in MTEP15 | West | XEL | 8075 | 2015-12-28 | 20395 | 2017-03-20 | SUB | 2016-12-30 | Lake Bavaria |  |  | 115 |  | Install new distribution substation | M5_In Service | 1153304 | Scoping | 2015 | MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 1153304 | 0% |  | 0
A in MTEP15 | West | XEL | 8079 | 2015-12-28 | 20403 | 2017-06-24 | LINE | 2022-12-01 | Madelia Switching Station | Village of Madelia | 1 | 69 |  | Rebuild 3.6 miles of 69 kV line from Madelia Switching Station to Village of Madelia to 336 ACSR | Planned | 1594000 | Scoping | 2015 | MN | 3.6 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-06-01 | Planned | 1594000 | 0% |  | 42
A in MTEP15 | West | XEL | 8097 | 2015-12-28 | 20425 | 2017-03-31 | SUB | 2017-03-01 | Poplar Lake |  |  | 161 |  | Install 161 kV 20 MVAR reactor at Poplar Lake substation | M5_In Service | 1990186 | Scoping | 2015 | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-10-07 | Planned | 2339744 | -14.94% |  | 5
A in MTEP15 | West | XEL | 8107 | 2016-09-01 | 20444 | 2015-05-21 | SUB | 2019-01-01 | Yankee |  |  | 115 | 34.5 | Install a 3rd 115/34.5 kV transformer at Yankee, cut over the Buffalo Ridge feeder 321 and serve from Yankee, add 115 kV breakers at Yankee | Planned | 4000000 | Planning | 2015 | MN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-01-01 | Planned | 4000000 | 0% |  | 0
A in MTEP15 | West | XEL | 8113 | 2015-12-28 | 20449 | 2016-09-29 | SUB | 2018-12-01 | Ward County |  |  | 230 | 115 | New 230/115 kV substation near Minot, ND | Planned | 12186000 | Scoping | 2015 | ND |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 12186000 | 0% |  | 0
A in MTEP15 | West | XEL | 8113 | 2015-12-28 | 20453 | 2016-09-29 | LN | 2018-12-01 | Ward County | McHenry | 1 | 230 |  | New 230 kV line from Ward County - McHenry | Planned | 26775100 | Scoping | 2015 | ND |  | 20 | 500 | 550 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 26775100 | 0% | Portion of substation deferred until expansion by foreign companies is needed. | 0
A in MTEP15 | West | XEL | 8117 | 2015-12-28 | 20471 | 2016-06-30 | LNrb | 2023-09-30 | Ward County | Souris | 1 | 115 |  | Rebuild the 115 kV line between Ward County and Souris | Planned | 7200000 | Scoping | 2015 | ND | 7 |  | 230 | 250 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2023-09-30 | Planned | 7200000 | 0% | This project has been deferred, cost to remain at $7,200,000 as recently reported last quarter. | 0
A in MTEP15 | West | XEL | 8117 | 2015-12-28 | 20473 | 2016-06-30 | LNrb | 2023-09-30 | Ward County | Souris | 2 | 115 |  | Rebuild the 115 kV line between Ward County and Souris | Planned | 7200000 | Scoping | 2015 | ND | 7 |  | 230 | 250 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2023-09-30 | Planned | 7200000 | 0% | This project has been deferred, cost to remain at $7,200,000 as recently reported last quarter. | 0
A in MTEP15 | West | XEL | 8142 | 2015-12-28 | 20508 | 2016-06-30 | TX | 2017-12-01 | Stone Lake |  |  | 161 | 69 | Upgrade 161-69 kV transformer to 112 MVA | Planned | 2227000 | Scoping | 2015 | WI |  |  | 112 | 128 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-01 | Planned | 2227000 | 0% |  | 0
A in MTEP15 | West | XEL | 8149 | 2015-12-28 | 20540 | 2017-06-24 | LN | 2022-12-01 | New Sub (South) | New Sub (North) | 1 | 69 |  | New 69 kV line tapping the existing Stinson - Bayfront 115 kV line to a new substation near Bayfield | Planned | 14500000 | Planning | 2015 | WI |  | 20 |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 14500000 | 0% | Routing is the cause for cost increase. | 48
A in MTEP15 | West | XEL | 8149 | 2015-12-28 | 20541 | 2017-06-24 | SUB | 2022-12-01 | New Sub (South) |  |  | 115 | 69 | New 115/69 kV substation on the Stinson - Bayfront 115 kV line | Planned | 5200000 | Planning | 2015 | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 5200000 | 0% | Routing is the cause for cost increase. | 48
A in MTEP15 | West | XEL | 8149 | 2015-12-28 | 20556 | 2017-06-24 | LNrb | 2022-12-01 | Iron River | Herbster | 1 | 69 |  | Rebuild Iron River - Herbster 34.5 kV to 69 kV using 477 ACSR | Planned | 6500000 | Planning | 2015 | WI | 25 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 6500000 | 0% |  | 48
A in MTEP15 | West | XEL | 8149 | 2015-12-28 | 20560 | 2017-06-24 | SUB | 2022-12-01 | New Sub (North) |  |  | 69 | 34.5 | New 69/34.5 kV line near Bayfield Tap. Includes one 3 MVAR 34.5 kV cap bank. | Planned | 2800000 | Planning | 2015 | WI |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 2800000 | 0% |  | 48
A in MTEP15 | West | XEL | 8149 | 2015-12-28 | 20561 | 2017-06-24 | LNrb | 2022-12-01 | Cornucopia | Bayfield Tap | 1 | 69 |  | Rebuild Cornucopia - Bayfield Tap 34.5 kV to 69 kV using 477 ACSR | Planned | 11000000 | Planning | 2015 | WI | 18 |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-01 | Planned | 11000000 | 0% | Routing is the cause for cost increase. | 48
A in MTEP15 | West | XEL | 8780 | 2015-12-28 | 20798 | 2017-03-13 | SUB | 2018-06-01 | Bailey Road |  |  | 345 | 115 | New substation tapping Red Rock-A.S. King 345 kV line | Withdrawn | 29000000 | Scoping |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 29000000 | 0% |  | 0
A in MTEP15 | West | XEL | 8780 | 2015-12-28 | 20799 | 2017-03-13 | TX | 2018-06-01 | Bailey Road |  | 9 | 345 | 115 | Bailey Road 345/115 transformer #9 | Withdrawn | 5500000 |  |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 5500000 | 0% | The cost for transmission lines upgrade which was a part of the approved project has not been reported before now. The transmission line component was listed in the reporting but without its associated cost. | 0
A in MTEP14 | Central | AmerenIL | 4076 | 2014-12-17 | 7725 | 2016-06-02 | LN | 2017-06-01 | Edwards Plant | ADM-Peoria (Hiram) | 1 | 138 |  | Build new 2.2 miles of 138 kV line wih 2000 A summer emergency capability. Reconnect deenergized 4.6 mile 138 kV line between Edwards Plant and Bartonville Substation. Add two new 138 kV, 2000 A PCBs at Edwards Plant. Relocate 138 kV lines outside Edwa | Planned | 6320000 | Planning |  | IL | 4.6 | 2.2 | 399 | 478 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 6320000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4345 | 2015-01-09 | 8312 | 2016-10-20 | SUB | 2018-12-01 | Gifford Sub |  |  | 138 |  | Establish a new 138 kV, 3-breaker ring bus at the existing Rantoul Junction in the Paxton, East-Sidney-1 138 kV Line | Planned | 4775000 | Engineering |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-05-22 | Planned | 4775000 | 0% |  | -5
A in MTEP14 | Central | AmerenIL | 4471 | 2015-01-09 | 8570 | 2015-04-30 | LN | 2017-12-01 | Cahokia | Dupo Ferry | 1 | 138 |  | Replace 6.98 miles of 2-300 kcmil Copper conductor with largest size conductor existing structures will carry. (Minimum capability of 1600 A) | Planned | 10403000 | Planning |  | IL | 6.98 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 10403000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4474 | 2015-01-09 | 8575 | 2015-09-21 | SUB | 2019-09-01 | Lasalle Tap (Hickok) | Install 138 kV Breaker Station |  | 138 |  | LaSalle Tap 138 kV Breaker Station (Hickok)- Install new 3-position breaker station in the Hennepin-Oglesby-1556 138 kV line at the tap to LaSalle Air Products and North LaSalle Substations. 3-2000A PCBs needed. | Planned | 3800032 | Engineering |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 3800032 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4474 | 2015-01-09 | 8576 | 2015-09-21 | TEQ | 2019-09-01 | Hennepin | Oglesby | 1556 | 138 |  | Upgrade disconnect switch, wave trap, relay limit at Hennepin, and 1200 A disconnect switch at ESK to match line rating. | Planned | 600000 | Planning |  | IL |  |  | 255 | 325 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 600000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4477 | 2015-01-09 | 8582 | 2015-09-21 | SUB | 2019-09-01 | Clayton Junction (Monument) | Install 138 kV Breaker Station |  | 138 |  | Install 138 kV breaker station at Clayton Junction. Needed: 3-2000 A PCBs. | Planned | 4950000 | Engineering |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 4950000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4477 | 2015-01-09 | 8583 | 2015-09-21 | TEQ | 2019-09-01 | Macomb | Monument |  | 138 |  | Upgrade relay limit | Planned |  |  |  | IL |  |  | 175 | 191 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4477 | 2015-01-09 | 8584 | 2015-09-21 | TEQ | 2019-09-01 | East Quincy | Monument |  | 138 |  | Upgrade relay limit | Planned |  |  |  | IL |  |  | 240 | 264 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4477 | 2015-01-09 | 8585 | 2015-09-21 | TEQ | 2019-09-01 | Meredosia East | Monument |  | 138 |  | Upgrade relay limit | Planned |  |  |  | IL |  |  | 240 | 264 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4479 | 2017-02-23 | 8587 | 2016-03-31 | SUB | 2019-09-01 | Ramsey, East | Install 345 kV Ring Bus |  | 345 |  | Install 345 kV ring bus. Needed: 3-3000 A PCBs | Planned | 6000000 | Planning |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-09-01 | Planned | 6000000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4480 | 2017-03-10 | 8588 | 2017-03-10 | SUB | 2020-11-01 | Oglesby | Rebuild Substation |  | 138 |  | Rebuild Oglesby Substation. Utilize a breaker-and-a-half arrangement. | Planned | 14660550 | Planning |  | IL |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-11-01 | Planned | 14660550 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4495 | 2015-01-09 | 8606 | 2016-12-12 | LN | 2016-12-01 | Rivermines | Maries | 1 | 138 |  | Rebuild/reconductor 60 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | M5_In Service | 15500000 | Engineering |  | MO | 60 |  | 269 | 305 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 15500000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4495 | 2015-01-09 | 8607 | 2016-12-12 | LN | 2016-12-01 | Clark | Osage | 2 | 138 |  | Rebuild/reconductor 95 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | M5_In Service | 15500000 | Engineering |  | MO | 95 |  | 269 | 305 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 15500000 | 0% |  | 0
A in MTEP14 | Central | AmerenIL | 4495 | 2015-01-09 | 8608 | 2016-12-12 | LN | 2016-12-01 | Maries | Osage | 1 | 138 |  | Rebuild/reconductor 34.3 miles of 250 kcmil Copper with 556 kcmil ACSS or equivalent. | M5_In Service | 15500000 | Engineering |  | MO | 34.3 |  | 269 | 305 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 15500000 | 0% |  | 0
A in MTEP14 | Central | AmerenMO | 2993 | 2015-01-09 | 5198 | 2017-03-10 | LN | 2018-12-01 | Dupo Ferry | Buck Knob | 1 | 138 |  | Dupo Ferry-Buck Knob 138 kV Line - Replace 22 mi. of 2-300 ACSR with maximum size conductor existing towers will support. | Planned | 31367940 | Engineering |  | MO | 22 |  | 275 | 287 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 31367940 | 0% |  | 0
A in MTEP14 | Central | AmerenMO | 4723 | 2015-01-09 | 8952 | 2014-08-22 | LN | 2017-12-01 | Kelso | Lutesville | 1 | 345 |  | Replace 50% of structures (17.6 miles) to maintain at least a 100 degree C conductor temperature capability on this line. | Planned | 8441336 |  |  | MO | 17.6 |  | 1178 | 1178 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 8441336 | 0% |  | 0
A in MTEP14 | West | ATC | 1624 | 2014-12-17 | 3241 | 2016-09-29 | LN | 2022-06-01 | Portage | Trienda | 2 | 138 |  | Uprate X-67 Portage - Trienda 138-kV | Planned | 2000000 |  |  | WI | 3.4 |  | 294 | 294 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2022-06-01 | Planned | 2000000 | 0% | Cost estimate changed. | 0
A in MTEP14 | West | ATC | 1708 | 2014-12-17 | 3490 | 2017-03-30 | LN | 2017-04-15 | Fairwater | Mackford Prairie | 1 | 69 |  | Construct Fairwater-Mackford Prairie 69 kV line | Planned | 20400000 | Engineering | 2018 | WI |  | 3.5 | 72 MVA | 72 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-01 | Planned | 20400000 | 0% | Change in cost estimate | 3
A in MTEP14 | West | ATC | 1708 | 2014-12-17 | 3491 | 2015-10-19 | LN | 2017-09-26 | Ripon | Metomen | 2 | 69 |  | Reconfigure the North Randolph-Ripon 69-kV line to form a second Ripon-Metomen 69-kV line and retire the circuit between Metomen and the Mackford Prairie tap | Planned |  |  |  | WI | 3.7 |  | 59 MVA | 59 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-09-26 | Planned | 0 | 0% | Cost change due to scope change since last estimate was entered | 0
A in MTEP14 | West | ATC | 2031 | 2014-12-17 | 3906 | 2014-12-23 | LNrb | 2018-06-01 | Colley Rd | Enzyme Bio Systems Tap | 1 | 69 |  | Rebuild Colley Rd-Enzyme Bio Systems Tap (Y-32) 69 kV | Planned | 0 | Engineering | 2018 | WI |  | 0.98 | 92 | 120 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% | Cost change due to scope change since last estimate was entered | 0
A in MTEP14 | West | ATC | 2031 | 2014-12-17 | 3907 | 2015-07-01 | LNrb | 2018-06-01 | Enzyme Bio Systems Tap | RC3 (Clinton) | 1 | 69 |  | Rebuild Enzyme Bio Systems Tap-RC3 (Clinton) 69 kV | Planned | 36968500 | Engineering | 2018 | WI |  | 5.33 | 147 | 201 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 36968500 | 0% | Cost estimate changed. | 0
A in MTEP14 | West | ATC | 2031 | 2014-12-17 | 3908 | 2014-12-23 | LNrb | 2018-06-01 | RC3 (Clinton) | Clinton Tap | 1 | 69 |  | Rebuild RC3 (Clinton)-Clinton Tap 69 kV | Planned | 0 | Engineering | 2018 | WI |  | 1.55 | 147 | 201 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% | Cost change due to scope change since last estimate was entered | 0
A in MTEP14 | West | ATC | 2031 | 2014-12-17 | 3909 | 2014-12-23 | LNrb | 2018-06-01 | Clinton Tap | Sharon Tap | 1 | 69 |  | Rebuild Clinton Tap-Sharon Tap 69 kV | Planned | 0 | Engineering | 2018 | WI |  | 9 | 147 | 201 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% | Cost change due to scope change since last estimate was entered | 0
A in MTEP14 | West | ATC | 2031 | 2014-12-17 | 7694 | 2014-12-23 | LN | 2018-06-01 | Brick church | Sharon Tap | 1 | 69 |  | Rebuild Brick Church to Sharon Tap | Planned | 0 | Engineering | 2018 | WI |  | 3.82 | 123 | 168 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 0 | 0% | Cost change due to scope change since last estimate was entered | 0
A in MTEP14 | West | ATC | 2056 | 2014-12-17 | 3943 | 2017-03-31 | LN | 2016-12-29 | Oak Creek | Pennsylvania | 1 | 138 |  | Uprate Oak Creek-Pennsylvania (837) 138 kV | M5_In Service | 3500000 |  |  | WI | 4.53 |  | 404 | 555 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-31 | M2a_Pre-Project Approval | 4000000 | -12.5% | Cost estimate changed. | -1
A in MTEP14 | West | ATC | 3096 | 2014-12-17 | 5421 | 2017-06-30 | LN | 2019-05-01 | Munising | Timber Products | 1 | 69 |  | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | Planned | 17000000 | Engineering |  | MI | 6.2 |  | 37 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 13000000 | 30.77% | Scope of work has changed since original entry | -19
A in MTEP14 | West | ATC | 3096 | 2014-12-17 | 5422 | 2014-10-17 | LN | 2020-12-31 | Timber Products | Seney | 1 | 69 |  | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | Planned |  | Engineering |  | MI | 28.4 |  | 37 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% | Scope of work has changed since original entry | 0
A in MTEP14 | West | ATC | 3096 | 2014-12-17 | 5423 | 2014-10-17 | LN | 2020-12-31 | Seney | Blaney Park | 1 | 69 |  | Increase ground clearance for the Inland line Munising-Blaney Park 69kV to 167 deg f (37 MVA) clearance | Planned |  | Engineering |  | MI | 18 |  | 37 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 0 | 0% | Scope of work has changed since original entry | 0
A in MTEP14 | West | ATC | 3510 | 2016-09-15 | 6481 | 2016-09-15 | LN | 2019-06-15 | Mukwonago | Edgewood | 1 | 138 |  | 671K61 Mukwonago-Edgewood 138-kV rebuild | Planned | 23121000 | Engineering |  | WI | 7.19 |  | 293 | 321 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-15 | Planned | 23121000 | 0% | Pre-planning cost estimate | 0
A in MTEP14 | West | ATC | 3510 | 2016-09-15 | 6482 | 2016-09-15 | LN | 2019-06-15 | Edgewood | St. Martins | 1 | 138 |  | 3013 Edgewood-St. Martins 138-kV rebuild | Planned | 0 | Engineering |  | WI | 7.07 |  | 287 | 287 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-15 | Planned | 0 | 0% | Pre-planning cost estimate,Pre-planning cost estimate | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7149 | 2015-07-01 | TX | 2019-06-01 | Geneva |  | 1 | 138 | 69 | New Geneva 138-69 kV Transformer | Planned | 12155000 | Planning |  | WI |  |  | 100 | 141 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 12155000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7150 | 2015-07-01 | LNrc | 2019-06-01 | Bain | Spring Valley | 1 | 138 |  | Reconductor Bain-Spring Valley 138 kV line with T2-477 | Planned | 1314000 | Planning |  | WI | 14.45 |  | 293 | 403 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 1314000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7151 | 2015-07-01 | LN | 2019-06-01 | Spring Valley | Geneva | 1 | 138 |  | Construct new Spring Valley-Geneva 138 kV line with T2-477 | Planned | 26567000 | Planning |  | WI | 11.55 |  | 293 | 403 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 26567000 | 0% | Cost estimate. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7152 | 2015-07-01 | LN | 2019-06-01 | Geneva | North Lake Geneva | 1 | 138 |  | Construct new Geneva-North Lake Geneva 138 kV line with T2-477 | Planned | 17420000 | Planning |  | WI | 12.5 |  | 293 | 403 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 17420000 | 0% | Cost Estimate. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7153 | 2015-07-01 | LNrc | 2019-06-01 | Katzenberg | Richmond Road | 1 | 69 |  | Reconductor Katzenberg-Richmond 69 kV line with T2-336 | Planned | 3024000 | Planning |  | WI | 2.6 |  | 116 | 158 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 3024000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7154 | 2015-07-01 | LNrc | 2019-06-01 | Richmond Road | Twin Lakes | 1 | 69 |  | Reconductor Twin Lakes-Richmond 69 kV line with T2-336 | Planned | 2675000 | Planning |  | WI | 2.3 |  | 116 | 158 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 2675000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3808 | 2014-12-17 | 7155 | 2015-07-01 | LN | 2019-06-01 | Twin Lakes | Geneva | 1 | 69 |  | Construct new Twin Lakes-Geneva 69 kV line with T2-336 | Planned | 7391000 | Planning |  | WI | 1 |  | 116 | 158 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 7391000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3890 | 2016-12-30 | 7435 | 2016-12-30 | LN | 2021-12-31 | Port Washington | Saukville | 1 | 138 |  | Reconductor Port Washington-Saukville (762) 138 kV line | Withdrawn | 2284000 | Planning |  | WI |  |  | 319 | 519 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2021-12-31 | Planned | 2284000 | 0% | Cost estimate change | 0
A in MTEP14 | West | ATC | 3891 | 2016-12-30 | 7436 | 2016-12-30 | LN | 2021-12-31 | Port Washington | Saukville | 1 | 138 |  | Reconductor Port Washington-Saukville (742) 138 kV line | Withdrawn | 2843000 | Planning |  | WI |  |  | 319 | 519 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2021-12-31 | Planned | 2843000 | 0% | Change in cost estimate | 0
A in MTEP14 | West | ATC | 3900 | 2014-12-17 | 7450 | 2017-06-30 | LN | 2017-03-31 | Bain | Albers | 1 | 138 |  | Reconductor Bain-Albers (63143) 138 kV line | M5_In Service | 3000000 | Engineering | 2015 | WI | 3.1 |  | 285 | 366 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1300000 | 130.8% | Updated estimate | 3
A in MTEP14 | West | ATC | 3904 | 2014-12-17 | 7457 | 2017-03-30 | LN | 2016-06-10 | McCue | REC Harmony | 1 | 69 |  | Reconductor McCue-REC Harmony (Y-171) 69 kV line | M5_In Service | 3500000 | Engineering | 2016 | WI | 1.36 |  | 88 | 118 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-10 | Planned | 3500000 | 0% | Cost estimate update. | 0
A in MTEP14 | West | ATC | 3904 | 2014-12-17 | 7458 | 2017-03-30 | LN | 2016-06-10 | REC Harmony | Red Hawk Tap | 1 | 69 |  | Reconductor REC Harmony-Red Hawk Tap 69 kV line | M5_In Service |  | Engineering | 2016 | WI | 2.45 |  | 88 | 118 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-10 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 3904 | 2014-12-17 | 8362 | 2017-03-30 | LN | 2016-06-10 | Red Hawk Tap | Lamar | 1 | 69 |  | Reconductor Red Hawk Tap - Lamar 69 kV line | M5_In Service |  | Engineering | 2016 | WI | 0.17 |  | 88 | 118 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-10 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4711 | 2014-12-17 | 8930 | 2017-06-30 | LNrb | 2017-11-09 | Wautoma | A11 Tap | 1 | 69 |  | Rebuild the 13.1 mile portion of Y-17 (WAU-A11 69 kV) with T2 4/0 Penguin. All structures used will allow operation to 200 deg F normal and 300 deg F emergency | Planned | 13600000 | Engineering | 2015 | WI | 13.1 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-10-17 | Planned | 13600000 | 0% | Estimate was in 2009$ | 13
A in MTEP14 | West | ATC | 4711 | 2014-12-17 | 8931 | 2017-03-30 | LNrb | 2017-05-29 | A11 Tap | Montello Tap | 1 | 69 |  | Rebuild the 6.1 mile portion of line Y-17 (A11-MOO 69 kV) with T2 4/0 Penguin. All structures used will allow operation to 200 deg F normal and 300 deg F emergency | Planned |  |  |  | WI | 3.1 |  | 79 | 108 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-10-17 | Planned | 0 | 0% |  | 7
A in MTEP14 | West | ATC | 4728 | 2014-12-17 | 8959 | 2017-06-30 | LNrb | 2017-05-01 | Whitewater | Bluff Creek | 1 | 138 |  | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | M5_In Service | 5075000 | Engineering | 2018 | WI |  | 5.02 | 175 | 229 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 5075000 | 0% | Project scope increase. | -1
A in MTEP14 | West | ATC | 4728 | 2014-12-17 | 8960 | 2015-10-19 | LNrb | 2017-06-01 | University | Mukwanago | 1 | 138 |  | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | Planned |  |  |  | WI |  | 22.7 | 246 | 298 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4728 | 2014-12-17 | 8961 | 2015-10-19 | LNrb | 2017-06-01 | University | Whitewater | 1 | 138 |  | Reconfigure the University area lines of Whitewater - University (4453) 138kV line, Bluff Creek - University (6552) 138kV line and Mukwonago - Whitewater (77353) 138kV line into new lines of Whitewater - University (4453A) 138kV line, Mukwonago - University (77353A) 138kVline and Whitewater - Bluff Creek (6552A) 138kV line | Planned |  |  |  | WI |  | 6.2 | 246 | 304 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4731 | 2014-12-17 | 8966 | 2017-06-30 | SUB | 2016-09-08 | Horicon |  |  | 69 |  | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | M5_In Service | 175000 | Engineering | 2014 | WI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-07-01 | Planned | 210000 | -16.67% | Updated estimate | 2
A in MTEP14 | West | ATC | 4731 | 2014-12-17 | 8967 | 2017-06-30 | LNup | 2016-09-08 | Horicon | Juneau Tap | 1 | 69 |  | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | M5_In Service |  |  |  | WI |  |  | 59 | 59 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-07-01 | Planned | 0 | 0% |  | 2
A in MTEP14 | West | ATC | 4731 | 2014-12-17 | 8968 | 2017-03-31 | LNup | 2016-09-08 | Horicon | Horicon Industrial Park | 1 | 69 |  | Replace the 4/0 Copper Main Strin Bus, Jumpers and lugs. In addition to the 336 ACSR Jumpers, 69 kV station Post insulators and bus support clamps. This will increase the bus & bus jumper ratings that are currently limiters and raise the limit to that of | Planned |  |  |  | WI |  |  | 64 | 94 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-07-01 | Planned | 0 | 0% |  | 2
A in MTEP14 | West | ATC | 4734 | 2014-12-17 | 8976 | 2014-01-10 | TAP | 2015-06-01 | Weston | Cedar Creek | 1 | 115 |  | Loop Weston - Dewey 115kV line into new Cedar Creek substation | Planned |  |  |  | WI |  | 0.25 | 205 | 279 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-06-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4734 | 2014-12-17 | 8977 | 2014-01-10 | TAP | 2015-06-01 | Cedar Creek | Dewey | 1 | 115 |  | Loop Weston - Dewey 115kV line into new Cedar Creek substation | Planned |  |  |  | WI |  | 15.65 | 205 | 279 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-06-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4734 | 2014-12-17 | 8978 | 2015-12-28 | CB | 2015-05-04 | Cedar Creek |  |  | 115 |  | Weston - Cedar Creek 115kV line breaker | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-05-04 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ATC | 4734 | 2014-12-17 | 8979 | 2017-06-29 | CB | 2015-04-29 | Cedar Creek |  |  | 115 |  | Cedar Creek - Dewey 115kV line breaker | M5_In Service | 1906000 |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-05-04 | Planned | 0 | 0% | Updated estimate. | -1
A in MTEP14 | West | ATC | 4734 | 2014-12-17 | 8980 | 2015-12-28 | CB | 2015-05-04 | Cedar Creek |  |  | 115 |  | Cedar Creek 115kV bus tie breaker | Planned |  |  |  | WI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-05-04 | Planned | 2000000 | -100% |  | 0
A in MTEP14 | West | CFU | 4588 | 2014-12-17 | 8730 | 2017-06-14 | SUB | 2017-06-01 | University Ave. | Transformer |  | 161 | 69 | New Substation | M5_In Service | 5398000 |  |  | IA |  |  | 143 MVA | 143 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-01 | Under Construction | 5398000 | 0% | Property acquisition costs were higher than originally estimated. | 2
A in MTEP14 | West | CFU | 4588 | 2014-12-17 | 8731 | 2017-06-14 | LN | 2017-06-01 | University Ave | GT to GH tap | 6915 | 69 |  | 69kV Line and 3 way switch | M5_In Service | 1800000 |  |  | IA |  | 1.3 | 143 MVA |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-01 | M4_Pre-Construction | 1536500 | 17.15% | Substation site location has changed resulting in higher transmission line costs. Also an engineering firm was hired in Q4 2014 to provide a more detailed cost estimate and begin preliminary engineering for the project. | 2
A in MTEP14 | West | CFU-PMEU | 4386 | 2015-11-03 | 8402 | 2015-11-03 | SUB | 2017-04-01 | Pella West |  |  | 69 |  | Reconfiguration of Pella West 69 kV Substation to improve load serving reliability for City of Pella. Substation will be reconfigured from a line breaker to a ring bus scheme. | Planned | 2360335 | Planning | 2013 | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-01 | Planned | 2360335 | 0% |  | 0
A in MTEP14 | Central | DEI | 3545 | 2014-12-17 | 6614 | 2016-11-04 | SUB | 2016-10-01 | Wabash River Sta. |  |  | 138 |  | Wabash Riv 138KV Gen Sta. Phase II (Bus #2 & Transfer Bus): Perform Line associated relay work. Repl. breakers: 138230-9, 13847 and DS Switches. Replace Bus Insulators. | M5_In Service | 1434000 | Engineering | 2013 | IN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 1434000 | 0% |  | -2
A in MTEP14 | Central | DEI | 3550 | 2016-08-03 | 6619 | 2016-08-03 | LN | 2017-12-31 | Martinsville Southeast | Martinsville E. | 1 | 69 |  | Construct approximately 1.5 mi of 69kv line to complete a normally open loop between Martinsville SE and Martinsville East distribution subs. | M4_Pre-Construction | 1434000 | Engineering | 2011 | IN |  | 1.5 | 153 | 153 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | M4_Pre-Construction | 1434000 | 0% |  | 0
A in MTEP14 | Central | DEI | 3556 | 2014-12-17 | 6629 | 2017-02-09 | Dist | 2016-12-31 | Greenwood South | new distribution sub |  | 69 | 12 | Build a new 69-12kV 22.4MVA sub in the 69102 line adjacent +/- to the existing HE Gilmore 69kv sub | M5_In Service | 481000 | Engineering | 2013 | IN |  |  |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 481000 | 0% |  | 0
A in MTEP14 | Central | DEI | 4368 | 2015-01-09 | 8363 | 2017-04-11 | LN | 2017-03-31 | Dresser | Wabash River Gen. Station | 1 | 138 |  | Build a new 138kV line from Dresser to Wabash River Gen. Station with 2000A terminal equipment and 954ACSS - 200C conductor; approx. 10 miles | M5_In Service | 34890000 | Engineering | 2013 | IN |  | 10 | 478 | 478 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-03-31 | Under Construction | 14500000 | 140.6% | higher than anticipated costs due to rough terrain, ROW legal costs, material cost increases, several adjacent circuits had to be relocated and were not originally estimated | 0
A in MTEP14 | Central | DEI | 4402 | 2015-01-09 | 8419 | 2016-12-16 | LNrb | 2017-06-01 | Huntington Riverfork | Huntington State St. |  | 69 |  | Huntington Riverfork to State St 69143 ckt: Reconductor 2.85 miles of 69kV transmission 2/0 Cu to 477 ACSR conductor. Begin about half mile east of Hunt Riv Fk sub at pole 823-6512 and continue to Hunt State St Sub 69kv bus. Also reconductor 4/0 ACSR river span. | Under Construction | 2520282 | Engineering | 2014 | IN | 2.85 |  | 100 | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2520282 | 0% |  | 6
A in MTEP14 | Central | DEI | 4408 | 2015-01-09 | 8425 | 2016-12-05 | LNrb | 2016-10-25 | Huntington 138 | Huntington State St |  | 69 |  | Reconductor 2.5 miles of the 69143 ckt from Huntington 138 sub to State St with 477ACSR @ 100C | M5_In Service | 2600000 | Engineering | 2013 | IN | 2.5 |  | 100 | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 2600000 | 0% |  | -2
A in MTEP14 | Central | DEI | 4411 | 2015-01-09 | 8430 | 2017-06-02 | LNrb | 2017-12-01 | Bloomington Meadow Pk | HE Brummett Crk Jct |  | 69 |  | AMIN0865 - Reconductor 6991 ckt from Bloomington Meadow Pk to HE Brummett Crk Jct - 1.6 miles of 954ACSS@200C | Under Construction | 1843000 | Engineering | 2013 | IN | 1.6 |  | 154 | 174 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 1843000 | 0% |  | 12
A in MTEP14 | Central | DEI | 4414 | 2015-01-09 | 8433 | 2017-06-02 | LN | 2017-08-01 | Chippewa | New 69132 Jct |  | 69 |  | New N.O. alternate 69kv feed from 69132 ckt over to Wabash Chippewa 69kv sub | Under Construction | 2244000 | Engineering | 2013 | IN |  | 4.5 | 100 | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2244000 | 0% |  | 8
A in MTEP14 | Central | DEI | 4415 | 2015-01-09 | 8434 | 2014-09-23 | TX | 2020-06-01 | Veedersburg West | xmr addition |  | 230 | 69 | Veedersburg West: Add 75MVA 230/69 Bk 2 with LTC at Veedersburg West sub; add breaker to 69kV ring bus and tie in new bank; convert 230kV bus into 4-breaker ring | M1_Final SPM or OOC | 3509000 | Engineering | 2013 | IN |  |  | 75 | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-06-01 | M1_Final SPM or OOC | 3509000 | 0% |  | 0
A in MTEP14 | Central | DEI | 4417 | 2015-01-09 | 8436 | 2017-03-08 | CB | 2017-12-31 | Pumpkin Center | brkr replacements |  | 69 |  | Pumpkin Center: Replace OCB 6952, OCB 69123, OCB 69230, (1) Ground Switch, (2) 230KV ABS and Motor Mechs, Lightning Arrestors, Line & Bus Pots, (7) 69KV Disconnect Switches and Station Service Transformer. Replace the 230kV Bk1 "230-69" Circuit Switcher w | M4_Pre-Construction | 2424000 | Engineering | 2013 | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 2424000 | 0% |  | 0
A in MTEP14 | Central | DEI | 4418 | 2015-01-09 | 8437 | 2017-06-02 | SUB | 2017-09-01 | Hillsdale North | new sub |  | 230 | 69 | Construct new Hillsdale North 230-69kV substation to be inserted in the 23003 ckt with high and low side ring buses, 1-200MVA bank, 2-69kv line terminals. Loop the existing 6906 ckt through. Change Normal Operational status to Open between Hillsdale Sw. S | Under Construction | 12300000 | Planning | 2014 | IN |  | 2 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 12300000 | 0% | Estimate type changed from Planning to Engineering w/ AFUDC - more detailed estimate. | 3
A in MTEP14 | South | Entergy-AR | 4751 | 2014-12-17 | 9019 | 2017-06-27 | CB | 2018-06-01 | Jacksonville North 115 kV substation |  |  | 115 |  | Upgrade Circuit Breaker: Jacksonville North 115 kV B3621-CBO | Under Construction |  |  |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 279164 | -100% | Scoping identified more cost needed. | 18
A in MTEP14 | South | Entergy-AR | 4755 | 2015-09-10 | 9023 | 2017-06-07 | TEQ | 2017-06-01 | ISES 500 kV substation |  |  | 500 |  | EAI SPOF Projects: Modify relaying at ISES 500/161 kV | M5_In Service | 14731461 | Scoping |  | AR |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | Under Construction | 16215941 | -9.154% |  | 0
A in MTEP14 | South | Entergy-AR | 4756 | 2015-09-10 | 9024 | 2016-12-16 | TEQ | 2016-12-30 | Mabelvale 500 kV Substation |  |  | 500 |  | EAI SPOF Projects: Modify relaying at Mabelvale 500 kV | M5_In Service | 7848983 | Scoping |  | AR |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 8013145 | -2.049% |  | 0
A in MTEP14 | South | Entergy-AR | 4757 | 2015-09-10 | 9025 | 2017-06-23 | TEQ | 2018-06-01 | El Dorado 500 kV substation |  |  | 500 |  | EAI SPOF Projects: Modify relaying at El Dorado 500 kV | Planned | 780239 | Scoping |  | AR |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1000000 | -21.98% | revised scoping. | 0
A in MTEP14 | South | Entergy-AR | 7761 | 2016-02-16 | 20072 | 2017-06-23 | CAP | 2017-06-30 | Datto |  |  | 161 |  | 24 MVAR capacitor bank | Under Construction | 1109087 | Planning |  | AR |  |  | 24 MVAR |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 1522059 | -27.13% | Schedule uncertainty | 6
A in MTEP14 | South | Entergy-AR | 8040 | 2015-09-10 | 20313 | 2017-06-23 | TEQ | 2018-06-01 | ANO 500kV substation | Mabelvale 500kV substation | 1 | 500 |  | ANO - Mabelvale 500kV: Replace Substation Equipment | Under Construction | 1611379 | Planning |  | AR |  |  | 2546 | 2546 | Other |  | Economic | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1809881 | -10.97% | budget changes | 0
A in MTEP14 | South | Entergy-AR | 8041 | 2015-09-10 | 20314 | 2017-05-08 | TEQ | 2017-12-01 | ANO 500kV substation | Pleasant Hill 500kV substation | 1 | 500 |  | ANO - Pleasant Hill 500kV: Replace Substation Equipment | M5_In Service | 1203715 | Planning w/AFUDC |  | AR |  |  | 2546 | 2546 | Other |  | Economic | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 1431807 | -15.93% | Scoping and Design certainty | 0
A in MTEP14 | South | Entergy-LA | 4605 | 2015-07-30 | 8751 | 2017-06-22 | TX | 2017-06-20 | Crown Zellerbach 230 kV substation | Crown Zellerbach 138 kV substation | 1 | 230 | 138 | Add transformer | M5_In Service | 19063731 | Planning |  | LA |  |  | 300 MVA | 300 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-09-01 | Planned | 17190728 | 10.9% | Design and scoping | -3
A in MTEP14 | South | Entergy-LA | 4605 | 2015-07-30 | 8752 | 2017-06-22 | SUB | 2017-06-20 | Crown Zellerbach 230 kV substation |  |  | 230 |  | Construct new substation | M5_In Service |  |  |  | LA |  |  | 300 MVA | 300 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-09-01 | Planned | 0 | 0% |  | -3
A in MTEP14 | South | Entergy-LA | 4605 | 2015-07-30 | 8753 | 2017-06-22 | SUB | 2017-06-20 | Crown Zellerbach 138 kV substation |  |  | 138 |  | Construct new substation | M5_In Service |  |  |  | LA |  |  | 300 MVA | 300 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-09-01 | Planned | 0 | 0% |  | -3
A in MTEP14 | South | Entergy-LA | 4761 | 2014-12-17 | 9029 | 2017-06-22 | SUB | 2018-04-25 | Willow Glen 500 kV substation |  |  | 500 |  | EGSL SPOF Projects: Modify relaying at Willow Glen 500 kV | Under Construction | 5117906 | Planning |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2018-04-25 | Under Construction | 6003861 | -14.76% | Scoping | 0
A in MTEP14 | South | Entergy-LA | 4762 | 2014-12-17 | 9030 | 2017-06-22 | SUB | 2018-06-01 | Fancy Point 500kV substation |  |  | 500 |  | EGSL SPOF Projects: Modify relaying at Fancy Point 500kV | Planned | 434616 | Planning |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 440111 | -1.249% |  | 0
A in MTEP14 | South | Entergy-LA | 4763 | 2014-12-17 | 9031 | 2017-03-23 | CB | 2016-11-08 | Jaguar 69 kV substation |  |  | 69 |  | Upgrade Circuit Breaker: Jaguar 69 kV 20940-CO | M5_In Service | 670586 |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 970497 | -30.9% |  | -1
A in MTEP14 | South | Entergy-LA | 4764 | 2014-12-17 | 9032 | 2017-03-23 | CB | 2016-11-08 | Jaguar 69 kV substation |  |  | 69 |  | Upgrade Circuit Breaker: Jaguar 69 kV 20905-CO | M5_In Service |  |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | -1
A in MTEP14 | South | Entergy-LA | 4765 | 2014-12-17 | 9033 | 2017-03-23 | CB | 2016-12-09 | Blount 69 kV substation |  |  | 69 |  | Upgrade Circuit Breaker: Blount 69 kV 14105-TC | M5_In Service |  |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | 0
A in MTEP14 | South | Entergy-LA | 4769 | 2014-12-17 | 9037 | 2017-06-22 | SUB | 2017-05-15 | Schriever230 kV substation |  |  | 230 |  | Construct new substation | M5_In Service | 11388167 | Planning |  | LA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-03-31 | Planned | 13443939 | -15.29% | Cost adjusted during scoping | 2
A in MTEP14 | South | Entergy-LA | 4770 | 2014-12-17 | 9038 | 2017-03-23 | CB | 2016-11-04 | Waterford 230 kV substation |  |  | 230 |  | Upgrade Circuit Breaker: Waterford 230 kV S7145-CO | M5_In Service | 655262 | Planning |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1082400 | -39.46% | Outage | -1
A in MTEP14 | South | Entergy-LA | 4771 | 2014-12-17 | 9039 | 2017-03-23 | CB | 2016-11-04 | Waterford 230 kV substation |  |  | 230 |  | Upgrade Circuit Breaker: Waterford 230 kV S7154-CO | M5_In Service |  |  |  | LA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | -1
A in MTEP14 | South | Entergy-LA | 4773 | 2014-12-17 | 9041 | 2017-06-22 | TEQ | 2017-12-31 | Ninemile 230 kV |  |  | 230 |  | ELL SPOF Projects: Modify relaying at Ninemile 230 kV | Under Construction | 4389611 | Planning |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2017-03-01 | Under Construction | 4036969 | 8.735% | overrun | 9
A in MTEP14 | South | Entergy-LA | 4774 | 2014-12-17 | 9042 | 2017-06-22 | TEQ | 2017-12-31 | Southport 230 kV |  |  | 230 |  | ELL SPOF Projects: Modify relaying at Southport 230 kV | Under Construction |  |  |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2017-04-01 | Under Construction | 0 | 0% |  | 8
A in MTEP14 | South | Entergy-LA | 4775 | 2014-12-17 | 9043 | 2017-06-22 | TEQ | 2017-12-31 | Labarre 230 kV |  |  | 230 |  | ELL SPOF Projects: Modify relaying at Labarre 230 kV | Under Construction |  |  |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2017-06-01 | Under Construction | 0 | 0% |  | 6
A in MTEP14 | South | Entergy-LA | 4776 | 2014-12-17 | 9044 | 2017-03-23 | TEQ | 2017-03-13 | Harrahan 230 kV |  |  | 230 |  | ELL SPOF Projects: Modify relaying at Harrahan 230 kV | M5_In Service |  |  |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2017-02-01 | Under Construction | 0 | 0% |  | 1
A in MTEP14 | South | Entergy-LA | 4778 | 2014-12-17 | 9046 | 2017-06-22 | TEQ | 2017-12-31 | Market Street 230 kV |  |  | 230 |  | ELL SPOF Projects: Modify relaying at Market Street 230 kV | Under Construction |  |  |  | LA |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2016-11-01 | Under Construction | 0 | 0% |  | 13
A in MTEP14 | South | Entergy-LA | 8284 | 2014-12-17 | 20630 | 2017-06-22 | TAP | 2018-12-31 | Tap | Panama |  | 230 |  | Tap the Bagatelle - Sorrento line into Panama substation | M3_Long Lead Materials |  |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 4145539 | -100% | Cost adjusted during scoping | 0
A in MTEP14 | South | Entergy-LA | 8284 | 2014-12-17 | 20632 | 2017-06-26 | LN | 2018-12-31 | Richardson | Iberville |  | 230 |  | Construct line using 1780 ACSR ~ 11.0 mi. | Planned | 68432055 |  |  | LA |  | 11 |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 39380000 | 73.77% | Updated information | 0
A in MTEP14 | South | Entergy-LA | 8284 | 2014-12-17 | 20633 | 2017-06-22 | TX | 2017-12-01 | Coly |  |  | 500 | 230 | Add second 1200 MVA, 500-230 kV autotransformer at Coly | Under Construction |  |  |  | LA |  |  |  |  | Other |  | Economic | N | N | Y | Bottom-Up | A | 2017-12-01 | Planned | 16670976 | -100% | Cost adjusted during scoping | 0
A in MTEP14 | South | Entergy-MS | 4614 | 2015-09-10 | 8767 | 2017-06-22 | LN | 2017-10-31 | Franklin 115 kV substation | McComb 115 kV substation |  | 115 | 115 | Construct new line | Under Construction | 30560946 |  |  | MS |  | 25 | 398 MVA | 398 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Planned | 33412348 | -8.534% | Scoping still underway. Normal small % cost increase as routing is finalized. | -1
A in MTEP14 | South | Entergy-MS | 4614 | 2015-09-10 | 8768 | 2017-03-22 | CB | 2017-10-31 | Franklin 115 kV substation | McComb 115 kV substation |  | 115 |  | Add substation terminals | Under Construction |  |  |  | MS |  |  | 398 MVA | 398 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-11-15 | Planned | 0 | 0% |  | -1
A in MTEP14 | South | Entergy-MS | 4788 | 2014-12-17 | 9056 | 2016-12-15 | CB | 2016-03-23 | Rex Brown 115 kV substation |  |  | 115 |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9732-CO | M5_In Service |  |  |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | -9
A in MTEP14 | South | Entergy-MS | 4789 | 2014-12-17 | 9057 | 2017-06-26 | CB | 2017-05-16 | Rex Brown 115 kV substation |  |  | 115 |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9742-CO | M5_In Service |  |  |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | 5
A in MTEP14 | South | Entergy-MS | 4790 | 2014-12-17 | 9058 | 2017-06-26 | CB | 2017-05-16 | Rex Brown 115 kV substation |  |  | 115 |  | Upgrade Circuit Breaker: Rex Brown 115 kV J9743-CO | M5_In Service |  |  |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | 5
A in MTEP14 | South | Entergy-MS | 4793 | 2014-12-17 | 9061 | 2016-12-15 | CB | 2016-11-21 | Greenville 115 kV substation |  |  | 115 |  | Upgrade Circuit Breaker: Greenville 115 kV J9940-CO | M5_In Service |  |  |  | MS |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | -1
A in MTEP14 | West | GRE | 2600 | 2014-12-17 | 4611 | 2016-12-29 | LN | 2016-10-25 | Big Sandy | Big Sandy Tap | 1 | 69 |  | New Distribution | M5_In Service | 4239175 | Planning |  | MN |  | 4 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2016-09-23 | Planned | 4239175 | 0% |  | 1
A in MTEP14 | West | GRE | 4379 | 2016-05-10 | 8391 | 2016-12-29 | LN | 2017-06-05 | Quarry | West St. Cloud | 1 | 115 |  | Build new line from Quarry to West St. Cloud | Planned | 3250000 | Planning |  | MN |  |  | 190 | 190 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-13 | Planned | 3250000 | 0% |  | 2
A in MTEP14 | West | GRE | 4379 | 2016-05-10 | 8392 | 2016-12-29 | SUB | 2017-06-05 | West St. Cloud |  |  | 115 |  | Install 115 kV breaker and half layout at West St. Cloud | Planned | 4000000 | Planning |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-13 | Planned | 4000000 | 0% |  | 2
A in MTEP14 | West | GRE-WMU | 4380 | 2015-01-09 | 8394 | 2016-09-15 | SUB | 2019-05-01 | Priam |  |  | 115 | 69 | Move Willmar 115/69 kV transformer to new Priam 115 kV substation | Planned | 3000000 | Planning |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-05-01 | Planned | 3000000 | 0% |  | 0
A in MTEP14 | West | GRE-WMU | 4380 | 2015-01-09 | 8395 | 2016-09-15 | LN | 2019-05-01 | Priam | Pennock/Willmar Waste Water | 1 | 69 |  | Establish 69 kV outlets from Priam | Planned | 1000000 | Planning |  | MN |  | 1.5 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-05-01 | Planned | 1000000 | 0% |  | 0
A in MTEP14 | Central | HE | 4714 | 2015-01-09 | 8940 | 2013-11-07 | TX | 2014-05-15 | 07Ratts 138/161 kV | 07Ratts8 138/161 kV | 1 | 161 | 138 | Replace Ratts AT3 | Planned | 3500000 | Engineering |  | IN |  |  | 322 | 400 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2014-05-15 | Planned | 3500000 | 0% |  | 0
A in MTEP14 | Central | HE | 4715 | 2015-01-09 | 8941 | 2013-11-07 | LNrc | 2014-05-15 | 07Ratts8 | 07Rattap | 1 | 138 |  | Reconductor 138 kV line | Planned | 200000 | Engineering |  | IN | 0.1 |  | 327 | 327 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2014-05-15 | Planned | 200000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4455 | 2014-12-17 | 8521 | 2015-06-30 | LN | 2016-12-31 | DAEC Tap | DAEC | 1 | 34 |  | Rebuild the line to 69kV standards for furture conversion. | Planned | 2674264 | Planning |  | IA | 3.32 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 2674264 | 0% | Cost estimate now includes the terminal conversion costs. | 0
A in MTEP14 | West | ITCM | 4456 | 2014-12-17 | 8523 | 2016-06-28 | SUB | 2020-12-31 | East Nevada Street | Substation | 1 | 34 |  | Add two 69kV breakers at the East Nevada distribution sub to allow for 69kV conversion. | Planned | 400000 | Planning |  | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 400000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4459 | 2014-12-17 | 8529 | 2016-06-28 | LN | 2018-12-31 | Rome REC | Rome REC Tap |  | 69 |  | Build a new 69kV line from Rome REC back to the present line. | Planned | 1080000 | Planning |  | IA | 2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1080000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4459 | 2014-12-17 | 8530 | 2016-06-28 | LN | 2018-12-31 | Clarence | Clarence REC |  | 69 |  | Build a new 69kV line from Clarence to Clarence REC | Planned | 1080000 | Planning |  | IA | 2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1080000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4459 | 2014-12-17 | 8531 | 2015-12-30 | LN | 2018-12-31 | New Liberty | New Liberty Tap |  | 69 |  | Build a new 69kV line from New Liberty back to the present line. | Planned | 1080000 | Planning |  | IA | 2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1080000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4459 | 2014-12-17 | 8532 | 2016-06-28 | LN | 2018-12-31 | Marion | Amber |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 1200000 | Planning |  | IA |  |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1200000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4461 | 2014-12-17 | 8537 | 2016-11-11 | SUB | 2016-08-31 | Marion | 34kV circuit |  | 69 |  | Convert the Marion Plant 34kV circuit to 69kV operation | M5_In Service | 1841957 | Planning |  | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-09-03 | Under Construction | 1841957 | 0% | Planning estimate replaced with Engineering estimate. Overall cost did not go up they were just split differently than originally submitted between facilities 8537 & 8538. | -1
A in MTEP14 | West | ITCM | 4462 | 2014-12-17 | 8539 | 2015-12-30 | SUB | 2021-12-30 | Victor Switching | Substation |  | 69 | 34 | ITC will add two 69kV breakers and a 69/34kV transformer at the new Victor substation. | Planned | 3000000 | Planning |  | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-30 | Planned | 3000000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8540 | 2015-12-30 | LN | 2019-12-31 | Fletcher | Green Mountain |  | 69 |  | Retire the 34kV line terminal out of Marshalltown and route the line to the new Fletcher 69kV bus built adjacent to Marshalltown. Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 240000 | Planning |  | IA | 6.84 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 240000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8541 | 2015-12-30 | LN | 2019-12-31 | Conrad | Green Mountain |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 0 | Planning |  | IA | 11.15 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8542 | 2015-12-30 | LN | 2019-12-31 | Conrad | Union |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 0 | Planning |  | IA | 12.65 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8543 | 2015-12-30 | LN | 2019-12-31 | CB Union | Union |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 0 | Planning |  | IA | 1.05 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8544 | 2015-12-30 | LN | 2019-12-31 | Otter Creek | CB Union |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 0 | Planning |  | IA | 10.01 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ITCM | 4463 | 2014-12-17 | 8545 | 2015-12-30 | LN | 2019-12-31 | Otter Creek | Hubbard Pump Tap |  | 69 |  | Convert the 34kV line, already built for 69kV, to 69kV operation. | Planned | 0 | Planning |  | IA | 14.17 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | ITCM | 4465 | 2014-12-17 | 8553 | 2016-10-05 | LN | 2016-09-30 | Toledo | Belle Plaine |  | 161 |  | Convert the 115kV line, already built for 161kV, to 161kV operation. | M5_In Service |  | Planning |  | IA | 16.5 |  | 327 MVA | 327 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | -3
A in MTEP14 | West | ITCM | 4465 | 2014-12-17 | 8554 | 2016-10-05 | LN | 2016-09-30 | Belle Plaine | Stoney Point |  | 161 |  | Convert the 115kV line, already built for 161kV, to 161kV operation. | M5_In Service |  | Planning |  | IA | 27.25 |  | 327 MVA | 327 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | -3
A in MTEP14 | West | ITCM | 4465 | 2014-12-17 | 8557 | 2016-10-05 | SUB | 2016-09-30 | Belle Plaine | Substation |  | 161 |  | Convert sub to 161kV operation. | M5_In Service | 100000 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 100000 | 0% |  | -3
A in MTEP14 | West | ITCM | 4465 | 2014-12-17 | 8558 | 2016-10-05 | SUB | 2016-09-30 | Stoney Point | Substation |  | 161 |  | Move the 6th Street 161/115kV transfomrer to Stoney Point and retire the 6th Street 161/115kV transformers. Convert sub to 161kV operation. | M5_In Service | 1000000 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 1000000 | 0% |  | -3
A in MTEP14 | West | ITCM | 4467 | 2014-12-17 | 8560 | 2017-03-07 | LN | 2019-12-31 | Oelwein | Fairbank |  | 69 |  | Rebuild 5.5 miles of the Oelwein-Fairbank 69kV line. | Planned | 5492400 | Planning |  | IA | 5.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 2805000 | 95.81% | Updated planning estimate with engineering estimate in 2016 dollars instead of 2014 dollars. Line needs to be relocated to other side of the roadway causing increase costs to obtain new easements. | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8904 | 2017-06-30 | LN | 2021-05-04 | Blairstown Tap | Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 1170000 | Planning |  | IA | 2.6 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-05-03 | Planned | 1170000 | 0% |  | 36
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8905 | 2016-06-30 | LN | 2018-04-27 | Williamsburg East | Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 1170000 | Planning |  | IA | 2.6 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-04-27 | Planned | 1170000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8906 | 2016-06-30 | LN | 2018-05-04 | Willamsbug South | Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 1350000 | Planning |  | IA | 3 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-05-04 | Planned | 1350000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8907 | 2016-06-30 | LN | 2018-05-24 | Koszta REC Tap | Belle Plaine Jct | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 2565000 | Planning |  | IA | 5.7 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-05-24 | Planned | 2565000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8908 | 2016-06-30 | LN | 2018-03-16 | Willaimsburg South | Parnell | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 6750000 | Planning |  | IA | 15 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-03-16 | Planned | 6750000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8909 | 2016-06-30 | LN | 2018-02-09 | Belle Plaine Jct | City of Belle Plaine | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 2160000 | Planning |  | IA | 4.8 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-02-09 | Planned | 2160000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8910 | 2016-06-30 | LN | 2021-12-31 | Benco | Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 706500 | Planning |  | IA | 1.57 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | Planned | 706500 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8911 | 2016-06-30 | LN | 2020-12-31 | Belle Plaine Jct | Vining REC Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 5706000 | Planning |  | IA | 12.68 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 5706000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8912 | 2017-06-30 | LN | 2018-05-31 | Vining REC Tap | Tama East | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 4783500 | Planning |  | IA | 10.63 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-07-29 | Planned | 4783500 | 0% |  | 10
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8913 | 2016-06-30 | LN | 2018-05-03 | Ferguson | Timber Creek Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 1687500 | Planning |  | IA | 3.75 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-05-03 | Planned | 1687500 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8914 | 2016-06-30 | LN | 2019-05-03 | Sutherland | LeGrand | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 2821500 | Planning |  | IA | 6.27 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-05-03 | Planned | 2821500 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8915 | 2016-06-30 | LN | 2020-12-31 | Traer | Dysart | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 3726000 | Planning |  | IA | 8.28 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | Planned | 3726000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8916 | 2016-06-30 | LN | 2018-02-16 | Ferguson REC Tap | Gilman Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 1687500 | Planning |  | IA | 3.75 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-02-16 | Planned | 1687500 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8917 | 2016-06-30 | LN | 2018-08-03 | Hills | Frytown | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 4986000 | Planning |  | IA | 11.08 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-08-03 | Planned | 4986000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8918 | 2016-06-30 | LN | 2018-08-03 | Frytown Tap | Kalona South Tap | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 2709000 | Planning |  | IA | 6.02 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-08-03 | Planned | 2709000 | 0% |  | 0
A in MTEP14 | West | ITCM | 4704 | 2014-12-17 | 8919 | 2016-06-30 | LN | 2019-09-02 | Kalona South Tap | Iowa Jct | 1 | 34 |  | Rebuild 34kV to 69kV statandards and continue to operate at 34kV | Planned | 2212000 | Planning |  | IA | 4.92 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-09-02 | Planned | 2212000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4499 | 2016-10-21 | 8618 | 2017-06-28 | CAP | 2017-08-01 | Tuscola |  |  | 120 |  | Install a 33.3 MVAR capacitor at the Tuscola 120 kV station. | Under Construction | 1350000 | Engineering | 2014 | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-03-31 | M4_Pre-Construction | 1350000 | 0% |  | 5
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8619 | 2017-05-18 | SwSta | 2018-04-30 | Carrigan |  |  | 120 |  | Construct a new 4-breaker 120 kV switching station named "Carrigan" in the Thumb area. Loop the Lee - Menlo & Wabash - Yuma 120 kV circuits into Carrigan. | M3_Long Lead Materials | 4930000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 4930000 | 0% | Cost estimate refined as engineering level estimate. | 4
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8620 | 2017-05-18 | LNrb | 2018-04-30 | Lee | Menlo | 1 | 120 |  | Replace the existing structures from a one-mile segment of the Lee - Menlo 120 kV circuit with double circuit structures and install 954 ACSR on both sides. | M3_Long Lead Materials | 1700000 | Engineering |  | MI | 1 | 1 | 305 MVA | 349 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 1700000 | 0% | Estimate updated to include land acquisition costs. | 4
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8621 | 2017-05-18 | LNup | 2018-04-30 | Carrigan | Lake Huron Pumping 1 Tap | 1 | 120 |  | New line created by looping the Menlo - Lake Huron Pumping 1 Tap (to Lee) circuit into Carrigan and associated relay upgrades | M3_Long Lead Materials | 275000 | Engineering |  | MI |  |  | 305 MVA | 349 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 275000 | 0% | Cost estimate refined as engineering level estimate. | 4
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8622 | 2017-05-18 | LNup | 2018-04-30 | Carrigan | Menlo | 1 | 120 |  | New line created by looping the Menlo - Lake Huron Pumping 1 Tap (to Lee) circuit into Carrigan and associated relay upgrades | M3_Long Lead Materials | 210000 | Engineering |  | MI |  |  | 134 MVA | 150 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 210000 | 0% | Estimate updated to include land acquisition costs. | 4
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8623 | 2017-05-18 | LNup | 2018-04-30 | Carrigan | Wabash | 1 | 120 |  | New line created by looping the Wabash - Yuma 120 kV circuit into Carrigan and associated relay upgrades. | M3_Long Lead Materials | 265000 | Engineering |  | MI |  |  | 274 MVA | 343 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 265000 | 0% | Cost estimate refined as engineering level estimate. | 4
A in MTEP14 | East | ITCT | 4500 | 2017-05-18 | 8624 | 2017-05-18 | LNup | 2018-04-30 | Carrigan | Yuma | 1 | 120 |  | New line created by looping the Wabash - Yuma 120 kV circuit into Carrigan. | M3_Long Lead Materials |  |  |  | MI |  |  | 134 MVA | 152 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 4
A in MTEP14 | East | ITCT | 4518 | 2016-11-07 | 8649 | 2016-11-07 | TX | 2019-12-31 | Monroe 345/120 kV Transformer 304 |  | 4 | 345 | 120 | Replace the 345/120 kV Transformer 304 at Monroe. | M3_Long Lead Materials | 3800000 | Engineering |  | MI |  |  | 649 MVA | 791 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-01 | M3_Long Lead Materials | 3800000 | 0% |  | 32
A in MTEP14 | East | ITCT | 4519 | 2017-01-11 | 8650 | 2017-01-11 | LN | 2040-04-01 | Custer | Monroe | 2 | 120 |  | Reconfigure the Custer ? Whiting 120 kV line into Monroe to create the Custer ? Monroe 2 120 kV and Monroe ? Whiting 120 kV lines. | Withdrawn | 12300000 | Engineering |  | MI |  | 2.9 | 204 MVA | 269 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2040-04-01 | M2a_Pre-Project Approval | 12300000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4519 | 2017-01-11 | 8651 | 2017-01-11 | LN | 2040-04-01 | Monroe | Whiting | 1 | 120 |  | Reconfigure the Custer ? Whiting 120 kV line into Monroe to create the Custer ? Monroe 2 120 kV and Monroe ? Whiting 120 kV lines. | Withdrawn |  |  |  | MI |  | 2.9 | 204 MVA | 269 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2040-04-01 | M2a_Pre-Project Approval | 0 | 0% |  | 0
A in MTEP14 | East | ITCT | 4529 | 2017-03-29 | 8671 | 2017-03-29 | LNup | 2017-12-31 | Brownstown | Elm | 1 | 230 |  | Remediate the sag limit on the Brownstown to Elm 230kV line up to its conductor rating | M4_Pre-Construction | 485000 | Engineering |  | MI |  |  | 743 MVA | 851 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 485000 | 0% |  | 12
A in MTEP14 | East | ITCT | 4530 | 2017-03-29 | 8672 | 2017-03-29 | LNup | 2017-12-31 | Brownstown | Navarre | 2 | 230 |  | Remediate the sag limit on the Brownstown to Navarre #2 230kV line up to a higher sag limit | M4_Pre-Construction | 290000 | Engineering |  | MI |  |  | 739 MVA | 739 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 290000 | 0% |  | 12
A in MTEP14 | East | ITCT | 4531 | 2016-12-20 | 8673 | 2016-12-20 | LNup | 2017-09-30 | Dorset | Milan | 1 | 120 |  | Remediate the sag limit on the Dorset to Milan 120kV line up to its conductor rating | M4_Pre-Construction | 225000 | Engineering |  | MI |  |  | 196 MVA | 223 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 225000 | 0% |  | 9
A in MTEP14 | East | ITCT | 4532 | 2017-03-27 | 8674 | 2017-03-27 | LNup | 2017-10-01 | Wayne | Hines | 1 | 230 |  | Remediate the sag limit on the Wayne to Hines 230kV line up to its conductor rating | Under Construction | 155000 | Engineering |  | MI |  |  | 585 MVA | 669 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 155000 | 0% |  | 10
A in MTEP14 | East | ITCT | 4566 | 2016-03-23 | 8708 | 2017-03-29 | TEQ | 2017-12-31 | Blanket for Customer Interconnections 2017 | Throughout system |  | 120 |  | Connect interconnecting entities as requested | Under Construction | 2000000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 2000000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4567 | 2016-03-23 | 8709 | 2014-12-29 | TEQ | 2018-12-31 | Blanket for Customer Interconnections 2018 | Throughout system |  | 120 |  | Connect interconnecting entities as requested | M2a_Pre-Project Approval | 2000000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 2000000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4573 | 2014-12-17 | 8715 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Transformer Refurbishment Program 2016 | Throughout system |  |  |  | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings. | M5_In Service | 600000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 600000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4584 | 2016-12-20 | 8726 | 2016-12-20 | TEQ | 2017-09-30 | Trenton Channel 120 kV Bus 14 |  |  | 120 |  | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 14 so that three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | M3_Long Lead Materials | 108000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 108000 | 0% |  | 9
A in MTEP14 | East | ITCT | 4585 | 2016-12-20 | 8727 | 2017-06-28 | TEQ | 2017-09-30 | Trenton Channel 120 kV Bus 17 |  |  | 120 |  | Install a second independent bus protection scheme on Trenton Channel 120 kV bus 17 so that a three (3) phase to ground fault on the bus will be cleared within 5 cycles when the existing single bus protection scheme is shutdown. | M4_Pre-Construction | 360000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 360000 | 0% | New estimate includes OPGW for Trenton Channel - Riverview line. | 9
A in MTEP14 | East | ITCT | 4701 | 2014-12-17 | 8886 | 2016-12-20 | LNup | 2016-12-31 | NERC Alert Facility Ratings for 2016 | Throughout system |  |  |  | Verify and remediate facilities as required due to the industry-wide NERC alert | M5_In Service | 3600000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 3600000 | 0% |  | 0
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9000 | 2017-03-02 | SUB | 2017-03-01 | Klam |  |  | 120 |  | Construct a new 3 breaker substation for Klam. | M5_In Service | 3160000 | Engineering |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 3160000 | 0% |  | 7
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9001 | 2017-03-02 | CAP | 2017-03-01 | Klam |  |  | 120 |  | Install a 33.3 MVAR capacitor at the new Klam 120 kV substation. | M5_In Service | 170000 | Engineering |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 170000 | 0% |  | 7
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9002 | 2017-03-02 | LN | 2017-03-01 | Klam | Bergen Tap | 1 | 120 |  | New line created by looping the Lapeer - Tuscola circuit into the new Klam substation | M5_In Service | 5220000 | Engineering |  | MI |  | 3.1 | 305 | 349 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 5220000 | 0% |  | 7
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9003 | 2017-03-02 | LN | 2017-03-01 | Klam | Lapeer | 1 | 120 |  | New line created by looping the Lapeer - Tuscola circuit into the new Klam substation | M5_In Service | 5220000 | Engineering |  | MI |  | 3.1 | 270 | 312 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 5220000 | 0% |  | 7
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9004 | 2017-03-02 | RLY | 2017-03-01 | Tuscola |  |  | 120 |  | Upgrade relay at the Tuscola Substation | M5_In Service | 210000 | Engineering |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 210000 | 0% |  | 7
A in MTEP14 | East | ITCT | 4737 | 2017-03-02 | 9005 | 2017-03-02 | RLY | 2017-03-01 | Lapeer |  |  | 120 |  | Upgrade relay at the Lapeer Substation | M5_In Service | 110000 | Engineering |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-08-31 | Under Construction | 110000 | 0% |  | 7
A in MTEP14 | West | MDU | 3083 | 2015-03-31 | 5364 | 2017-01-16 | LN | 2019-12-31 | North Dickinson | Dickinson West | 1 | 115 |  | New line Segment | Planned | 750000 | Engineering |  | ND |  | 3 | 120 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-07-01 | Planned | 750000 | 0% |  | 17
A in MTEP14 | West | MDU | 3083 | 2015-03-31 | 5365 | 2017-01-16 | CB | 2019-12-31 | North Dickinson | 2 PCB |  | 115 |  | Complete North Dickinson bus | Planned | 1500000 | Engineering |  | ND |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-07-01 | Planned | 1500000 | 0% |  | 17
A in MTEP14 | West | MDU | 4133 | 2015-01-09 | 7864 | 2017-06-21 | TX | 2017-03-30 | Collins | 115/41.6 kV transformer | 1 | 115 | 41.6 | 115/41.6 kV transformer | M5_In Service | 1439000 | Engineering |  | ND |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-03-01 | Planned | 1500000 | -4.067% |  | 0
A in MTEP14 | West | MDU | 4134 | 2015-01-09 | 7865 | 2017-06-21 | SUB | 2017-07-31 | South 9th | 115/12.47 kV transformer | 1 | 115 | 12.47 | New substation & transformer | Planned | 3600000 | Engineering |  | ND |  |  | 25 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 3600000 | 0% |  | 1
A in MTEP14 | West | MDU | 4134 | 2015-01-09 | 7866 | 2017-06-21 | LN | 2017-05-12 | South 9th tap | South 9th | 1 | 115 |  | Double circuit line to the new South 9th substation connecting to the East Bismarck-Sweet Ave 115 kV line | M5_In Service | 906000 | Engineering |  | ND |  |  | 190 | 190 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 600000 | 51% | design changes | -1
A in MTEP14 | West | MDU | 4141 | 2015-01-09 | 7875 | 2017-03-20 | IND | 2016-12-22 | Wishek Jct | tertiary reactor |  | 13.8 |  | 1 X 30 Mvar tertiary reactor | M5_In Service | 1284000 | Engineering |  | ND |  |  | 15 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-09-30 | Planned | 500000 | 156.8% | Replaced existing transformer with spare 230/115 xfmr and low side 115 kV switcher was replaced with breaker | 3
A in MTEP14 | West | MEC | 4255 | 2015-09-16 | 8003 | 2017-06-27 | SUB | 2017-05-01 | Sioux City Airport | Substation |  | 161 | 13 | Sioux City Airport Substation | M5_In Service | 2500000 | Planning | 2012 | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 2500000 | 0% |  | 0
A in MTEP14 | West | MEC | 4594 | 2015-09-16 | 8741 | 2017-06-27 | LN | 2017-05-01 | Raun | Sioux City Airport | 1 | 161 |  | Add Raun-Sioux City Airport 161 kV line | M5_In Service | 169000 | Planning |  | IA |  | 0.1 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 70000 | 141.4% |  | 0
A in MTEP14 | West | MEC | 4594 | 2015-09-16 | 8742 | 2017-06-27 | LN | 2017-05-01 | Kellogg | Sioux City Airport | 1 | 161 |  | Add CF Industries-Sioux City Airport 161 kV line | M5_In Service | 169000 | Planning |  | IA |  | 0.1 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-05-01 | Planned | 70000 | 141.4% |  | 0
A in MTEP14 | East | METC | 1803 | 2017-03-01 | 3618 | 2017-03-01 | LNrb | 2017-02-28 | Plum | Stover | 1 | 138 |  | Rebuild the 8.8 mile 138 kV line using 954 ACSR and OPGW (Pre-build to 230 kV construction). | M5_In Service | 10500000 | Engineering |  | MI | 8.8 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 10500000 | 0% | Updated estimate includes OPGW. | 2
A in MTEP14 | East | METC | 4504 | 2017-06-08 | 8630 | 2017-06-08 | LNup | 2017-06-05 | Vergennes | Marquette | 1 | 138 |  | Remediate the sag limit on the 795 ACSR from the Vergennes - Marquette 138 kV circit up to the conductor limit. | M5_In Service | 345000 | Engineering |  | MI | 17.2 |  | 315 MVA | 360 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 345000 | 0% | Refined Engineering Estimate | 6
A in MTEP14 | East | METC | 4505 | 2016-11-01 | 8631 | 2016-11-01 | LNup | 2017-12-31 | Bass Creek | Sternberg | 1 | 138 |  | Remediate the sag limits on the 336.4 and 266.8 ACSR portions of the Bass Creek - Sternberg 138 kV circuit. | M3_Long Lead Materials | 1200000 | Engineering |  | MI | 15.9 |  | 154 MVA | 174 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 1200000 | 0% | The project scope has been revised. There are 20 condemned wood poles that need to be replaced in order to remediate the sag limit on this circuit. | 12
A in MTEP14 | East | METC | 4521 | 2017-06-28 | 8662 | 2017-06-28 | LNup | 2017-05-01 | Riggsville | Rondo | 1 | 138 |  | Remediate sag on the Riggsville - Rondo 138 kV section to bring its rating up to the conductor limit (174 MVA). | M5_In Service | 324000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 324000 | 0% |  | 5
A in MTEP14 | East | METC | 4522 | 2014-12-17 | 8663 | 2016-12-20 | LNrb | 2016-11-09 | Lawndale | Murphy | 1 | 138 |  | Rebuild the 3/0 Cu & 2/0 Cu 6-wire (1.188 mile) and 336 ACSR (1.713 mile) sections on the Lawndale ? Murphy 138 kV line to 954 ACSR. | M5_In Service | 2800000 | Engineering |  | MI | 2.84 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 2800000 | 0% |  | -1
A in MTEP14 | East | METC | 4537 | 2016-03-23 | 8679 | 2017-03-29 | Dist | 2017-12-31 | Blanket for Customer Interconnections 2017 | Throughout system |  | 138 |  | Connect interconnecting entities as requested | Under Construction | 2500000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | M2a_Pre-Project Approval | 2500000 | 0% |  | 0
A in MTEP14 | East | METC | 4538 | 2016-03-23 | 8680 | 2014-12-29 | Dist | 2018-12-31 | Blanket for Customer Interconnections 2018 | Throughout system |  | 138 |  | Connect interconnecting entities as requested | M2a_Pre-Project Approval | 2500000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 2500000 | 0% |  | 0
A in MTEP14 | East | METC | 4539 | 2014-12-17 | 8681 | 2015-12-28 | RLY | 2017-12-31 | METC Hemphill Control Relocation Project - Years 2015, 2016, 2017 | Hemphill |  |  |  | Replace METC relaying and controls at Hemphill Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | M3_Long Lead Materials | 3640000 |  |  | MI |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 3640000 | 0% |  | 0
A in MTEP14 | East | METC | 4542 | 2014-12-17 | 8684 | 2015-06-29 | RLY | 2017-12-31 | METC Morrow Control Relocation Project - Years 2015, 2016, 2017 | Morrow |  |  |  | Replace METC relaying and controls at Morrow Substation. Locate the new relaying and controls in a new dedicated METC control center. Install dedicated METC AC and DC systems. | M3_Long Lead Materials | 3110000 |  |  | MI |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 3110000 | 0% |  | 0
A in MTEP14 | East | METC | 4546 | 2014-12-17 | 8688 | 2016-12-20 | TEQ | 2016-12-31 | METC Power Transformer Refurbishment Program - Year 2016 | Throughout system |  |  |  | Replace leaking oil pumps and valves, transformer oil, surge arresters, and bushings | M5_In Service | 600000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 600000 | 0% |  | 0
A in MTEP14 | East | METC | 4555 | 2017-06-28 | 8697 | 2017-06-28 | TEQ | 2018-03-31 | Tippy | Stronach | 1 | 138 |  | Install a dual pilot relay protection system on the Tippy to Stronach 138 kV circuit so that three (3) phase to ground faults will be cleared within 5 cycles. The Tippy 138 kV BK 177 bypassing will also be removed. | M3_Long Lead Materials | 575000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 575000 | 0% |  | 15
A in MTEP14 | East | METC | 4556 | 2016-11-10 | 8698 | 2016-11-10 | TEQ | 2017-12-31 | Blackstone |  |  | 138 |  | install a second bus relay scheme on Blackstone blue and white busses and install second independent relay components on Blackstone end of the Blackstone-Marshall 138 kV circuit, Blackstone-Tompkins 138 kV ckts #1 and #2 and Blackstone-Leoni 138 kV ckts # | M3_Long Lead Materials | 845000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | M3_Long Lead Materials | 845000 | 0% |  | 9
A in MTEP14 | East | METC | 4557 | 2017-02-21 | 8699 | 2017-02-21 | TEQ | 2019-12-31 | Croton | Four Mile | 1 | 138 |  | Add a dual pilot relay protection system on Croton to Four Mile 138 kV circuit so that 3 phase to ground faults on the circuit will be cleared within 5 cycles. | M3_Long Lead Materials | 483000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 483000 | 0% |  | 36
A in MTEP14 | East | METC | 4558 | 2015-12-28 | 8700 | 2016-12-20 | TEQ | 2016-10-21 | Karn | Manning | 1 | 138 |  | Install a dual pilot relay protection scheme on the Karn to Manning 138 kV circuit | M5_In Service | 460000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 460000 | 0% | Cost estimate refined to include overhead costs which were previously omitted.,Cost estimate refined to include overhead costs which were previously omitted. | -2
A in MTEP14 | East | METC | 4559 | 2015-12-28 | 8701 | 2016-12-20 | TEQ | 2016-11-25 | Karn | Saginaw River | 1 | 138 |  | Install a dual pilot relay protection scheme on the Karn to Saginaw River 138 kV circuit | M5_In Service | 575000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 575000 | 0% | Cost estimate refined to include overhead costs which were previously omitted.,Cost estimate refined to include overhead costs which were previously omitted. | -1
A in MTEP14 | East | METC | 4699 | 2014-12-17 | 8884 | 2016-12-20 | LNup | 2016-12-31 | NERC Alert Facility Ratings for 2016 | Throughout system |  |  |  | Verify and remediate facilities as required due to the industry-wide NERC alert | M5_In Service | 11200000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 11200000 | 0% |  | 0
A in MTEP14 | East | METC | 4814 | 2016-12-20 | 9097 | 2016-12-20 | LNup | 2017-09-30 | Morrow | Battle Creek | 1 | 138 |  | Remediate sag limit on the Morrow - Battle Creek #1 138 kV line to lowest overhead line rating. | M4_Pre-Construction | 366000 | Engineering |  | MI |  |  | 225 MVA | 257 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 366000 | 0% |  | 9
A in MTEP14 | East | METC | 4815 | 2016-10-11 | 9098 | 2017-03-29 | LNup | 2017-12-31 | Verona | Foundry | 1 | 138 |  | Remediate sag limit on the Verona - Foundry 138 kV line to lowest overhead line rating. | M4_Pre-Construction | 2000000 | Engineering |  | MI |  |  | 180 MVA | 208 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M3_Long Lead Materials | 815000 | 145.4% | Revised estimate to account for signification labor costs due to the extensive wetland mitigation needed to access the right of way. | 12
A in MTEP14 | West | MH, MP | 3831 | 2014-12-17 | 7200 | 2014-09-24 | LN | 2020-06-01 | Dorsey | US/MB Border | 1 | 500 |  | Dorsey-US/Manitoba Border 500 kV Line | Planned |  |  |  | MB |  | 160 | 1732 |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | MH, MP | 3831 | 2014-12-17 | 7201 | 2014-11-18 | LN | 2020-06-01 | US/MB Border | Iron Range | 1 | 500 |  | US/Manitoba Border-Iron Range 500 kV Line | Planned | 573207005 | Facility Study | 2013 | MN |  | 220 | 1732 | 2165 | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 573207005 | 0% |  | 0
A in MTEP14 | West | MH, MP | 3831 | 2014-12-17 | 7202 | 2014-09-24 | SUB | 2020-06-01 | Iron Range |  |  | 500 | 230 | New Iron Range 500/230 kV Substation adjacent to existing Blackberry 230/115 kV Substation | Planned | 46023004 | Facility Study | 2013 | MN | 0 | 0 | 1200 | 1500 | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 46023004 | 0% |  | 0
A in MTEP14 | West | MH, MP | 3831 | 2014-12-17 | 7622 | 2014-11-18 | SC | 2020-06-01 | Warroad River |  |  | 500 |  | New midpoint series compensation station on Dorsey - Iron Range 500 kV Line | Planned | 52433712 | Facility Study | 2013 | MN | 0 | 0 | 1732 | 2165 | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 52433712 | 0% |  | 0
A in MTEP14 | West | MP | 3831 | 2014-12-17 | 20289 | 2015-01-06 | LNrl | 2020-06-01 | Iron Range | various |  | 230 |  | Modifications to and reroutes of existing 230 kV and 115 kV lines at Iron Range Substation site | Planned | 3891711 | Facility Study | 2013 | MN | 0 | 2 |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 3891711 | 0% |  | 0
A in MTEP14 | West | MP | 3831 | 2014-12-17 | 20290 | 2015-01-06 | RLY | 2020-06-01 | Blackberry |  |  | 230 |  | Two 230 kV panel replacements at Blackberry to facilitate interconnection of Iron Range 500/230 kV Substation | Planned | 275000 | Facility Study | 2013 | MN | 0 | 0 |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 275000 | 0% |  | 0
A in MTEP14 | West | MP | 3831 | 2014-12-17 | 20291 | 2015-01-06 | RLY | 2020-06-01 | Forbes |  |  | 230 |  | One 230 kV panel replacement at Forbes to facilitate interconnection of Iron Range 500/230 kV Substation | Planned | 137500 | Facility Study | 2013 | MN | 0 | 0 |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 137500 | 0% |  | 0
A in MTEP14 | West | MP | 3831 | 2014-12-17 | 20292 | 2015-01-06 | RLY | 2020-06-01 | Arrowhead |  |  | 230 |  | One 230 kV panel replacement at Arrowhead to facilitate interconnection of Iron Range 500/230 kV Substation | Planned | 137500 | Facility Study | 2013 | MN | 0 | 0 |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 137500 | 0% |  | 0
A in MTEP14 | West | MP | 3831 | 2014-12-17 | 20293 | 2015-01-06 | RLY | 2020-06-01 | Hilltop |  |  | 230 |  | One 230 kV panel replacement at Hilltop to facilitate interconnection of Iron Range 500/230 kV Substation | Planned | 137500 | Facility Study | 2013 | MN | 0 | 0 |  |  | TDSP |  |  | N | N | Y | Externally Driven | A | 2020-06-01 | Planned | 137500 | 0% |  | 0
A in MTEP14 | West | MP | 4044 | 2014-12-17 | 7681 | 2015-06-12 | SUB | 2016-06-30 | Canosia Road | New Substation |  | 115 | 14 | New substation in Arrowhead - Cloquet 115 kV Line | Under Construction | 4868663 | Engineering |  | MN | 0 |  | 39.2 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-06-30 | Under Construction | 4868663 | 0% | Project staging over multiple years due to annual budget constraints | 0
A in MTEP14 | West | MP | 4045 | 2014-12-17 | 7682 | 2015-05-19 | TX | 2016-10-01 | Embarrass |  | 1 | 115 | 23 | Embarrass 115/23 kV Transformer | Planned | 1850000 | Planning | 2014 | MN | 0 | 0 | 18.6 | 23.3 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-10-01 | Planned | 1850000 | 0% | Scope change - breaker addition & bus expansion required to facilitate transformer addition | 0
A in MTEP14 | West | MP | 4426 | 2015-01-09 | 8457 | 2015-06-10 | BUS | 2017-01-31 | Hoyt Lakes |  |  | 138 |  | Bus reconfiguration & equipment replacements | Planned | 2500000 | Planning Preliminary | 2014 | MN | 0 | 0 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-31 | Planned | 2500000 | 0% | Further project scoping has refined project estimate | 0
A in MTEP14 | West | MP | 4426 | 2015-01-09 | 20288 | 2015-06-10 | CAP | 2017-01-31 | Hoyt Lakes |  |  | 138 |  | Hoyt Lakes 30 MVAr cap bank | Planned | 500000 | Planning Preliminary | 2014 | MN | 0 | 0 | 30 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-31 | Planned | 500000 | 0% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8563 | 2017-06-29 | LN | 2016-12-31 | Fergus Falls | Silver Lake | 1 | 230 |  | Address woodpecker damage and prevent future damage on existing line. | Withdrawn | 0 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8564 | 2017-06-29 | LN | 2016-12-31 | Alexandria - MRES | Grant County | 1 | 115 |  | Address woodpecker damage and prevent future damage on existing line. | Withdrawn | 0 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8565 | 2017-06-29 | LN | 2016-12-31 | Alexandria Tap | Miltona Tap | 1 | 115 |  | Address woodpecker damage and prevent future damage on existing line. | M5_In Service | 66365 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 150000 | -55.76% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8566 | 2017-06-29 | LN | 2016-12-31 | Audubon | Cormorant Jct. | 1 | 115 |  | Address woodpecker damage and prevent future damage on existing line. | Withdrawn | 0 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8567 | 2017-06-29 | LN | 2016-12-31 | Edgetown | Pelican Rapids | 1 | 115 |  | Address woodpecker damage and prevent future damage on existing line. | Withdrawn | 0 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | MRES | 4470 | 2016-09-26 | 8568 | 2017-06-29 | LN | 2016-12-31 | Detroit Lakes West | Detroit Lakes Industrial | 1 | 115 |  | Address woodpecker damage and prevent future damage on existing line. | Withdrawn | 0 | Planning | 2013 | MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% |  | 0
A in MTEP14 | West | OTP | 4444 | 2016-12-22 | 8503 | 2016-12-22 | LNup | 2017-01-31 | NERC Alert Facility Ratings for Low Priority | Throughout system |  | 115 |  | Verify and remediate facilities as required due to the industry-wide NERC alert | Planned | 7701028 | Construction |  | MN,ND,SD |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 7701028 | 0% |  | 1
A in MTEP14 | Central | PPI | 4434 | 2017-06-02 | 8468 | 2016-05-02 | TAP | 2016-12-31 | Alsey | Alsey Tap | 1 | 138 |  | Alsey 2nd 138 kV Tap to Ameren | M4_Pre-Construction | 1039100 | Engineering | 2013 | IL | 0 | 0.33 | 229 | 229 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 1039100 | 0% | PPI has agreed with Ameren, to construct a new 138 kV switching station west of Alsey to be named Ballard. This substation replaces Ameren's Bogart substation. The Ballard station is being built by PPI and will be sold to Ameren when completed. The Ballard station will initially contain terminals Ballard-Alsey, Ballard-Meredosia/Jerseyville and Ballard-Pittsfield. At a later date after Ameren obtains the ROW, Ameren will build the line that will sectionalize the Meredosia-Jerseyville 138 kV line. Then the Ballard-Meredosia/Jerseyville terminal will be replaced by a Ballard-Meredosia terminal and a Ballard-Jerseyville terminal. | 0
A in MTEP14 | West | XEL | 4379 | 2016-05-10 | 8393 | 2016-12-29 | CB | 2017-06-05 | Quarry |  |  | 115 |  | Install 115 kV breaker and half layout at existing Quarry substation | Planned | 2000000 | Planning |  | MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-04-13 | Planned | 2000000 | 0% |  | 2
A in MTEP14 | West | XEL | 4693 | 2014-12-17 | 8877 | 2017-06-27 | LNrb | 2017-06-01 | Douglas County | West Union | 1 | 69 |  | Rebuild the Douglas County - West Union 69 kV line to 477 ACSR and transfer Osakis substation load to Douglass County | M5_In Service | 5000000 |  |  | MN | 6.6 |  | 71.7 | 71.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-23 | Planned | 3011966 | 66% | Previous reports did not indicate EAC. Adding forecasted amount at this time. | 6
A in MTEP14 | West | XEL | 4694 | 2014-12-17 | 8878 | 2017-03-20 | CAP | 2018-01-15 | Gravel Island |  |  | 161 |  | Install two steps of 30 Mvar capacitor banks at Gravel Island substation on the 161 kV bus | M4_Pre-Construction | 3500000 |  |  | WI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-08-01 | M4_Pre-Construction | 3500000 | 0% | Reporting for this project was not previously done, added EAC for initial reporting | 5
A in MTEP14 | West | XEL | 4697 | 2014-12-17 | 8881 | 2017-06-24 | LNrc | 2020-10-15 | Split Rock | Nobles County | 1 | 345 |  | Reconductor 35 miles to Bundled 477 T-2 ACSR | Planned | 5547376 |  |  | MN | 35 |  | 1195 | 1195 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-11-30 | Planned | 5547376 | 0% | Entering initial EAC. This project did not appear to have been updated quarterly in the past. | 23
A in MTEP13 | Central | AmerenIL | 2302 | 2013-02-25 | 4218 | 2016-12-12 | LN | 2016-12-01 | Madison Industrial | Madison State Street | 1 | 138 |  | Reconductor 795 SAC to 1200 A summer emergency capability | M5_In Service | 1637000 | Engineering |  | IL | 2.35 |  | 240 | 285 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 1637000 | 0% |  | 0
A in MTEP13 | Central | AmerenIL | 4272 | 2012-11-09 | 8052 | 2016-12-12 | LN | 2016-12-01 | Grand Tower | Makanda | 1 | 138 |  | Grand Tower-Makanda-1 138 kV Line - Rebuild 16.91 miles of existing 556 kcmil ACSR conductor with conductor capable of carrying 1200 A under summer emergency conditions. | M5_In Service |  |  |  | IL | 16.91 |  | 269 | 305 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3813 | 2014-01-31 | 7160 | 2014-09-26 | LNrc | 2017-12-31 | Dam Heights | Eagleview | 1 | 69 |  | Reconductor Dam Heights-Eagleview 69 kV line with T2-4/0 | M1_Final SPM or OOC | 0 | Engineering | 2015 | WI | 0.1 |  | 79 | 95 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 0 | 0% | Estimate was in 2009$ | 0
A in MTEP13 | West | ATC | 3813 | 2014-01-31 | 7161 | 2014-06-13 | LNrc | 2017-12-31 | Eagleview | Merrimac Tap | 1 | 69 |  | Reconductor Eagleview-Merrimac Tap 69 kV line with T2-4/0 | M1_Final SPM or OOC |  | Engineering | 2015 | WI | 8.4 |  | 41 | 55 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3813 | 2014-01-31 | 7162 | 2015-09-30 | LNrc | 2017-12-31 | Merrimac Tap | Merrimac | 1 | 69 |  | Reconductor Merrimac Tap-Merrimac 69 kV line with T2-4/0 | M1_Final SPM or OOC | 33700000 | Engineering | 2015 | WI | 1.8 |  | 79 | 95 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 33700000 | 0% | Cost estimate change | 0
A in MTEP13 | West | ATC | 3813 | 2014-01-31 | 7163 | 2014-06-13 | LNrc | 2017-12-31 | Merrimac Tap | Caledonia | 1 | 69 |  | Reconductor Merrimac Tap-Caledonia 69 kV line with T2-4/0 | M1_Final SPM or OOC |  | Engineering | 2015 | WI | 8.4 |  | 41 | 55 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3813 | 2014-01-31 | 7164 | 2014-06-13 | LNrc | 2017-12-31 | Caledonia | Portage | 1 | 69 |  | Reconductor Caledonia-Portage 69 kV line with T2-4/0 | M1_Final SPM or OOC |  | Engineering | 2015 | WI | 7 |  | 41 | 55 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3817 | 2016-01-11 | 7168 | 2016-09-29 | CB | 2017-12-01 | Shoto |  |  | 138 |  | Shoto 138-69 kV Tr highside breaker additions | M3_Long Lead Materials | 4325000 |  |  | WI |  |  |  |  | Other |  | Relaying | N | N | Y | Bottom-Up | A | 2017-12-01 | M3_Long Lead Materials | 4325000 | 0% | Engineering Estimate vs Planning Estimate, scope is more refined | 0
A in MTEP13 | West | ATC | 3841 | 2014-01-31 | 7268 | 2017-03-30 | LN | 2016-11-16 | Pulliam | Liberty St | 1 | 138 |  | Existing line conversion from 69 to 138 from Pulliam to Liberty St | M5_In Service | 25000000 | Engineering, Nominal |  | WI | 3.93 |  | 246 | 246 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | M1_Final SPM or OOC | 22675655 | 10.25% |  | -1
A in MTEP13 | West | ATC | 3841 | 2014-01-31 | 7269 | 2017-06-29 | LN | 2016-11-10 | Liberty St | Ashland Ave | 1 | 138 |  | Existing line conversion from 69 to 138 from Liberty St to Ashland Ave | M5_In Service | 0 |  |  | WI | 2.81 |  | 246 | 246 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-03-01 | M1_Final SPM or OOC | 0 | 0% |  | 8
A in MTEP13 | West | ATC | 3841 | 2014-01-31 | 7272 | 2015-10-19 | SUB | 2016-03-01 | Pulliam |  |  |  |  | Substation work to accommodate new 138 kV line | M1_Final SPM or OOC | 0 |  |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-03-01 | M1_Final SPM or OOC | 0 | 0% | Most current cost estimate.,Most current cost estimate. | 0
A in MTEP13 | West | ATC | 3841 | 2014-01-31 | 7273 | 2015-10-19 | TX | 2016-12-01 | Pulliam |  |  | 138 | 69 | New Transformer at Pulliam | M1_Final SPM or OOC | 0 |  |  | WI |  |  | 154 | 154 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3841 | 2014-01-31 | 7274 | 2015-10-19 | TX | 2016-03-01 | Glory Rd |  |  | 138 | 69 | New Transformer at Glory Rd | M1_Final SPM or OOC | 0 |  |  | WI |  |  | 154 | 154 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-03-01 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP13 | West | ATC | 3892 | 2013-02-18 | 7437 | 2016-12-30 | LN | 2017-01-01 | Stage Coach | Black Earth | 1 | 69 |  | Uprate Stagecoach-Wick Drive 69 kV line | M1_Final SPM or OOC | 2800000 |  |  | WI |  |  | 83 | 95 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-01 | M1_Final SPM or OOC | 3500000 | -20% | Engineering Estimate vs Planning Estimate, scope is more refined | 0
A in MTEP13 | West | ATC | 3892 | 2013-02-18 | 7438 | 2016-03-30 | LN | 2017-01-01 | Black Earth | Mazomanie | 1 | 69 |  | Uprate Stagecoach-Wick Drive 69 kV line | M1_Final SPM or OOC |  |  |  | WI |  |  | 70 | 94 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-01 | M1_Final SPM or OOC | 0 | 0% | Engineering Estimate, Scope has been more refined | 0
A in MTEP13 | West | ATC | 3892 | 2013-02-18 | 7439 | 2016-03-30 | LN | 2017-01-01 | Mazomanie | Wick Drive | 1 | 69 |  | Uprate Stagecoach-Wick Drive 69 kV line | M1_Final SPM or OOC |  |  |  | WI |  |  | 70 | 94 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-01-01 | M1_Final SPM or OOC | 0 | 0% | Engineering Estimate, Scope has been more refined | 0
A in MTEP13 | West | ATC | 3895 | 2014-01-31 | 7442 | 2017-03-30 | LN | 2016-05-04 | Oak Creek | Ramsey | 1 | 138 |  | Reconductor Oak Creek-Ramsey to meet line clearances needed for new rating | M5_In Service | 830000 |  |  | WI | 0.33 |  | 233 | 293 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | M3_Long Lead Materials | 830000 | 0% | Scope increase. | -1
A in MTEP13 | West | ATC | 3895 | 2014-01-31 | 7443 | 2017-03-30 | LN | 2016-05-04 | Ramsey | Kansas | 1 | 138 |  | Reconductor Ramsey-Kansas to meet line clearances needed for new rating | M5_In Service |  |  |  | WI |  |  | 246 | 293 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-01 | M3_Long Lead Materials | 0 | 0% |  | -1
A in MTEP13 | Central | CWLP | 4270 | 2012-11-19 | 8048 | 2012-11-19 | LNrc | 2014-06-01 | N Auburn | Chatham Main | 1 | 138 | 138 | Reconductor N Auburn- Chatham Main 138 kV Line to 795 ACSS | Planned | 130000 | Planning |  | IL | 2.6 |  | 382 MVA | 382 MVA | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2014-06-01 | Planned | 130000 | 0% |  | 0
A in MTEP13 | Central | DEI | 4029 | 2012-09-12 | 7662 | 2016-12-05 | LNrb | 2016-11-25 | Sylvania | Yedo | 1 | 69 |  | Rebuild radial tap in the 6935 ckt from Sylvania to Kingman to Yedo with 477acsr @ 100C and upgrade Kingman line switches (2) to 1200A. | M5_In Service | 2770000 | Engineering | 2012 | IN | 6.8 |  | 100 | 100 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 2770000 | 0% |  | -1
A in MTEP13 | Central | DEI | 4030 | 2012-09-12 | 7663 | 2016-11-04 | LNrb | 2016-10-07 | Cayuga 69 | Gessie Jct. | 1 | 69 |  | Rebuild 6936 ckt from Cayuga 69 sub towards Gessie Jct. (str. 804-2501) with 477acsr @ 100C | M5_In Service | 3100000 | Engineering | 2012 | IN | 6.2 |  | 100 | 100 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 3100000 | 0% |  | -2
A in MTEP13 | Central | DEI | 4032 | 2012-09-12 | 7665 | 2017-03-08 | CB | 2018-12-31 | Five Points 230kV | brkr replacements |  | 230 | 138 | Five Points Station Upgrade Phase I ? Install new prefabricated control building. Replace 230kV breakers and relays. Replace 230kV circuit switchers with 230kV breakers. Replace 230-138kV bank protection. Replace 230kV bus protection. 230kV wave traps | M3_Long Lead Materials | 5406000 | Engineering | 2012 | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 5406000 | 0% | Increased scope to include 5-position 230kv ring bus for improved operational flexibility and to decrease the NERC contingency exposure (P2, 4, 5). Duke has been reviewing substations system-wide in regard to this issue. | 12
A in MTEP13 | Central | DEI | 4033 | 2016-10-04 | 7666 | 2016-10-04 | LNrb | 2018-12-31 | Camp Atterbury | Edinburg |  | 69 |  | Camp Atterbury to Edinburg 6950 Reconductor 2/0 Cu (4.0 miles) to 477ACSR and uprate existing 477ACSR 80C to 477ACSR 100C (4.5 miles). | M3_Long Lead Materials | 1650765 | Engineering | 2013 | IN | 8.5 |  | 100 | 100 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 1650765 | 0% |  | 12
A in MTEP13 | Central | DEI | 4037 | 2012-09-12 | 7670 | 2016-08-23 | SUB | 2019-12-31 | Lafayette 230 | breaker |  | 230 |  | Lafayette 230kV Sub Ring Bus - Phase 2, install one 230kV breaker, support structures, bus and 954KCM jumpers to complete five-breaker - 230kV ring bus. Insert between Banks 3 and 4. | M3_Long Lead Materials | 1618000 | Engineering | 2013 | IN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | M3_Long Lead Materials | 1618000 | 0% |  | 0
A in MTEP13 | West | GRE | 3531 | 2015-08-10 | 8039 | 2014-04-09 | LN | 2015-03-31 | Deer River | Enbridge-Deer River | 1 | 115 |  | GRE will provide 3 way motor-operated switch to accommodate MP 115 kV line from Enbridge | Planned | 400000 | Planning |  | MN |  |  | 239 | 239 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-03-31 | Planned | 400000 | 0% |  | 0
A in MTEP13 | West | GRE | 3531 | 2015-08-10 | 20918 | 2015-08-10 | TX | 2015-10-01 | Blackberry | Transformer |  | 115 | 69 | Upgrade the 46.7 MVA 115/69 kV Blackberry xfmr with a 70 MVA 115/69 kV xfmr. | Planned | 2148264 |  |  | MN |  |  | 70 |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-10-01 | Planned | 2148264 | 0% |  | 0
A in MTEP13 | West | GRE | 4008 | 2014-09-15 | 7635 | 2017-03-28 | TAP | 2016-08-31 | New Market |  | 1 | 69 |  | Replace the current 69kV switch with a manual quick whip 115kV switch | M5_In Service | 200000 | Planning |  | MN | 0 |  | 190 | 190 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-08-31 | Planned | 200000 | 0% |  | 0
A in MTEP13 | West | GRE | 4009 | 2012-09-11 | 7641 | 2016-12-29 | SUB | 2016-11-15 | St. Bonifacius |  |  | 115 | 69 | Install second 115/69 kV transformer, 115 kV ring bus, split 69 kV bus | M5_In Service | 10185577.27 | Planning |  | MN | 0 |  | 70 | 87.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-02-06 | Planned | 10185577.27 | 0% | Scope change | -3
A in MTEP13 | Central | IPL | 4724 | 2015-04-03 | 8953 | 2017-01-12 | SUB | 2016-04-16 | Eagle Valley 138 kV Substation | new gen i-connect |  | 138 |  | J238 - 138kV - Generator interconnection substation - install 4 bay breaker and a half design substation for 725MW Eagle Valley CCGT in Morgan county Indiana at the existing Pritchard Plant site. | M5_In Service |  |  |  | IN |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2016-04-16 | Under Construction | 0 | 0% |  | 0
A in MTEP13 | West | ITCM | 4099 | 2012-09-14 | 7763 | 2016-06-30 | LN | 2021-12-31 | Albert Lea Westside | South Broadway | 1 | 69 | 69 | Rebuild the Albert Lea Westside-South Broadway 69kV to T2-4/0. | M1_Final SPM or OOC | 840000 | Planning |  | MN | 2 |  | 40 MVA | 40 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 840000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4101 | 2012-09-14 | 7765 | 2016-06-30 | LN | 2016-12-31 | Montgomery | GRE-French Lake Tap | 1 | 69 | 69 | Rebuild the Montgomery-French Lake tap to T2-4/0. | Under Construction | 12483427 | Planning |  | MN | 13.25 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 12483427 | 0% | Planning estimate updated with engineering level estimate and estimate now includes terminal upgrades. | 0
A in MTEP13 | West | ITCM | 4101 | 2012-09-14 | 7766 | 2016-06-30 | LN | 2020-12-31 | GRE-French Lake Tap | Waseca Junction | 1 | 69 | 69 | Rebuild the French Lake tap-Waseca Jct. to T2-4/0. | M3_Long Lead Materials | 13654256 | Planning |  | MN | 16.34 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M3_Long Lead Materials | 13654256 | 0% | Planning estimate updated with engineering level estimate. | 0
A in MTEP13 | West | ITCM | 4102 | 2012-09-14 | 7767 | 2016-06-30 | LN | 2021-12-31 | Newport | Cairo REC | 1 | 69 | 69 | Rebuild the Newport-Cairo REC 69kV to T2-4/0. | M1_Final SPM or OOC | 6242696 | Planning |  | IA | 8.65 |  | 36 MVA | 36 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 6242696 | 0% | Engineering estimate updated the planning estimate. | 0
A in MTEP13 | West | ITCM | 4102 | 2012-09-14 | 7768 | 2016-06-30 | LN | 2021-12-31 | Cairo REC | Winfield Tap | 1 | 69 | 69 | Rebuild the Cairo REC-Winfield Tap 69kV to T2-4/0. | M1_Final SPM or OOC | 1991889 | Planning |  | IA | 2.76 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 1991889 | 0% | Engineering estimate updated the planning estimate. | 0
A in MTEP13 | West | ITCM | 4102 | 2012-09-14 | 7769 | 2016-06-30 | LN | 2021-12-31 | Winfield Tap | IBP Tap | 1 | 69 | 69 | Rebuild the Winfield Tap-IBP Tap 69kV to T2-4/0. | M1_Final SPM or OOC | 5492130 | Planning |  | IA | 7.61 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 5492130 | 0% | Engineering estimate updated the planning estimate. | 0
A in MTEP13 | West | ITCM | 4102 | 2012-09-14 | 7770 | 2016-06-30 | LN | 2021-12-31 | IBP Tap | Columbus Jct | 1 | 69 | 69 | Rebuild the IBP Tap-Columbus Jct 69kV to T2-4/0. | M1_Final SPM or OOC | 72170 | Planning |  | IA | 0.1 |  | 59 MVA | 59 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 72170 | 0% | Engineering estimate updated the planning estimate. | 0
A in MTEP13 | West | ITCM | 4103 | 2012-09-14 | 7771 | 2017-06-30 | LN | 2018-03-30 | North Burlington | North Burlington Tap | 1 | 69 | 69 | Rebuild the North Burlington-North Burlington Tap 69kV to T2-4/0. | M1_Final SPM or OOC | 5760000 | Engineering |  | IA | 8.76 |  | 69 MVA | 69 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-09-01 | M1_Final SPM or OOC | 5760000 | 0% | Due to landslides in the area and the cross country/poor access of the old line route a new route had to be taken that added 2.5 miles and the additonal cost of the new ROW issues. The Planning level esitmate was updated with an Engineering estimate. | 18
A in MTEP13 | West | ITCM | 4104 | 2012-09-14 | 7772 | 2017-06-30 | LN | 2021-12-31 | Lansing | Harper's Ferry Tap | 1 | 69 | 69 | Rebuild the Lansing-Harper's Ferry Tap 69kV to T2-4/0. | M3_Long Lead Materials | 5777996 | Planning |  | IA | 6.57 |  | 57 MVA | 57 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M3_Long Lead Materials | 5777996 | 0% | Final design estimate replaced the planning estimate and also now includes terminal upgrades. | 12
A in MTEP13 | West | ITCM | 4104 | 2012-09-14 | 7773 | 2017-06-30 | LN | 2021-12-31 | Harper's Ferry Tap | WatervilleTap | 1 | 69 | 69 | Rebuild the Harper's Ferry Tap-Waterville Tap 69kV to T2-4/0. | M3_Long Lead Materials | 2171703 | Planning |  | IA | 2.63 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M3_Long Lead Materials | 2171703 | 0% | Final design estimate replaced the planning estimate and also now includes terminal upgrades. | 12
A in MTEP13 | West | ITCM | 4104 | 2012-09-14 | 7774 | 2017-06-30 | LN | 2021-12-31 | WatervilleTap | Monona | 1 | 69 | 69 | Rebuild the Waterville Tap-Monona 69kV to T2-4/0. | M3_Long Lead Materials | 13025337 | Planning |  | IA | 15.59 |  | 48 MVA | 48 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M3_Long Lead Materials | 13025337 | 0% | Final design estimate replaced the planning estimate and also now includes terminal upgrades. | 12
A in MTEP13 | West | ITCM | 4105 | 2012-09-14 | 7775 | 2016-06-29 | LN | 2022-12-31 | Decorah | Ludlow Tap | 1 | 69 | 69 | Rebuild the Decorah-Ludlow Tap 69kV to T2-4/0. | M1_Final SPM or OOC | 8600000 | Planning |  | IA | 20.48 |  | 69 MVA | 69 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 8600000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4105 | 2012-09-14 | 7776 | 2016-06-29 | LN | 2022-12-31 | Ludlow Tap | Waukon - IPL | 1 | 69 | 69 | Rebuild the Ludlow Tap-Waukon 69kV to T2-4/0. | M1_Final SPM or OOC | 1060000 | Planning |  | IA | 2.51 |  | 59 MVA | 59 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 1060000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4106 | 2012-09-14 | 7777 | 2017-06-30 | LN | 2022-12-31 | Windsor | Hawk Tap | 1 | 69 | 69 | Rebuild the Windsor-Hawk Tap 69kV to T2-4/0. | M1_Final SPM or OOC | 2775000 | Planning |  | IA | 6.6 |  | 48 MVA | 48 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M1_Final SPM or OOC | 2775000 | 0% |  | 24
A in MTEP13 | West | ITCM | 4106 | 2012-09-14 | 7778 | 2017-06-30 | LN | 2022-12-31 | Hawk Tap | Richfield | 1 | 69 | 69 | Rebuild the Hawk Tap-Richfield 69kV to T2-4/0. | M1_Final SPM or OOC | 1975000 | Planning |  | IA | 4.64 |  | 45 MVA | 45 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-31 | M1_Final SPM or OOC | 1975000 | 0% |  | 24
A in MTEP13 | West | ITCM | 4107 | 2012-09-14 | 7782 | 2017-06-30 | LN | 2017-05-19 | Armour | Lehigh Quarry Tap | 1 | 69 | 69 | Rebuild the Armour-Nettle to T2-4/0 | M5_In Service | 1078800 | Engineering |  | IA | 1.87 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-08-04 | M1_Final SPM or OOC | 1078800 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | -3
A in MTEP13 | West | ITCM | 4107 | 2012-09-14 | 7783 | 2017-06-30 | LN | 2017-05-19 | Nettle | Northwest Tap | 1 | 69 | 69 | Rebuild the 25th Street Tap-Northwest Tap to T2-4/0 | M1_Final SPM or OOC | 616800 | Engineering |  | IA | 1.01 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-08-04 | M1_Final SPM or OOC | 616800 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | -3
A in MTEP13 | West | ITCM | 4107 | 2012-09-14 | 7784 | 2017-06-30 | LN | 2017-05-19 | Nettle | Lehigh Quarry Tap | 1 | 69 | 69 | Rebuild the line from 25th Street Tap-Lehigh Quarry Tap to T2-4/0 | M1_Final SPM or OOC | 600000 | Engineering |  | IA | 1.65 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-08-04 | M1_Final SPM or OOC | 600000 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | -3
A in MTEP13 | West | ITCM | 4108 | 2012-09-14 | 7779 | 2016-06-30 | LN | 2022-12-31 | Ellendale | Steele Center Tap | 1 | 69 | 69 | Rebuild the Ellendale-Steele Center Tap to T2-4/0 | M1_Final SPM or OOC | 1091365 | Planning |  | MN | 1.98 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 1091365 | 0% | Engineering estimate replaced the planning level estimate. | 0
A in MTEP13 | West | ITCM | 4108 | 2012-09-14 | 7780 | 2016-06-30 | LN | 2022-12-31 | Steele Center Tap | Pratt Tap | 1 | 69 | 69 | Rebuild the Steele Center Tap-Pratt Tap to T2-4/0 | M1_Final SPM or OOC | 3847336 | Planning |  | MN | 6.98 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 3847336 | 0% | Engineering estimate replaced the planning level estimate. | 0
A in MTEP13 | West | ITCM | 4108 | 2012-09-14 | 7781 | 2016-06-30 | LN | 2022-12-31 | Pratt Tap | West Owatonna | 1 | 69 | 69 | Rebuild the Pratt Tap-West Owatonna to T2-4/0 | M1_Final SPM or OOC | 2342576 | Planning |  | MN | 4.25 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 2342576 | 0% | Engineering estimate replaced the planning level estimate. | 0
A in MTEP13 | West | ITCM | 4113 | 2012-09-14 | 7794 | 2014-03-31 | TEQ | 2015-04-30 | Hayward | Substation | 1 | 161 | 69 | Upgrade 69kV breaker 665 terminal equipment | Planned | 15000 | Planning |  | MN |  |  | 250 MVA | 250 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-04-30 | Planned | 15000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4114 | 2012-09-14 | 7795 | 2014-03-31 | TEQ | 2015-04-30 | Triboji | Substation | 1 | 161 | 69 | Upgrade 69kV breaker 6730 terminal equipment | Planned | 15000 | Planning |  | IA |  |  | 250 MVA | 250 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-04-30 | Planned | 15000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4114 | 2012-09-14 | 7796 | 2014-03-31 | TEQ | 2015-04-30 | Flying Cloud | Substation | 1 | 161 | 69 | Change CT ratio to increase capacity/coordinate with Triboji work | Planned | 5000 | Planning |  | IA |  |  | 250 MVA | 250 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-04-30 | Planned | 5000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4115 | 2012-09-14 | 7808 | 2016-06-30 | SUB | 2019-12-31 | Fletcher | Substation | 1 | 161 | 69 | Build new Fletcher 161kV & 69kV sub | M1_Final SPM or OOC | 5173600 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 5173600 | 0% |  | 0
A in MTEP13 | West | ITCM | 4115 | 2012-09-14 | 7809 | 2016-06-30 | TX | 2019-12-31 | Fletcher | Transformer | 1 | 161 | 69 | New Fletcher 150 MVA 161/69kV TRF | M1_Final SPM or OOC | 2000000 | Engineering |  | IA |  |  | 150 MVA | 150 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 2000000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4116 | 2012-09-14 | 7804 | 2016-06-28 | LN | 2017-12-31 | Springville | Amber | 1 | 69 | 69 | Rebuild the Springville-Amber to T2-4/0 | M1_Final SPM or OOC | 9120000 | Engineering |  | IA | 21.1 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 9120000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4116 | 2012-09-14 | 7806 | 2016-06-28 | LN | 2017-12-31 | Lovell REC | Monticello Industrial | 1 | 69 | 69 | Rebuild the Lovell REC-Monticello Industrial to T2-4/0 | M1_Final SPM or OOC | 2270000 | Planning |  | IA | 5.4 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 2270000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4116 | 2012-09-14 | 7807 | 2014-06-13 | LN | 2016-12-31 | Linn TWP REC | Cornell | 1 | 69 | 69 | Build a new Linn TWP REC-Cornell 69kV with T2-4/0 | M1_Final SPM or OOC | 1760000 | Planning |  | IA |  | 4.2 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 1760000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4118 | 2012-09-14 | 7798 | 2017-04-06 | LN | 2017-04-03 | Grand Junction | Grand Jct REC Tap | 1 | 34 | 34 | Rebuild the Grand Jct-Grand Jct REC Tap to T2-4/0 | M5_In Service | 62000 | Planning |  | IA | 0.1 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-25 | M1_Final SPM or OOC | 62000 | 0% | Engineering estimate replaced the planning level estimate. | -8
A in MTEP13 | West | ITCM | 4118 | 2012-09-14 | 7799 | 2017-04-06 | LN | 2017-04-03 | Grand Jct REC Tap | Grant REC Tap | 1 | 34 | 34 | Rebuild the Grand Jct REC Tap-Grant REC Tap to T2-4/0 | M5_In Service | 5315800 | Planning |  | IA | 6.4 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-25 | M1_Final SPM or OOC | 5315800 | 0% | Engineering estimate replaced the planning level estimate and mileage increased. | -8
A in MTEP13 | West | ITCM | 4118 | 2012-09-14 | 7800 | 2017-04-06 | LN | 2017-04-03 | Grant REC Tap | Jefferson WCC | 1 | 34 | 34 | Rebuild the Grant REC TapJefferson WCC to T2-4/0 | M5_In Service | 739800 | Planning |  | IA | 0.25 |  | 39 MVA | 39 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-25 | M1_Final SPM or OOC | 739800 | 0% | Engineering estimate replaced the planning level estimate and mileage increased. | -8
A in MTEP13 | West | ITCM | 4121 | 2012-09-14 | 7821 | 2017-02-24 | LN | 2016-12-31 | Blanket for Customer Interconnections under $1 million for 2013 | Throughout system |  |  |  | These projects are being done at the request of an interconnection customer in order to facilitate new load, re-distribute existing load, improve the performance of the sub-transmission and distribution systems, or to accommodate a new Transmission-to-Transmission connection request. | M5_In Service | 2000000 | Planning |  | IA,MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2000000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4122 | 2012-09-14 | 7825 | 2017-02-24 | LN | 2016-12-31 | Blanket for Misc. Line Equipment Replacement 2016 | Throughout system |  |  |  | Replace defective cross arms, insulators, arrestors, and pole quuys | M5_In Service | 4000000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 4000000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4123 | 2012-09-14 | 7829 | 2017-02-24 | LN | 2016-12-31 | Blanket for Breaker Replacement Program 2016 | Throughout system |  |  |  | Replace defective and damaged breakers | M5_In Service | 5000000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 5000000 | 0% | Breaker replacements budget reduced to more acurately reflect the amount of work expected to be complete. | 0
A in MTEP13 | West | ITCM | 4124 | 2012-09-14 | 7832 | 2017-02-24 | LN | 2016-12-31 | Blanket for Fiber Optic Static Wire Additions 2016 | Throughout system |  |  |  | Project includes the Engineering, Procurement, Construction and Commissioning of Fiber Optic Static Wire Additions for use with ITCM?s SCADA system and protective relaying. | M5_In Service | 720000 | Planning |  | IA,MN |  |  |  |  | Other |  | Metering | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 720000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4125 | 2012-09-14 | 7835 | 2012-09-14 | LN | 2015-12-31 | Blanket for Replacement of PCB Equipment 2015 | Throughout system |  |  |  | Replace known and unknown PCB equipment in substations due to environmental hazard with expensive remediation. | Planned | 1800000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 1800000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4125 | 2012-09-14 | 7836 | 2012-09-14 | LN | 2016-12-31 | Blanket for Replacement of PCB Equipment 2016 | Throughout system |  |  |  | Replace known and unknown PCB equipment in substations due to environmental hazard with expensive remediation. | Planned | 1800000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1800000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4126 | 2012-09-14 | 7840 | 2017-02-24 | LN | 2016-12-31 | Blanket for Pole Top Switch Replacement Program 2016 | Throughout system |  |  |  | Replace defective pole top switches | M5_In Service | 960000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 960000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4127 | 2012-09-14 | 7844 | 2017-02-24 | LN | 2016-12-31 | Blanket for Relay Betterment Program 2016 | Throughout system |  |  |  | Replace defective cross arms, insulators, arrestors, and pole quuys | M5_In Service | 2500000 | Planning |  | IA,MN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2500000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4128 | 2012-09-14 | 7848 | 2017-02-24 | LN | 2016-12-31 | Blanket for SMART GRID Project 2016 | Throughout system |  |  |  | Replace, upgrade, or install TELECOM, RTUs, Relay, etc. | M5_In Service | 4800000 | Planning |  | IA,MN |  |  |  |  | Other |  | Metering | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 4800000 | 0% |  | 0
A in MTEP13 | West | ITCM | 4129 | 2012-09-14 | 7852 | 2017-02-24 | LN | 2016-12-31 | Blanket for Wood Pole Replacement Program 2016 | Throughout system |  |  |  | Replace deteriorating wood pole | M5_In Service | 3500000 | Planning |  | IA,MN |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 3500000 | 0% |  | 0
A in MTEP13 | West | ITCM, MEC | 3249 | 2014-03-31 | 6052 | 2016-09-16 | LN | 2018-12-01 | NE 54th Ave. | Bondurant | 1 | 161 |  | New 161 kV line from NE 54th Ave. to Bondurant and associated substation equipment additions. | Planned | 11221895 | Planning | 2010 | IA | 0 | 8.3 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 11221895 | 0% | Refined estimate | 0
A in MTEP13 | East | ITCT | 1550 | 2017-06-30 | 2639 | 2017-06-30 | LNug | 2017-07-21 | Hager | Sunset | 1 | 120 |  | Replace the 0.08 miles of underground 1500 KCM CU XLPE SSC 120 kV conductor from the Hager to Sunset 120 kV circuit with 5000 KCM CU XLPE 120 kV conductor. Also address clearance issues causing the sag limit on the 954 ACSR overhead conductor portion of this circuit | Under Construction | 2200000 | Engineering |  | MI | 0.1 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 2200000 | 0% | Detailed design specified the need for more extensive structures to transition from underground to overhead as the circuit enters the station. In addition, the revised project scope involves replacing underground cable with 2500 KCM CU XLPE cable instead of 2000 KCM CU XLPE to ensure circuit has adequate future capacity. | 7
A in MTEP13 | East | ITCT | 3938 | 2017-02-28 | 7500 | 2017-05-16 | CAP | 2017-04-28 | Greenwood |  |  | 120 |  | Install two 120kV, 26 Mvar capacitors capacitor banks at the Greenwood substation with 2 synchronous breakers and a 120 kV line breaker. | M5_In Service | 2020000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-07-15 | M3_Long Lead Materials | 2020000 | 0% | Previous estimate was for a single 54 MVAR capacitor bank. Project scope updated to include two 26 MVAR capacitor banks, two synchronous breakers, and a line breaker. | -3
A in MTEP13 | East | ITCT | 4145 | 2017-06-30 | 7880 | 2017-06-30 | LNug | 2017-12-31 | Quaker | Southefield |  | 120 |  | Reconductor the 0.36 mile Quaker to Southfield Underground cable section using 5000 KCM CU XLPE cable | M4_Pre-Construction | 3960000 | Engineering |  | MI | 0.36 |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 3960000 | 0% | Revised estimate includes line termination equipment. | 12
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7892 | 2016-12-20 | SwSta | 2018-11-30 | Toll Road 120kV |  |  | 120 |  | Construct a 120kV switching station (Toll Road). | M3_Long Lead Materials | 15000000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 15000000 | 0% | Cost estimate includes line entrances and necessary relay upgrades. | 11
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7894 | 2016-12-20 | LN | 2019-06-01 | Toll Road | Shoal | 1 | 120 |  | Loop the existing Fermi - Shoal 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 18
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7895 | 2016-12-20 | LN | 2019-06-01 | Toll Road | Fermi | 1 | 120 |  | Loop the existing Fermi - Shoal 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 18
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7896 | 2016-12-20 | LN | 2018-11-30 | Toll Road | Radka | 1 | 120 |  | Loop the existing Fermi - Radka 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 11
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7897 | 2016-12-20 | LN | 2018-11-30 | Toll Road | Fermi | 2 | 120 |  | Loop the existing Fermi - Radka 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 11
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 7898 | 2016-12-20 | LN | 2018-11-30 | Toll Road | Swan Creek | 1 | 120 |  | Loop the existing Fermi - Swan Creek 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 11
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 8317 | 2016-12-20 | LN | 2018-11-30 | Toll Road | Fermi | 3 | 120 |  | Loop the existing Fermi - Swan Creek 120kV line into Toll Road. | M3_Long Lead Materials | 0 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | M3_Long Lead Materials | 0 | 0% |  | 11
A in MTEP13 | East | ITCT | 4153 | 2016-12-20 | 8318 | 2015-06-29 | SVC | 2018-12-31 | Toll Road |  |  | 120 |  | Install a 100 MVAR SVC at Toll Road. | M2a_Pre-Project Approval | 25000000 | Planning |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 25000000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4159 | 2014-01-31 | 7906 | 2016-12-20 | LNrb | 2016-12-31 | ITCT Wood Pole Replacement 2016 | Throughout system |  |  |  | Replace aging wood poles with concrete poles or steel towers. | M5_In Service | 8500000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 8500000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | ITCT | 4163 | 2014-01-31 | 7910 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Surge Arrestor Replacement 2016 | Throughout system |  |  |  | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | M5_In Service | 360000 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 360000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | ITCT | 4171 | 2014-01-31 | 7918 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Misc Line Equipment Replacement 2016 | Throughout system |  |  |  | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | M5_In Service | 5000000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 5000000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4175 | 2016-08-30 | 6706 | 2017-06-28 | TEQ | 2018-09-30 | Seville 1 & 2 |  |  | 120 |  | Install a new 120 kV, 3-way, full-load-break pole top switch at each tap | M4_Pre-Construction |  |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 0 | 0% |  | 21
A in MTEP13 | East | ITCT | 4175 | 2016-08-30 | 6711 | 2016-03-22 | TEQ | 2016-06-30 | Topaz 2 | Peru |  | 120 |  | Install a new 120 kV, 1-way, full-load-break pole top switch (toward Peru) | M4_Pre-Construction |  |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-06-30 | M4_Pre-Construction | 0 | 0% |  | 0
A in MTEP13 | East | ITCT | 4175 | 2016-08-30 | 7922 | 2014-11-06 | TEQ | 2014-12-31 | ITCT Pole Top Switch Additions/Replacement 2014 | Throughout system |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | Under Construction | 2400000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2014-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4176 | 2016-08-30 | 6705 | 2016-12-20 | TEQ | 2016-11-23 | Long Lake 1 & 2 |  |  | 120 |  | Install 2 new 120 kV, 1-way, full-load-break pole top switches at each tap | M5_In Service |  |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 0 | 0% |  | -1
A in MTEP13 | East | ITCT | 4176 | 2016-08-30 | 7923 | 2016-12-20 | TEQ | 2015-12-31 | ITCT Pole Top Switch Additions/Replacement 2015 | Throughout system |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | M5_In Service | 2400000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4177 | 2016-08-30 | 7924 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Pole Top Switch Additions/Replacement 2016 | Throughout system |  |  |  | Install a new or replace an existing120 kV, 1-way, full-load-break pole top switch at needed tap points. | M5_In Service | 2400000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4181 | 2014-01-31 | 7928 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Instrument Transformer Replacement 2016 | Throughout system |  |  |  | Replace the aging potential devices including potential transformers and coupling-capacitor type potential devices. | M5_In Service | 360000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 360000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4187 | 2014-01-31 | 7934 | 2016-12-20 | TEQ | 2016-12-31 | ITCT NERC Protection Compliance Program 2016 | Throughout system |  |  |  | Upgrade relay throughout system. | M5_In Service | 2400000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4191 | 2014-01-31 | 7938 | 2016-12-20 | CB | 2016-12-31 | ITCT Breaker Replacement 2016 | Throughout system |  |  |  | Replace defective breakers throughout system | M5_In Service | 6250000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 6250000 | 0% | Project cost was changed in error, and is changing back to originally approved amount. | 0
A in MTEP13 | East | ITCT | 4195 | 2014-01-31 | 7942 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Battery Replacement 2016 | Throughout system |  |  |  | Replace battery chargers with the new ones. | M5_In Service | 200000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 200000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4199 | 2014-01-31 | 7946 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Disconnect Switch Replacement Program 2016 | Throughout system |  |  |  | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | M5_In Service | 400000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 400000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | ITCT | 4204 | 2014-01-31 | 7951 | 2016-12-20 | TEQ | 2016-12-31 | ITCT Annual Relay Betterment Program 2016 | Throughout system |  |  |  | Replace damaged or defective relays. | M5_In Service | 10400000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 10400000 | 0% | Revised cost estimate for future year. | 0
A in MTEP13 | East | ITCT | 4286 | 2015-04-03 | 8093 | 2015-03-25 | LN | 2018-05-31 | Frisbie | Waterman | 1 | 120 |  | Loop in the Frisbie ? Waterman 120 kV underground cable to feed the Henry Ford substation. Splices and terminals will be installed and underground cable run from the existing line to the new substation. The substation is located approximated 150 feet fro | M2a_Pre-Project Approval | 5000000 | Engineering |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | M2a_Pre-Project Approval | 5000000 | 0% |  | 0
A in MTEP13 | East | ITCT | 4287 | 2017-06-30 | 8094 | 2017-06-30 | LN | 2017-09-30 | Lincoln | Northeast | 1 | 120 |  | Loop the Lincoln - Northeast 120 kV circuit to feed the new Hilton Road (formerly Ferndale) substation. The substation is located adjacent to the circuit. At the new station, 3-120 kV breakers and the associated 120 kV station equipment will be installed. | Under Construction | 3800000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-03-31 | M4_Pre-Construction | 3800000 | 0% |  | 6
A in MTEP13 | West | MEC | 2952 | 2016-09-16 | 8020 | 2016-09-16 | SUB | 2018-06-01 | NE 54th Ave. | Substation |  | 161 | 13 | New 161-13 kV Substation. | Planned | 1300000 | Planning |  | IA |  |  | 33 | 33 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 1300000 | 0% | More refined cost estimate. | 0
A in MTEP13 | West | MEC | 3248 | 2015-09-15 | 6048 | 2016-09-16 | LN | 2018-06-01 | Rising Sun Substation | NE 54th Ave. | 1 | 161 |  | New 161 kV line from Rising Sun Substation on DPS-Reasnor line to East Altoona and associated substation equipment additions. | Planned | 8100000 | Planning | 2010 | IA | 0 | 6 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 8100000 | 0% | Refined cost estimate. | 0
A in MTEP13 | West | MEC | 3248 | 2015-09-15 | 6049 | 2017-06-28 | SwSta | 2018-06-01 | Rising Sun Substation |  |  | 161 |  | New 161 kV breakered substation off the DPS-Reasnor 161 kV line | Planned | 5200000 | Planning | 2010 | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 5200000 | 0% | More refined cost estimate. | 1
A in MTEP13 | West | MEC | 3248 | 2015-09-15 | 6050 | 2017-06-28 | LN | 2018-06-01 | DPS | Reasnor | 1 | 161 |  | Add 161 kV line taps to new Rising Sun Substation | Planned | 736000 | Planning | 2012 | IA |  | 0.1 | 325 | 325 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-01 | Planned | 736000 | 0% | Line taps will be longer than originally anticipated. | 1
A in MTEP13 | West | MEC | 4256 | 2015-10-01 | 8016 | 2016-09-30 | LN | 2016-12-01 | Hwys 141 & 44 | NW 70th Avenue | 1 | 161 |  | New 161 kV line from Hwys 141 & 44 Sub to NW 70th Ave. Substation | Planned | 3200000 | Planning |  | IA |  | 3 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 3200000 | 0% |  | 0
A in MTEP13 | West | MEC | 4256 | 2015-10-01 | 8017 | 2016-09-30 | LN | 2016-12-01 | NW 70th Avenue | Sycamore | 1 | 161 |  | New 161 kV line from NW 70th Avenue Sub to Sycamore Sub | Planned | 3200000 | Planning |  | IA |  | 4 | 410 | 410 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 3200000 | 0% |  | 0
A in MTEP13 | West | MEC | 4256 | 2015-10-01 | 8018 | 2016-09-30 | SUB | 2016-12-01 | NW 70th Avenue | Substation |  | 161 | 13 | New 161-13 kV Substation. | Planned | 2670000 | Planning |  | IA |  |  | 33 | 33 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 2670000 | 0% | Local government requirements. | 0
A in MTEP13 | East | METC | 4143 | 2017-03-29 | 7877 | 2017-03-29 | TEQ | 2018-12-31 | Verona |  | 1 | 138 |  | Upgrade Terminal Equipment at Verona 138 kV (position 388). | M4_Pre-Construction | 80000 | Engineering |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 80000 | 0% |  | 24
A in MTEP13 | East | METC | 4146 | 2016-07-14 | 7881 | 2017-01-04 | LNrb | 2016-12-30 | Marshall | Blackstone | 1 | 138 |  | Rebuild 34.5 miles to 954 ACSR conductor | M5_In Service | 46300000 | Engineering |  | MI | 34.5 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 46300000 | 0% | Revised estimate to account for complicated terrain as much of this rebuild crosses wetlands. | 0
A in MTEP13 | East | METC | 4147 | 2017-06-30 | 7882 | 2017-06-30 | LNrb | 2017-06-05 | Battle Creek | Island Road | 1 | 138 |  | Rebuild 23.9 miles to 954 ACSR conductor | M5_In Service | 24300000 | Engineering |  | MI | 23.9 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-06-01 | M4_Pre-Construction | 24300000 | 0% |  | 0
A in MTEP13 | East | METC | 4149 | 2016-12-20 | 7884 | 2016-12-20 | LNup | 2017-09-30 | Argenta | Tallmadge | 1 | 345 |  | Remediate sag on the Argenta ? Tallmadge 345kV line to bring its thermal rating up to 2422 Amp (1447 MVA) | M4_Pre-Construction | 1500000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-30 | M4_Pre-Construction | 1500000 | 0% |  | 15
A in MTEP13 | East | METC | 4150 | 2017-03-29 | 7885 | 2017-03-29 | TEQ | 2018-12-31 | Verona |  | 1 | 138 |  | Upgrade station equipment at Verona 138kV (position 277). | M4_Pre-Construction | 140000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 140000 | 0% |  | 24
A in MTEP13 | East | METC | 4157 | 2013-09-13 | 7904 | 2016-12-20 | LNrb | 2016-12-31 | METC Wood Pole Replacement 2016 | Throughout system |  |  |  | Replace defective wood poles with concrete poles or steel towers. | M5_In Service | 9000000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 9000000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4161 | 2012-09-14 | 7908 | 2016-12-20 | TEQ | 2016-12-31 | METC Surge Arrestor Replacement 2016 | Throughout system |  |  |  | Replace old Silicon Carbide and Gap-type surge arresters with the new MOV gapless type ones in substations. | M5_In Service | 360000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 360000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4167 | 2013-09-13 | 7914 | 2016-12-20 | LNup | 2016-12-31 | METC Misc Line Equipment Replacement 2016 | Throughout system |  |  |  | Replace cross arms that need to be replaced to maintain lines in serviceable conditions. Replace defective and damaged insulators for system reliability. Replace defective pole guying for system reliability or to meet code issues. | M5_In Service | 6000000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 6000000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4174 | 2016-08-30 | 7921 | 2016-12-20 | TEQ | 2016-12-31 | METC Pole Top Switch Additions/Replacement 2016 | Throughout system |  |  |  | Install or replace an existing a new 138 kV, 2-way, full-load-break pole top switch at needed tap points. | M5_In Service | 3600000 |  |  | MI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 3600000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4179 | 2013-09-13 | 7926 | 2016-12-20 | TEQ | 2016-12-31 | METC Instrument Transformer Replacement - Year 2016 | Throughout system |  |  |  | Replace the aging instrument transformers including potential transformers and coupling-capacitor type instrument transformers. | M5_In Service | 360000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 360000 | 0% |  | 0
A in MTEP13 | East | METC | 4184 | 2012-09-14 | 7931 | 2016-12-20 | TEQ | 2016-12-31 | METC NERC Protection Compliance Program 2016 | Throughout system |  |  |  | Upgrade relay throughout system. | M5_In Service | 2400000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | METC | 4189 | 2012-09-14 | 7936 | 2016-12-20 | CB | 2016-12-31 | METC Breaker Replacement 2016 | Throughout system |  |  |  | Replace defective breakers throughout system | M5_In Service | 9000000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 9000000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4193 | 2013-09-13 | 7940 | 2016-12-20 | TEQ | 2016-12-31 | METC Battery Replacement 2016 | Throughout system |  |  |  | Replace battery chargers with the new ones. | M5_In Service | 120000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 120000 | 0% |  | 0
A in MTEP13 | East | METC | 4203 | 2013-06-13 | 7950 | 2016-12-20 | TEQ | 2016-12-31 | METC Disconnect Switch Replacement Program 2016 | Throughout system |  |  |  | Replace problematic Pennsylvania Type A6A-2, EEE, RI&E, WESTINGHOUSE, HK-PORTER, AND DELTA-STAR disconnect switches (or any disconnect switches with problematic auxiliary latch assemblies) | M5_In Service | 900000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 900000 | 0% |  | 0
A in MTEP13 | East | METC | 4205 | 2012-09-14 | 7952 | 2016-12-20 | TEQ | 2016-12-31 | METC Annual Relay Betterment Program 2016 | Throughout system |  |  |  | Replace damaged or defective relays. | M5_In Service | 7000000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 7000000 | 0% | Updated cost for future year. | 0
A in MTEP13 | East | METC | 4207 | 2016-08-30 | 7954 | 2016-12-20 | TEQ | 2016-12-31 | METC Power Plant Control Relocation 2016 | Throughout system |  |  |  | Replace controls for METC substations that currently exist in power plant buildings. Locate new controls in dedicated METC control houses. | M5_In Service | 2400000 |  |  | MI |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2400000 | 0% |  | 0
A in MTEP13 | East | METC | 4218 | 2016-12-20 | 7965 | 2017-01-26 | LNup | 2017-01-13 | Bass Creek | Black River | 1 | 138 |  | Remediate the sag limit on the Bass Creek - Black River 138kV line up its conductor rating of 208 MVA (871 A) | M5_In Service | 180000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-06-30 | M4_Pre-Construction | 180000 | 0% |  | 7
A in MTEP13 | West | MP | 3531 | 2015-08-10 | 6591 | 2015-06-12 | SUB | 2015-12-15 | Deer River Substation | Substation Equipment |  | 230 | 115 | New Substation with 230/115 kV 187 MVA Transformer (spare transformer) | Under Construction | 2000000 | Engineering |  | MN |  |  | 187 | 205.7 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-12-15 | Under Construction | 2000000 | 0% |  | 0
A in MTEP13 | West | MP | 3531 | 2015-08-10 | 7672 | 2015-06-12 | TX | 2015-12-15 | Deer River Substation | Substation Equipment |  | 230 | 115 | New Substation with 230/115 kV 187 MVA Transformer | Under Construction | 10309809 | Engineering |  | MN |  | 0.25 | 187 | 205.7 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-12-15 | Under Construction | 10309809 | 0% | shifting cost around between facilities | 0
A in MTEP13 | West | MP | 3531 | 2015-08-10 | 7673 | 2015-06-12 | Dist | 2015-12-15 | Deer River Substation | Substation Equipment |  | 115 | 23 | New 115/23 kV 10 MVA transformer | Under Construction | 348488 | Engineering |  | MN |  |  | 10 | 11 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2015-12-15 | Under Construction | 348488 | 0% | Shifting cost around between facilities | 0
A in MTEP13 | West | MP | 3531 | 2015-08-10 | 7685 | 2015-06-12 | LN | 2016-11-08 | GRE Deer River | MP Deer River |  | 115 |  | New 115 kV line to complete the loop in Deer River | Under Construction | 2197441 | Engineering |  | MN | 1 | 0.75 | 122 | 134.2 | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-11-08 | Under Construction | 2197441 | 0% |  | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8124 | 2017-01-16 | LNup | 2016-03-02 | Arrowhead | 16 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 990207 | Planning |  | MN | 44.76 | 0 | 55 | 60.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1907155.88 | -48.08% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8125 | 2017-01-16 | LNup | 2015-06-19 | Arrowhead | Cloquet | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 311078 | Planning |  | MN | 10.51 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 430220.59 | -27.69% | Actuals may vary widely when discrepancies are known | -18
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8126 | 2017-01-16 | LNup | 2016-03-02 | Arrowhead | Colbyville | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 1617690 | Planning |  | MN | 19.24 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 808573.53 | 100.1% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8127 | 2017-01-16 | LNup | 2015-03-12 | Arrowhead | Haines Road | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 200231 | Planning |  | MN | 7.6 | 0 | 135 | 148.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 315867.65 | -36.61% | Actuals may vary widely when discrepancies are known | -21
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8128 | 2017-01-16 | LNup | 2015-08-09 | Arrowhead | Hibbard | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 119025 | Planning |  | MN | 10.73 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 430608.82 | -72.36% | Actuals may vary widely when discrepancies are known | -16
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8129 | 2017-01-16 | LNup | 2016-11-30 | Arrowhead | 15th Ave West | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 44811 | Planning |  | MN | 11.86 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 493094.12 | -90.91% | Actuals may vary widely when discrepancies are known | -1
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8131 | 2017-01-16 | LNup | 2016-03-25 | Badoura | Dog Lake | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 428878 | Planning |  | MN | 33.99 | 0 | 58 | 63.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1427750 | -69.96% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8132 | 2017-01-16 | LNup | 2016-12-16 | Badoura | Hubbard | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 138604 | Planning |  | MN | 14.77 | 0 | 91 | 100.1 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 619211.76 | -77.62% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8133 | 2017-01-16 | LNup | 2014-10-31 | Badoura | Akeley | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 340938 | Planning |  | MN | 9.41 | 0 | 122 | 134.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 367788.24 | -7.3% | Actuals may vary widely when discrepancies are known | -26
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8134 | 2017-01-16 | LNup | 2015-03-11 | Blackberry | 9 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 64896 | Planning |  | MN | 32.83 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% | Majority of cost incorporated into 9L Rebuild (Prj #3373) | -21
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8135 | 2017-01-16 | LNup | 2016-07-13 | Colbyville | Two Harbors | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 654233 | Planning |  | MN | 22.98 | 0 | 118 | 129.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 984882.35 | -33.57% | Actuals may vary widely when discrepancies are known | -5
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8136 | 2017-01-16 | LNup | 2016-11-02 | Blanchard | Pepin Lake | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 760169 | Planning |  | MN | 14.27 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 618329.41 | 22.94% | Actuals may vary widely when discrepancies are known | -1
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8137 | 2017-01-16 | LNup | 2016-05-04 | Blanchard | Little Falls | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 595366 | Planning |  | MN | 8.4 | 0 | 90 | 99 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 366005.88 | 62.67% | Actuals may vary widely when discrepancies are known | -7
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8138 | 2017-01-16 | LNup | 2014-11-14 | Blandin | 20 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 890122 | Planning |  | MN | 8.32 | 0 | 135 | 148.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 365864.71 | 143.3% | Actuals may vary widely when discrepancies are known | -25
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8140 | 2017-01-16 | LNup | 2015-06-18 | Boise | International Falls | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 51659 | Planning |  | MN | 1.4 | 0 | 85 | 93.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 62961.76 | -17.95% | Actuals may vary widely when discrepancies are known | -18
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8141 | 2017-01-16 | LNup | 2016-02-02 | Boswell | Blandin | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 197762 | Planning |  | MN | 7.78 | 0 | 120 | 120 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 316185.29 | -37.45% | Actuals may vary widely when discrepancies are known | -10
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8142 | 2017-01-16 | LNup | 2015-12-11 | Boswell | Nashwauk | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 2364766 | Planning |  | MN | 36.09 | 0 | 120 | 120 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1540673.53 | 53.49% | Actuals may vary widely when discrepancies are known | -12
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8143 | 2017-01-16 | LNup | 2015-10-07 | Boswell | Grand Rapids | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 453958 | Planning |  | MN | 10.73 | 0 | 120 | 120 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 430608.82 | 5.422% | Actuals may vary widely when discrepancies are known | -14
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8144 | 2017-01-16 | LNup | 2016-02-04 | Brainerd | Riverton | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 215915 | Planning |  | MN | 13.1 | 0 | 71 | 78.1 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 555773.53 | -61.15% | Actuals may vary widely when discrepancies are known | -10
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8145 | 2017-01-16 | LNup | 2016-03-01 | Cloquet | 9 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 1044939 | Planning |  | MN | 30.25 | 0 | 78 | 85.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1264873.53 | -17.39% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8147 | 2017-01-16 | LNup | 2016-10-31 | Cromwell | Riverton | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 944200 | Planning |  | MN | 61.15 | 0 | 77 | 84.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 2601482.35 | -63.71% | Actuals may vary widely when discrepancies are known | -2
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8148 | 2017-01-16 | LNup | 2016-04-11 | Dog Lake | 24 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 88063 | Planning |  | MN | 0.65 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 61638.24 | 42.87% | Actuals may vary widely when discrepancies are known | -8
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8149 | 2017-01-16 | LNup | 2015-03-06 | Embarrass | Virginia | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 1207677 | Planning |  | MN | 15.34 | 0 | 90 | 99 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 620217.65 | 94.72% | Actuals may vary widely when discrepancies are known | -21
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8150 | 2017-01-16 | LNup | 2015-06-01 | Embarrass | Babbitt | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 586079 | Planning |  | MN | 26.37 | 0 | 64 | 70.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1111847.06 | -47.29% | Actuals may vary widely when discrepancies are known | -18
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8151 | 2017-01-16 | LNup | 2015-03-22 | ETCO | 16 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 209328 | Planning |  | MN | 1.52 | 0 | 90 | 99 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 63173.53 | 231.4% | Actuals may vary widely when discrepancies are known | -21
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8152 | 2017-01-16 | LNup | 2016-03-10 | Fond Du Lac | Hibbard | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 133899 | Planning |  | MN | 11.5 | 0 | 40 | 44 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 492458.82 | -72.81% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8153 | 2017-01-16 | LNup | 2016-11-30 | Forbes | ETCO | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 836540 | Planning |  | MN | 6.28 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 253047.06 | 230.6% | Actual cost based on field condition. Preliminary estimates were based on per unit assumptions | -1
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8154 | 2017-01-16 | LNup | 2016-04-28 | Forbes | 44 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 932150 | Planning |  | MN | 17.83 | 0 | 85 | 93.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 733829.41 | 27.03% | Actuals may vary widely when discrepancies are known | -8
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8155 | 2017-01-16 | LNup | 2015-03-11 | Forbes | 78 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 930875 | Planning |  | MN | 15.87 | 0 | 113 | 124.3 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 669879.41 | 38.96% | Actuals may vary widely when discrepancies are known | -21
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8156 | 2017-01-16 | LNup | 2016-09-16 | Gary | Stinson | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 176991 | Planning |  | MN | 11.05 | 0 | 207 | 227.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 491664.71 | -64% | Actuals may vary widely when discrepancies are known | -3
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8157 | 2017-01-16 | LNup | 2016-12-16 | Grand Rapids | Riverton | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 1134513 | Planning |  | MN | 67.7 | 0 | 55 | 60.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 2843241.18 | -60.1% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8158 | 2017-01-16 | LNup | 2016-05-02 | Haines Road | Swan Lake Road | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 134727 | Planning |  | MN | 1.32 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 62820.59 | 114.5% | Actuals may vary widely when discrepancies are known | -7
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8159 | 2017-01-16 | LNup | 2016-09-16 | Hibbard | Winter Street | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 22973 | Planning |  | MN | 3.38 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 126947.06 | -81.9% | Actuals may vary widely when discrepancies are known | -3
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8161 | 2017-01-16 | LNup | 2016-02-07 | Hibbing | 14 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 330631 | Planning |  | MN | 5.76 | 0 | 99 | 108.9 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 252129.41 | 31.14% | Actuals may vary widely when discrepancies are known | -10
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8162 | 2017-01-16 | LNup | 2014-06-30 | Hibbing | 44 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 224525 | Planning |  | MN | 1.72 | 0 | 91 | 100.1 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 63526.47 | 253.4% | Actuals may vary widely when discrepancies are known | -30
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8165 | 2017-01-16 | LNup | 2016-07-12 | Hibbtac | 78 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 625190 | Planning |  | MN | 7.75 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 316132.35 | 97.76% | Actuals may vary widely when discrepancies are known | -5
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8167 | 2017-01-16 | LNup | 2016-12-16 | Hilltop | 15th Ave West | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 25081 | Planning |  | MN | 4.57 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 189538.24 | -86.77% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8168 | 2017-01-16 | LNup | 2015-06-18 | Hilltop | LSPI | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 9817 | Planning |  | MN | 2.91 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 126117.65 | -92.22% | Actuals may vary widely when discrepancies are known | -18
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8169 | 2017-01-16 | LNup | 2016-09-16 | Hoyt Lakes | Laskin | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 267535 | Planning |  | MN | 5.75 | 0 | 168 | 184.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 252111.76 | 6.118% | Actuals may vary widely when discrepancies are known | -3
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8171 | 2017-01-16 | LNup | 2016-09-21 | International Falls | Fort Frances | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 94113 | Planning |  | MN | 2.19 | 0 | 180 | 198 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 125288.24 | -24.88% | Actuals may vary widely when discrepancies are known | -3
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8172 | 2017-01-16 | LNup | 2016-04-07 | Laskin | Embarrass | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 136746 | Planning |  | MN | 10.23 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 429726.47 | -68.18% | Actuals may vary widely when discrepancies are known | -8
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8173 | 2017-01-16 | LNup | 2015-02-18 | Laskin | Forbes | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 341767 | Planning |  | MN | 31.41 | 0 | 113 | 124.3 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1302214.71 | -73.75% | Actuals may vary widely when discrepancies are known | -22
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8174 | 2017-01-16 | LNup | 2014-12-30 | Laskin | Virginia | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 341621 | Planning |  | MN | 25.86 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1110947.06 | -69.25% | Actuals may vary widely when discrepancies are known | -24
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8175 | 2017-01-16 | LNup | 2016-06-02 | Little Falls | West St. Cloud | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 738117 | Planning |  | MN | 17.57 | 0 | 103 | 113.3 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 745135.29 | -0.9419% | Actuals may vary widely when discrepancies are known | -6
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8177 | 2017-01-16 | LNup | 2016-12-08 | Long Prairie | Pepin Lake | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 842450 | Planning |  | MN | 12.69 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 555050 | 51.78% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8178 | 2017-01-16 | LNup | 2016-05-03 | Long Prairie | Douglas County | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 371198 | Planning |  | MN | 9.37 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 367717.65 | 0.9465% | Actuals may vary widely when discrepancies are known | -7
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8182 | 2015-04-13 | LNup | 2016-12-31 | Mud Lake | Brainerd | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 189238.24 | Planning |  | MN | 4.4 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 189238.24 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8183 | 2015-04-13 | LNup | 2016-12-31 | Mud Lake | Little Falls | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1176061.76 | Planning |  | MN | 28.48 | 0 | 71 | 78.1 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1176061.76 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8184 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | 14 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 178320.59 | Planning |  | MN | 4.88 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 178320.59 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8185 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | National | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 252958.82 | Planning |  | MN | 6.23 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 252958.82 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8186 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | Blackberry | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 555879.41 | Planning |  | MN | 13.16 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 555879.41 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8187 | 2015-04-13 | LNup | 2016-12-31 | Nashwauk | Blackberry | 2 | 115 |  | NERC facility ratings alert mitigation | Planned | 555791.18 | Planning |  | MN | 13.11 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 555791.18 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8190 | 2017-01-16 | LNup | 2016-03-04 | Ridgeview | Colbyville | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 294489 | Planning |  | MN | 9.1 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 367241.18 | -19.81% | Actuals may vary widely when discrepancies are known | -9
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8191 | 2015-04-13 | LNup | 2016-12-31 | Riverton | Pequot Lakes | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 808450 | Planning |  | MN | 19.17 | 0 | 58 | 63.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 808450 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8192 | 2015-04-13 | LNup | 2016-12-31 | Riverton | Baxter | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 556391.18 | Planning |  | MN | 13.45 | 0 | 77 | 84.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 556391.18 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8193 | 2015-04-13 | LNup | 2016-12-31 | Savanna | 9 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 0 | Planning |  | MN | 12.98 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 0 | 0% | Cost incorporated into Savanna (Prj #2634) | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8194 | 2015-04-13 | LNup | 2016-12-31 | Scearcyville | 24 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 694802.94 | Planning |  | MN | 16.66 | 0 | 77 | 84.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 694802.94 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8197 | 2015-04-13 | LNup | 2016-12-31 | Shannon | Hibbtac Pumps | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 315744.12 | Planning |  | MN | 7.53 | 0 | 217 | 238.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 315744.12 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8198 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Fairmount Park | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 126400 | Planning |  | MN | 3.07 | 0 | 175 | 192.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 126400 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8199 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Bayfront | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1110752.94 | Planning |  | MN | 25.75 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1110752.94 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8200 | 2015-04-13 | LNup | 2016-12-31 | Stinson | Stone Lake | 1 | 161 |  | NERC facility ratings alert mitigation | Planned | 1794126.47 | Planning |  | MN | 42.6 | 0 | 168 | 184.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1794126.47 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8201 | 2015-04-13 | LNup | 2016-12-31 | Swan Lake Road | Ridgeview | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 126047.06 | Planning |  | MN | 2.87 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 126047.06 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8204 | 2015-04-13 | LNup | 2016-12-31 | Taconite Harbor | Silver Bay | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1048691.18 | Planning |  | MN | 24.86 | 0 | 159 | 174.9 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1048691.18 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8205 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Fond Du Lac | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 64373.53 | Planning |  | MN | 2.2 | 0 | 90 | 99 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 64373.53 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8206 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Potlatch | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 302832.35 | Planning |  | MN | 6.88 | 0 | 84 | 92.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 302832.35 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8207 | 2015-04-13 | LNup | 2016-12-31 | Thomson | Cromwell | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1175302.94 | Planning |  | MN | 28.05 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1175302.94 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8208 | 2015-04-13 | LNup | 2016-12-31 | Verndale | 24 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 670761.76 | Planning |  | MN | 16.37 | 0 | 77 | 84.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 670761.76 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8209 | 2015-04-13 | LNup | 2016-12-31 | Verndale | Wing River | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 62397.06 | Planning |  | MN | 1.08 | 0 | 98 | 107.8 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 62397.06 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8210 | 2015-04-13 | LNup | 2016-12-31 | Virginia | 16 Line Tap | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 443061.76 | Planning |  | MN | 11.12 | 0 | 90 | 99 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 443061.76 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8211 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Hibbing | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1236958.82 | Planning |  | MN | 28.71 | 0 | 55 | 60.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1236958.82 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8212 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Inland | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 188602.94 | Planning |  | MN | 4.04 | 0 | 120 | 132 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 188602.94 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8214 | 2015-04-13 | LNup | 2016-12-31 | Virginia | Minntac | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 253011.76 | Planning |  | MN | 6.26 | 0 | 144 | 158.4 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 253011.76 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8215 | 2015-04-13 | LNup | 2016-12-31 | Wing River | Long Prairie | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 1302550 | Planning |  | MN | 31.6 | 0 | 85 | 93.5 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1302550 | 0% | Actuals may vary widely when discrepancies are known | 0
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8216 | 2017-01-16 | LNup | 2016-09-16 | Winter Street | Fairmount Park | 1 | 115 |  | NERC facility ratings alert mitigation | M5_In Service | 127421 | Planning |  | MN | 3.48 | 0 | 182 | 200.2 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 127123.53 | 0.234% | Actuals may vary widely when discrepancies are known | -3
A in MTEP13 | West | MP | 4294 | 2015-04-13 | 8218 | 2017-01-16 | LNup | 2015-04-08 | Riverton 230 | Riverton 115 | 1 | 115 |  | NERC facility ratings alert mitigation | Planned | 52937 | Planning |  | MN | 0.68 | 0 | 217 | 238.7 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1200 | 4311% | Actuals may vary widely when discrepancies are known | -20
A in MTEP13 | West | OTP | 3667 | 2012-09-28 | 6829 | 2015-05-12 | LN | 2015-11-30 | Nunda | Rutland | 1 | 41.6 | 41.6 | Rebuild 8 miles of 41.6 kV line | Under Construction | 466000 | Planning |  | SD | 8 |  | 34 MVA |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-11-30 | Under Construction | 466000 | 0% |  | 0
A in MTEP13 | West | OTP | 4233 | 2017-03-28 | 7989 | 2017-03-28 | TX | 2017-07-31 | Parshall 41.6kV sub | Parshall 41.6kv/24kV sub | 1 | 41.6 | 24 | Adding new transformer 10 MVA | M3_Long Lead Materials | 500000 | Planning |  | ND |  |  | 10 | 25 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-05-01 | M3_Long Lead Materials | 500000 | 0% | Project delay | 2
A in MTEP13 | East | WPSC | 4084 | 2015-04-03 | 7737 | 2016-09-15 | LNrb | 2018-12-31 | North Shade | Vestaburg | 1 | 69 |  | Rebuild Line (Poles have reached the end of their useful life) | Planned | 10000000 |  |  | MI | 19.29 |  | 143.4MVA | 143.4MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 10000000 | 0% | Updated in 2015 planning review | 0
A in MTEP13 | East | WPSC | 4085 | 2015-04-03 | 7738 | 2017-03-07 | LNrb | 2016-12-31 | Lake County | Fountain Junction | 1 | 69 |  | Rebuild Overloaded line (Peak case) | Planned | 3100000 |  | 2013 | MI | 6.35 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 3100000 | 0% | Increased estimated cost in 2015 planning review. | 0
A in MTEP13 | West | XEL | 4224 | 2012-09-14 | 7972 | 2016-12-21 | LNrb | 2020-12-01 | Ironwood | Northside | 1 | 34.5 |  | Rebuild .5 mile protion of existing line, Replace in-line disconnect with three-way GOAB switch | Withdrawn | 475000 | Planning |  | WI | 0.5 |  | 16 MVA | 18 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 475000 | 0% |  | 0
A in MTEP13 | West | XEL | 4224 | 2012-09-14 | 7973 | 2016-12-21 | LNrb | 2020-12-01 | Ironwood | Kimball (DPC) | 1 | 34.5 |  | Rebuild .5 mile protion of existing line, Replace in-line disconnect with three-way GOAB switch | Withdrawn | 475000 | Planning |  | WI | 0.5 |  | 22 MVA | 24 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 475000 | 0% |  | 0
A in MTEP13 | West | XEL | 4224 | 2012-09-14 | 7974 | 2017-06-24 | SUB | 2019-12-01 | Ironwood | Ironwood |  | 34.5 |  | Relay setting updates, install 34.5 kV voltage regulator | Withdrawn | 75000 | Planning |  | WI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2020-12-01 | Planned | 200000 | -62.5% |  | -12
A in MTEP13 | West | XEL | 4305 | 2013-01-10 | 8236 | 2017-03-23 | SUB | 2017-07-01 | Yankee |  |  | 115 |  | Install 1x25 MVAr switched inductor | Under Construction | 4300000 | Planning |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-03-01 | Under Construction | 4300000 | 0% | delays and increase costs in construction due to re mobilization into 2017 | 4
A in MTEP13 | West | XEL | 4305 | 2013-01-10 | 8237 | 2017-06-26 | SUB | 2019-01-01 | Fenton |  |  | 115 |  | Install 1x25 MVAr switched inductor | Planned | 4030000 | Planning |  | MN |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 3800000 | 6.053% | Cost increase due to costs change in materials | -5
A in MTEP13 | West | XEL | 4308 | 2013-01-10 | 8243 | 2017-06-24 | LNrb | 2017-07-06 | Cedar Falls | Menomonie | 1 | 69 |  | Rebuilding 5 miles of 4/0 and 336 ACSR conductor between Cedar Falls-Menomonie 69 kV to 795 ACSR. Also, replacing bus work at Cedar Falls from 4/0 to 1590 AAC to increase the rating | M5_In Service | 4087810 | Planning |  | WI |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 4087810 | 0% |  | 7
A in MTEP13 | West | XEL | 4314 | 2013-01-10 | 8251 | 2015-12-28 | LNrb | 2021-12-01 | Bay Front | Saxon Pump | 1 | 88 |  | It is expected to rebuild this line to 115 kV capable 795 ACSR conductor operated at 88 kV. | Planned | 26377500 | Planning |  | WI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-01 | Planned | 26377500 | 0% | Negotiating land rights with BadRiver Indian Reservation and BIA, planning change | 0
A in MTEP13 | West | XEL | 4314 | 2013-01-10 | 8252 | 2015-09-30 | LNrb | 2021-12-01 | Saxon Pump | Norrie | 1 | 88 |  | It is expected to rebuild this line to 115 kV capable 795 ACSR conductor operated at 88 kV. | Planned | 9600000 | Planning |  | WI,MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-01 | Planned | 9600000 | 0% |  | 0
A in MTEP12 | Central | AmerenMO | 3366 | 2015-09-11 | 6237 | 2015-09-11 | CB | 2018-12-01 | Wallen Creek | Install 1200 A breaker and disconnect switches |  | 138 |  | Install 2000 A breaker and 2-2000 A 138 kV motor operated disconnect switches | Planned | 2635000 | Engineering | 2010 | MO |  |  | 240 | 285 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-01 | Planned | 2635000 | 0% |  | 0
A in MTEP12 | West | ATC | 1270 | 2015-09-15 | 1989 | 2015-10-19 | LNup | 2025-06-01 | Arcadian | Waukesha | 2 | 138 |  | Rebuild Ck 2 of Arcadian to Waukesha 138 kV Line | M1_Final SPM or OOC | 23406000 | Engineering |  | WI | 3.88 |  | 504 | 574 | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2025-06-01 | M1_Final SPM or OOC | 23406000 | 0% | Combining total cost estimates for all facilities. Including pre-cert estimate. | 0
A in MTEP12 | West | ATC | 1270 | 2015-09-15 | 1990 | 2015-10-19 | LNup | 2025-06-01 | Arcadian | Waukesha | 1 | 138 |  | Rebuild Ck 1 of Arcadian to Waukesha 138 kV Line | M1_Final SPM or OOC | 0 | Engineering |  | WI | 4.06 |  | 504 | 574 | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2025-06-01 | M1_Final SPM or OOC | 0 | 0% | Current cost estimate | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 6910 | 2017-03-31 | LN | 2016-08-13 | Holmes | Old Mead Road | 1 | 138 |  | New 138kV line from Holmes - Old Mead Road | M1_Final SPM or OOC | 93013000 | Engineering |  | MI |  | 65 | 294 | 402 | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-08-13 | M1_Final SPM or OOC | 101600000 | -8.452% | Total Expenditures decreased. | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 6911 | 2017-03-31 | SUB | 2018-05-13 | North Appleton |  |  | 345 |  | New 345 kV Switchyard North Appleton | M1_Final SPM or OOC | 36812000 | Engineering |  | WI |  |  |  |  | BaseRel | Shared |  | Y | Y | Y | Bottom-Up | A | 2018-05-13 | M1_Final SPM or OOC | 34265000 | 7.433% | Cost estimate update. | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 6912 | 2017-03-31 | LN | 2018-10-25 | North Appleton | Morgan | 1 | 345 |  | New 345 kV line from North Appleton - Morgan | M1_Final SPM or OOC | 120534000 | Engineering |  | WI |  | 40 | 1204 | 1671 | BaseRel | Shared |  | Y | Y | Y | Bottom-Up | A | 2018-10-25 | M1_Final SPM or OOC | 155814000 | -22.64% | Cost estimate update. | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 6919 | 2017-03-31 | SVC | 2017-08-01 | Benson Lake |  | 1 | 138 |  | New 150 MVAR SVC at Benson Lake (near Amberg) | M1_Final SPM or OOC | 32008000 | Engineering |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2017-08-01 | M1_Final SPM or OOC | 40213000 | -20.4% | Cost estimate update. | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 6923 | 2017-03-31 | LN | 2017-03-31 | Morgan | Stiles | 2 | 138 |  | Debifurcate Morgan-Falls-Pioneer-Stiles 138 kV ckt to form new Morgan-Stiles 138 kV ckt | M1_Final SPM or OOC | 6636000 | Engineering |  | WI |  | 11 | 294 | 402 | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2017-03-31 | M1_Final SPM or OOC | 6669000 | -0.4948% | Cost estimate update. | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 7242 | 2017-03-31 | TX | 2016-08-13 | Old Mead Road |  | 2 | 138 | 69 | Add new 2nd 138/69 kV Transformer at Old Mead Road | M1_Final SPM or OOC | 1496000 | Engineering |  | MI |  |  | 60 | 75 | BaseRel | Shared |  | N | N | Y | Bottom-Up | A | 2016-08-13 | M1_Final SPM or OOC | 4300000 | -65.21% |  | 0
A in MTEP12 | West | ATC | 3679 | 2014-06-13 | 7243 | 2017-03-31 | SUB | 2018-10-25 | Morgan |  |  | 345 |  | Morgan 345 kV substation expansion | M1_Final SPM or OOC | 15296000 | Engineering |  | WI |  |  |  |  | BaseRel | Shared |  | Y | Y | Y | Bottom-Up | A | 2018-10-25 | M1_Final SPM or OOC | 13987000 | 9.359% | Cost estimate update. | 0
A in MTEP12 | West | ATC | 3952 | 2014-06-13 | 6926 | 2017-03-31 | TX | 2018-05-13 | North Appleton |  | 1 | 345 | 138 | New 345/138kV Transformer at North Appleton | M1_Final SPM or OOC | 2942000 | Engineering |  | WI |  |  | 500 | 625 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-05-13 | M1_Final SPM or OOC | 7700000 | -61.79% | Routes are longer than earlier assumed, some rebuilding of existing lines was not assumed in the original estimate, more work at end point substations than was anticipated, enhanced security at North Appleton Substation, additional work at remote substati | 0
A in MTEP12 | West | ATC | 3952 | 2014-06-13 | 6927 | 2017-03-31 | LN | 2018-10-28 | North Appleton | Morgan | 1 | 138 |  | New 138 kV line from North Appleton-Morgan | M1_Final SPM or OOC | 61810000 | Engineering |  | WI |  | 40 | 294 | 402 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-10-28 | M1_Final SPM or OOC | 69011000 | -10.43% | Cost estimate update. | 0
A in MTEP12 | West | BREC | 3792 | 2012-04-20 | 7127 | 2013-06-07 | LN | 2016-01-01 | BR Tap (3 terminal midpoint) | Matanzas (LKE) | 1 | 161 |  | 10.5 Mile 161 kV of line from Wilson Substation to new 161kV station - only 600 feet of new construction required. | Under Construction | 0 | Planning |  | KY |  | 0.2 | 509 | 509 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-01-01 | Under Construction | 0 | 0% |  | 0
A in MTEP12 | Central | DEI | 3542 | 2015-09-15 | 6611 | 2016-11-04 | Dist | 2019-12-31 | New Castle Ingersoll |  |  | 69 | 12 | New Castle Ingersoll 1 Bank 2 Repl ? Replace 34/12kV bank w/22MVA 69/12kV Bank. Add 69kV tap line to existing sub. | Under Construction | 579657 | Engineering | 2011 | IN |  | 0.23 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 579657 | 0% |  | 30
A in MTEP12 | West | GRE | 3470 | 2011-01-11 | 6397 | 2014-03-25 | GEN | 2014-12-31 | G667-200987 | Round Lake Tap |  |  |  | Connection on GRE Round Lake tap | Planned | 722000 | Engineering |  | MN |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2014-12-31 | Planned | 722000 | 0% |  | 0
A in MTEP12 | West | GRE | 11543 | 2016-07-25 | 21785 | 2016-07-25 | TAP | 2018-11-01 | Glacial Ridge |  |  | 69 |  | Install new 69kV 3-way switch structure. | Planned | 150000 | Planning |  | MN |  |  |  |  | GIP |  |  | N | N | NT | Externally Driven | A | 2018-11-01 | Planned | 150000 | 0% |  | 0
A in MTEP12 | West | GRE | 11563 | 2016-07-25 | 21786 | 2017-03-28 | SUB | 2018-09-20 | McHenry |  |  | 115 |  | Install 115 kV ring bus | Planned | 4952173 | Planning | 2012 | ND |  |  |  |  | GIP |  |  | N | N | Y | Externally Driven | A | 2017-11-01 | Planned | 4952173 | 0% |  | 10
A in MTEP12 | West | ITCM | 3627 | 2011-12-13 | 6750 | 2016-12-16 | LN | 2016-12-15 | Chariton | Derby REC | 1 | 69 |  | Rebuild line section. | M5_In Service | 2044831 | Engineering |  | IA | 4.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 2044831 | 0% | Planning level estimate updated with engineering estimates. | 0
A in MTEP12 | West | ITCM | 3627 | 2011-12-13 | 6751 | 2016-12-16 | LN | 2016-12-15 | Millerton | Derby REC | 1 | 69 |  | Rebuild line section. | M5_In Service | 3862451 | Engineering |  | IA | 8.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 3862451 | 0% | Planning level estimate updated with engineering estimates. | 0
A in MTEP12 | West | ITCM | 3627 | 2011-12-13 | 6752 | 2016-12-16 | LN | 2016-12-15 | Millerton | Corydon | 1 | 69 |  | Rebuild line section. | M5_In Service | 2444704 | Engineering |  | IA | 5.38 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-30 | Under Construction | 2444704 | 0% | Planning level estimate updated with engineering estimates. | 0
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 6733 | 2015-06-30 | LN | 2017-08-25 | General Foods | Northwest Tap | 1 | 69 |  | Build a new 69kV line from the General Foods substation to the Northwest substation. | M1_Final SPM or OOC | 1494000 | Engineering |  | IA |  |  | 77 MVA | 77 MVA | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 1494000 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | 0
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 6734 | 2015-06-30 | LN | 2017-08-25 | Holnam | Lehigh | 1 | 69 |  | Retire the existing Lehgihg to Holnam 69kV line section | M1_Final SPM or OOC | 270000 | Engineering |  | IA |  |  | 77 MVA | 77 MVA | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 270000 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | 0
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 6735 | 2017-06-30 | SUB | 2017-04-28 | Nettle | Substation | 1 | 69 |  | New 3 terminal Nettle Lehigh area switch station | M5_In Service | 3135600 | Engineering |  | IA |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 3135600 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | -4
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 6736 | 2015-06-30 | SUB | 2017-08-25 | Lehigh | Substation | 1 | 69 |  | Retire the existing Lehigh switch station | M1_Final SPM or OOC | 60000 | Engineering |  | IA |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 60000 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | 0
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 9082 | 2015-06-30 | LN | 2017-08-25 | Nettle | Northwest Switch Station | 1 | 69 |  | Rebuild the Nettle to old Lehigh site 69kV line and install OPGQ to NWSS. | M1_Final SPM or OOC | 1305600 | Engineering |  | IA |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 1305600 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | 0
A in MTEP12 | West | ITCM | 3628 | 2011-12-13 | 9083 | 2015-06-30 | LN | 2017-08-25 | Holnam | New 69kV Tap | 1 | 69 |  | Install new GOAB and 69kV tap | M1_Final SPM or OOC | 490000 | Engineering |  | IA |  |  |  |  | Other |  | Relocation | N | N | Y | Bottom-Up | A | 2017-08-25 | M1_Final SPM or OOC | 490000 | 0% | New location is 1.5 miles west and will require reconfiguration changes that increased costs on 3628 and 4107. | 0
A in MTEP12 | West | ITCM | 3629 | 2013-06-27 | 6744 | 2017-01-11 | LN | 2017-01-09 | 8th Street | Salem | 1 | 161 | 69 | Build 3.5 miles of new 161kV line, 8th Street sub work, Salem sub work | M5_In Service | 7222073 | Engineering |  | IA |  | 3.5 |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 7222073 | 0% | Planning estimate updated with Engineering estimate. | 1
A in MTEP12 | West | ITCM | 3629 | 2013-06-27 | 6745 | 2017-01-11 | SUB | 2017-01-09 | Salem | Substation | 1 | 161 |  | Add new 161kV terminal and 161kv bus tie breaker | M5_In Service | 0 | Planning |  | IA |  |  | 558 MVA | 558 MVA | BaseRel | Shared |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | 1
A in MTEP12 | West | ITCM | 3629 | 2013-06-27 | 6746 | 2017-01-11 | SUB | 2017-01-09 | 8th Street | Substation | 1 | 161 |  | Add new 161kV terminal and reroute line to new terminal. | M5_In Service | 0 | Planning |  | IA |  |  | 558 MVA | 558 MVA | BaseRel | Shared |  | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 0 | 0% |  | 1
A in MTEP12 | West | ITCM | 3630 | 2011-12-13 | 6739 | 2017-06-30 | LN | 2023-12-31 | Adams | Stewartvillle 6th Street | 1 | 69 |  | Rebuild 69kV line to T2-4/0 ACSR | Planned | 10500000 | Planning |  | IA | 29.88 |  | 77 MVA | 77 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 10500000 | 0% |  | 60
A in MTEP12 | West | ITCM | 3630 | 2011-12-13 | 6740 | 2017-06-30 | LN | 2023-12-31 | Stewartvillle 6th Street | Stewartville Junction | 1 | 69 |  | Rebuild 69kV line to T2-4/0 ACSR | Planned | 1700000 | Planning |  | IA | 4.68 |  | 77 MVA | 77 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-12-31 | Planned | 1700000 | 0% |  | 60
A in MTEP12 | West | ITCM | 3631 | 2011-12-13 | 6772 | 2017-06-29 | LN | 2017-06-06 | Rock Creek | CMP NT | 1 | 69 |  | Rebuild the 69kV line section | M5_In Service | 862402 | Planning |  | IA | 1.2 |  | 140 MVA | 140 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 1250000 | -31.01% |  | -6
A in MTEP12 | West | ITCM | 3631 | 2011-12-13 | 6773 | 2017-06-29 | LN | 2017-06-06 | CMP NT | Mill Creek | 1 | 69 |  | Rebuild the 69kV line section | M5_In Service | 0 | Planning |  | IA | 3.6 |  | 140 MVA | 140 MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 1250000 | -100% | This line section is not being rebuilt. | -6
A in MTEP12 | West | ITCM | 3632 | 2011-12-13 | 6753 | 2017-03-08 | SUB | 2018-12-30 | Arnold | Substation | 1 | 161 |  | Add two new 161kV breakers and reroute Hiawatha line terminal off the generation bus. | Planned | 2529402 | Planning |  | IA |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2400000 | 5.392% | Updated with 2016 dollars and engineering level estimate. | 12
A in MTEP12 | West | ITCM | 3638 | 2011-12-13 | 6755 | 2017-06-29 | SUB | 2018-03-30 | Corydon | Substation | 1 | 69 |  | Complte rebuild of the Corydon sub | M1_Final SPM or OOC | 5129204 | Planning |  | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 5129204 | 0% | Old sub site was space constrained and a greenfield site was chosen and the additional line work to re-terminate 69kV lines increased the cost. | 3
A in MTEP12 | West | ITCM | 3639 | 2011-12-13 | 6754 | 2017-06-30 | SUB | 2017-03-24 | Chariton | Substation | 1 | 69 |  | Complte rebuild of the Chariton sub | M5_In Service | 7683367 | Planning |  | IA |  |  | 143 MVA | 143 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-09-02 | Under Construction | 7683367 | 0% | Due to space constraints and difficulty obtaining outages, a new site in close proximity was chosen. The new sub name will be Court substation. | 6
A in MTEP12 | West | ITCM | 3640 | 2011-12-13 | 6761 | 2016-06-30 | LN | 2018-12-31 | Belmond | Meservey Tap | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 1627500 | Planning |  | IA | 4.65 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 1627500 | 0% |  | 0
A in MTEP12 | West | ITCM | 3643 | 2011-12-13 | 6765 | 2016-06-30 | LN | 2022-12-31 | Osceola | Woodburn Junction | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 1950000 | Planning |  | IA | 5.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | M1_Final SPM or OOC | 1950000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3644 | 2011-12-13 | 6766 | 2016-06-30 | LN | 2021-12-31 | Knoxville | Lucas | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 3750000 | Planning |  | IA | 10.6 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 3750000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3645 | 2011-12-13 | 6767 | 2014-06-13 | LN | 2017-12-31 | Triboji | Montgomery | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 2000000 | Planning |  | IA | 5.75 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 2000000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3645 | 2011-12-13 | 6768 | 2014-06-13 | LN | 2017-12-31 | Bosworth | Montgomery | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 750000 | Planning |  | IA | 2.16 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 750000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3645 | 2011-12-13 | 6769 | 2014-06-13 | LN | 2017-12-31 | Bosworth | Spirti Lake | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 400000 | Planning |  | IA | 1.17 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 400000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3645 | 2011-12-13 | 6770 | 2014-06-13 | LN | 2017-12-31 | Spirti Lake | Orleans Tap | 1 | 69 |  | Rebuild the 69kV line section | M1_Final SPM or OOC | 200000 | Planning |  | IA | 0.4 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 200000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 6812 | 2015-12-30 | LN | 2017-01-13 | Ryan REC | Ryan REC tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 350000 | Planning |  | IA | 1 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-01-13 | M1_Final SPM or OOC | 350000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 6813 | 2015-04-14 | LN | 2017-12-31 | Cascade Muni | Cascade Muni Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 350000 | Planning |  | IA | 1 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-12-31 | M1_Final SPM or OOC | 350000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 6814 | 2014-06-13 | LN | 2015-12-31 | Clarence | Clarence Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 350000 | Planning |  | IA | 1 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | M1_Final SPM or OOC | 350000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 6815 | 2015-12-30 | LN | 2018-06-01 | Clarence | Wyoming | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 3850000 | Planning |  | IA | 11 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-06-01 | M1_Final SPM or OOC | 3850000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 6816 | 2015-12-30 | LN | 2017-04-28 | Prairie Creek | Bertam JU | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 2100000 | Planning |  | IA | 6 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-04-28 | M1_Final SPM or OOC | 2100000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7109 | 2015-12-30 | LN | 2016-12-31 | Coggon | Manchester Industrial | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 0 | Planning |  | IA |  | 2.5 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7110 | 2015-12-30 | LN | 2018-12-31 | Rome Tap | Rome | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 700000 | Planning |  | IA |  | 2 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 700000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7111 | 2015-12-30 | LN | 2018-12-31 | Clarence | Clarence REC | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 700000 | Planning |  | IA |  | 2 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 700000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7112 | 2015-12-30 | LN | 2018-12-31 | Manchester Tap | Manchester Industrial | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 175000 | Planning |  | IA |  | 0.5 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 175000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7113 | 2016-06-30 | LN | 2017-09-28 | Mt Vernon | Lisbon | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 1400000 | Planning |  | IA | 2 | 2 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-09-28 | M1_Final SPM or OOC | 1400000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7114 | 2015-12-30 | LN | 2019-12-31 | PCI | Putnam | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 175000 | Planning |  | IA |  | 0.5 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 175000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7115 | 2014-06-13 | LN | 2015-12-31 | Zwingle | Mosalem REC | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 2800000 | Planning |  | IA |  | 8 | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | M1_Final SPM or OOC | 2800000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3647 | 2011-12-13 | 7116 | 2015-12-30 | LN | 2021-12-31 | Dixon | Fulton | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 5950000 | Planning |  | IA | 17 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-12-31 | M1_Final SPM or OOC | 5950000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6791 | 2015-12-30 | LN | 2019-12-31 | Boone Jct | Ridgeport REC | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 1200000 | Planning |  | IA | 2.75 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 1200000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6798 | 2017-06-30 | LN | 2017-08-31 | Marion | Nevada Street | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | Under Construction | 500000 | Planning |  | IA | 1.4 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-03-17 | M1_Final SPM or OOC | 500000 | 0% |  | 5
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6799 | 2014-06-13 | LN | 2015-12-31 | Gilbert | Ames | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 2000000 | Planning |  | IA | 4.7 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | M1_Final SPM or OOC | 2000000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6800 | 2014-06-13 | LN | 2015-12-31 | Story City | Ames | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 1200000 | Planning |  | IA | 3.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | M1_Final SPM or OOC | 1200000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6801 | 2014-06-13 | LN | 2015-12-31 | William Bros Pipline | Roland | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 500000 | Planning |  | IA | 2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2015-12-31 | M1_Final SPM or OOC | 500000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6802 | 2017-06-30 | LN | 2017-08-31 | Ames Mine | Ames Mine Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 300000 | Planning |  | IA | 1.5 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2017-03-17 | M1_Final SPM or OOC | 300000 | 0% |  | 5
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6803 | 2015-12-30 | LN | 2018-03-23 | Quartz Ave | Boone South | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 1700000 | Planning |  | IA | 5.2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2018-03-23 | M1_Final SPM or OOC | 1700000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6804 | 2016-11-08 | LN | 2018-03-23 | Boone South | Valley RECTap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 400000 | Planning |  | IA | 1.15 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-07-11 | Under Construction | 400000 | 0% |  | 20
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6805 | 2016-06-30 | LN | 2019-02-28 | Valley RECTap | Odgen Muni Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M1_Final SPM or OOC | 600000 | Planning |  | IA | 1.7 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2019-02-28 | M1_Final SPM or OOC | 600000 | 0% |  | 0
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6806 | 2016-11-08 | LN | 2016-07-05 | Boone Jct | Clear Lake Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M5_In Service | 1200000 | Planning |  | IA | 3.4 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-02-12 | Under Construction | 1200000 | 0% |  | 5
A in MTEP12 | West | ITCM | 3648 | 2011-12-13 | 6807 | 2017-06-30 | LN | 2017-05-25 | Ames NADC | Ames Mine Tap | 1 | 34 |  | Rebuild the 34kV line section to 69kV for future conversion | M5_In Service | 700000 | Planning |  | IA | 2 |  | 77 MVA | 77 MVA | Other |  | Condition | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 700000 | 0% |  | 5
A in MTEP12 | West | ITCM | 3649 | 2011-12-13 | 6758 | 2017-06-30 | SUB | 2025-12-31 | Plaza | Substation | 1 | 161 |  | New Plaza 161/12.5kV substation with 161kV in and out breakers and bus tie breaker | M1_Final SPM or OOC | 1550000 | Planning |  | IA |  |  | 143 MVA | 143 MVA | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-12-31 | M1_Final SPM or OOC | 1550000 | 0% |  | 60
A in MTEP12 | West | ITCM | 3649 | 2011-12-13 | 6759 | 2017-06-30 | LN | 2025-12-31 | Plaza | Timber Creek | 1 | 161 |  | Tap the Marshalltown-Timber Creek 161kV for new Plaza sub. | M1_Final SPM or OOC | 100000 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-12-31 | M1_Final SPM or OOC | 100000 | 0% |  | 60
A in MTEP12 | West | ITCM | 3649 | 2011-12-13 | 6760 | 2017-06-30 | LN | 2025-12-31 | Plaza | Marshalltown | 1 | 161 |  | Tap the Marshalltown-Timber Creek 161kV for new Plaza sub. | M1_Final SPM or OOC | 100000 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-12-31 | M1_Final SPM or OOC | 100000 | 0% |  | 60
A in MTEP12 | East | ITCT | 3591 | 2017-06-30 | 6690 | 2017-06-30 | TEQ | 2017-09-30 | St. Clair |  |  | 345 |  | Replace 345kV station equipment in the B, C and D rows at St. Clair. | Under Construction | 924000 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-05-31 | Under Construction | 924000 | 0% | Updated several year old cost estimate | 16
A in MTEP12 | East | ITCT | 3624 | 2016-03-23 | 6731 | 2016-12-20 | Dist | 2016-12-31 | Blanket for Customer Interconnections 2016 | Throughout system |  | 120 |  | Connect interconnecting entities as requested | M5_In Service | 2000000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2000000 | 0% |  | 0
A in MTEP12 | West | MEC | 3710 | 2014-03-31 | 7023 | 2016-03-30 | SUB | 2021-07-01 | Norwalk |  |  | 161 | 13.2 | Norwalk 161-13 kV XFMR | Planned | 886413 | Planning |  | IA |  |  | 33 | 33 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2021-07-01 | Planned | 886413 | 0% | Refined cost estimate. | 0
A in MTEP12 | East | METC | 3590 | 2015-02-26 | 8297 | 2015-02-26 | SVC | 2030-06-01 | Tippy | SVC |  | 138 |  | Install an svc at tippy sub | Planned | 28500000 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2030-06-01 | Planned | 28500000 | 0% |  | 0
A in MTEP12 | East | METC | 3599 | 2014-03-31 | 6698 | 2015-09-28 | TEQ | 2018-12-31 | Palisades |  |  | 345 |  | Upgrade the station equipment at Palisades in rows 25, 27, and 29 for the existing configuration. | M4_Pre-Construction | 4000000 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2018-12-31 | M4_Pre-Construction | 4000000 | 0% |  | 0
A in MTEP12 | East | METC | 3625 | 2016-03-23 | 6732 | 2016-12-20 | Dist | 2016-12-31 | Blanket for Customer Interconnections 2016 | Throughout system |  | 138 |  | Connect interconnecting entities as requested | M5_In Service | 2500000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | Under Construction | 2500000 | 0% |  | 0
A in MTEP12 | West | XEL | 3769 | 2011-12-13 | 7048 | 2017-06-24 | LN | 2022-03-01 | Carver County | Arlington | 1 | 69 |  | Rebuild 13 miles of 69 kV line to 477 ACSR to reduce impedance and increase capacity | Planned | 4155551 | Planning |  | MN | 13 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-03-01 | Planned | 4155551 | 0% | Cost increase due to delayed ISD. | 36
A in MTEP12 | West | XEL | 3775 | 2011-12-13 | 7070 | 2016-12-21 | TX | 2016-11-22 | Osprey |  |  | 161 | 115 | A 161/115 kV transformer will be added at Osprey and a termiation in the current 115 kV yard | M5_In Service | 6500000 | Scoping |  | WI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2017-01-27 | Under Construction | 7000000 | -7.143% | Sub delayed pending PSCW Minor Route Adjustment approval 161kV line route and DNR wetland permit. | -2
A in MTEP12 | West | XEL | 3797 | 2012-01-07 | 7134 | 2017-06-24 | LN | 2019-05-31 | Maple River | Red River | 2 | 115 |  | New 5 mile 115 kV line | Planned | 11797665 | Planning |  | ND |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-10-31 | Planned | 11797665 | 0% | Cost increase due to ROW estimates increased. | 19
A in MTEP12 | West | XEL | 3797 | 2012-01-07 | 7135 | 2017-06-24 | SUB | 2019-05-31 | Maple River | substation |  | 115 |  | New Line and Termination Work | Planned | 1483410 | Planning |  | ND |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-22 | Planned | 1483410 | 0% | Cost increase due to ROW estimates increased. | 17
A in MTEP12 | West | XEL | 3797 | 2012-01-07 | 7136 | 2017-06-24 | SUB | 2019-05-31 | Red River | substation |  | 115 |  | New Line and Termination Work | Planned | 2338410 | Planning |  | ND |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-22 | Planned | 2338410 | 0% | Cost increase due to ROW estimates increased. | 17
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 4104 | 2016-12-12 | LN | 2016-11-15 | Pana | Faraday | 1 | 345 |  | new line - 35.9 miles of 345 kV | M5_In Service | 69868495 |  | 2014 | IL |  | 35.9 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Planned | 77050763 | -9.321% |  | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 4151 | 2016-12-12 | TX | 2016-11-15 | Faraday | Transformer | 1 | 345 | 138 | new transformer - 560 MVA, 345/138 kV, plus 345 kV ring bus | M5_In Service | 30395701 |  |  | IL |  |  | 560 | 560 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | M3_Long Lead Materials | 22927839 | 32.57% | Actual and estimated material & construction costs are higher than the planning quality estimate costs. | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 4152 | 2017-06-29 | LN | 2018-03-31 | Faraday | Kansas | 1 | 345 |  | new line - 70.2 miles 345 kV | Under Construction | 149030976 |  | 2014 | IL |  | 70.2 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 157278038 | -5.244% | Should not have applied update on 06/29/2017. Revised back to previous number. | -8
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 4154 | 2017-06-30 | LN | 2019-11-15 | Kansas | Sugar Creek | 1 | 345 |  | new line - 34.5 miles 345 kV; Kansas to Indiana State Line | M3_Long Lead Materials | 83394282 |  | 2014 | IL |  | 34.5 | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 86838538 | -3.966% |  | 12
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20772 | 2016-10-19 | LNrl | 2018-11-15 | Faraday | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | Under Construction | 1603555 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2018-11-15 | Planned | 3496405 | -54.14% |  | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20773 | 2016-10-19 | LNrl | 2018-11-15 | Kansas | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 4615179 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2018-11-15 | Planned | 5341519 | -13.6% |  | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20824 | 2016-10-19 | LNrb | 2017-06-01 | Mt. Zion PPG | Mt. Zion Rt. 121 |  | 138 |  | Rebuild 2.37 miles of 795 kcmil ACSR conductor with conductor capable of carrying 2000 A under summer emergency conditions. | M5_In Service | 4026729 | Planning |  | IL | 2.37 |  | 399 | 478 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | Planned | 2345666 | 71.67% | N/A | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20825 | 2016-10-19 | LNrb | 2017-06-01 | Mt. Zion PPG | Route 51 |  | 138 |  | Rebuild 4.43 miles of 795 kcmil ACSR with conductor capable of carrying 2000 A under summer emergency conditions. | Under Construction | 6488978 | Planning |  | IL | 4.43 |  | 399 | 478 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | Planned | 4248992 | 52.72% | Actual and estimated material & construction costs are higher than the planning quality estimate costs. | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20826 | 2016-12-12 | CB | 2016-11-15 | PPG Substation | Install 4-138 kV breakers |  | 138 |  | Install 4 138 kV, 2000 A breakers to accommodate connection of the Faraday (formerly Mt. Zion) 345/138 kV Substation. | M5_In Service | 6355558 | Planning |  | IL |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Planned | 4509333 | 40.94% | N/A | 0
A in MTEP11 | Central | AmerenIL | 2237 | 2011-11-03 | 20827 | 2016-12-12 | LN | 2016-11-15 | Faraday | Mt. Zion PPG | 1 | 138 |  | Build 2 miles of 138 kV line between Faraday 138 kV Substation (formerly Mt. Zion area Substation) and Mt. Zion PPG 138 kV Substation. The new line needs to have a 2000 A summer emergency capability. | M5_In Service | 17075305 | Planning |  | IL |  | 2 | 399 | 478 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Planned | 14386687 | 18.69% | This facility, previously a separate 2 mile section of line construction, has been reconfigured as 2 miles of double-circuit 138 kV line. | 0
A in MTEP11 | West | AmerenIL | 2237 | 2011-11-03 | 20828 | 2016-10-19 | LN | 2016-11-15 | Faraday | Mt. Zion PPG | 2 | 138 |  | Build 2 miles of 138 kV line between Faraday 138 kV Substation (formerly Mt. Zion area Substation) and Mt. Zion PPG 138 kV Substation. The new line needs to have a 2000 A summer emergency capability. | Withdrawn_AltOrScope | 0 | Planning |  | IL |  | 2 | 399 | 478 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Planned | 12759396 | -100% |  | 0
A in MTEP11 | Central | AmerenIL | 2239 | 2011-11-03 | 20774 | 2016-10-19 | LNrl | 2016-06-01 | Rising | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 2098486 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-06-01 | Planned | 5268524 | -60.17% |  | 0
A in MTEP11 | Central | AmerenIL | 2239 | 2011-11-03 | 20775 | 2016-10-19 | LNrl | 2016-06-01 | Sidney | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 5994959 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-06-01 | Planned | 3434896 | 74.53% | Updated cost figure reflects as-constructed costs which were higher than the planning quality estimate costs. | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 4149 | 2017-06-29 | LN | 2017-11-15 | Meredosia | Ipava | 1 | 345 |  | new line - 48.0 miles 345 kV; Includes 1.1 mile Illinois river crossing | Under Construction | 141841823 |  | 2014 | IL |  | 48 | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-11-15 | M3_Long Lead Materials | 139715270 | 1.522% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 4150 | 2017-06-29 | LN | 2017-09-30 | Meredosia | Austin | 1 | 345 |  | new line - 76.5 miles 345 kV | Under Construction | 161929701 |  | 2014 | IL |  | 76.5 | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-11-15 | M3_Long Lead Materials | 176912468 | -8.469% | Should not have applied update on 06/29/2017. Changed estimate back to previous number. | -2
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 5202 | 2016-12-12 | LN | 2016-11-15 | Maywood | Herleman | 1 | 345 |  | new line - 15.2 miles 345 kV; Includes 1.6 mile Mississippi river crossing | M5_In Service | 101864380 |  | 2014 | IL |  | 15.2 | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | M3_Long Lead Materials | 73857213 | 37.92% | Adjusted mileage and cost estimate 10/12/2012. Actual and estimated material & construction costs are higher than the planning quality estimate costs - 10/19/2016 | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 5203 | 2016-12-12 | TX | 2016-11-15 | Herleman | Xfmr Addition | 1 | 345 | 138 | Quincy Area 345/138 kV Substation - 1-560 MVA transformer, 345 kV ring bus. | M5_In Service | 30335735 |  |  | IL |  |  | 450 | 450 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Under Construction | 29311011 | 3.496% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 5227 | 2016-12-12 | LN | 2016-11-15 | Herleman | Meredosia | 1 | 345 |  | new line - 46.6 miles 345 kV; Includes 0.8 mile Illinois river crossing | M5_In Service | 140387611 |  | 2014 | IL |  | 46.6 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | M3_Long Lead Materials | 147551577 | -4.855% |  | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 6430 | 2017-06-29 | TX | 2017-11-15 | Austin | Transformer | 2 | 345 | 138 | 2nd. 345/138, 560 MVA Xfmr, establish 345 kV breaker-and-a-half arrangement at Pawnee | M5_In Service | 39087835 |  |  | IL |  |  | 560 | 560 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-11-15 | M3_Long Lead Materials | 40230142 | -2.839% |  | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 6597 | 2017-06-29 | LN | 2017-06-01 | Ipava |  | 1 | 345 |  | Substation work for new Meredosia-Ipava 345 kV line | M5_In Service | 32550431 |  |  | IL |  |  | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M3_Long Lead Materials | 30284809 | 7.481% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 6968 | 2016-12-12 | TX | 2016-11-15 | Meredosia | Install 345/138 kV Xfmr | 1 | 345 | 138 | Meredosia 345/138 kV Substation - Install 345/138 kV Xfmr, 345 kV ring bus. | M5_In Service | 30401343 |  |  | IL |  |  | 560 | 560 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Under Construction | 29111231 | 4.432% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 20777 | 2016-12-12 | LNrl | 2016-01-10 | Herleman | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 7338406 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-01-10 | Under Construction | 6730984 | 9.024% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 20778 | 2016-12-12 | LNrl | 2016-01-10 | Austin | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 13661079 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-01-10 | Under Construction | 4960087 | 175.4% | Actual and estimated material & construction costs are higher than the planning quality estimate costs. | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 20779 | 2017-06-29 | LNrl | 2017-06-01 | Ipava | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 11211156 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2017-06-01 | Planned | 13131584 | -14.62% |  | 0
A in MTEP11 | Central | AmerenIL | 3017 | 2016-01-27 | 20780 | 2016-12-12 | LNrl | 2016-11-15 | Meredosia | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 12620356 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-11-15 | Planned | 13604236 | -7.232% |  | 0
A in MTEP11 | Central | AmerenIL | 3022 | 2015-04-02 | 5232 | 2017-06-29 | LN | 2018-11-15 | Fargo | Sandburg | 1 | 345 |  | Fargo-Sandburg 345 kV Line - New 39 mile, 3000 A summer emergency capability line. | Under Construction | 88494427 | Budgetary | 2014 | IL |  | 39 |  | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 92100000 | -3.915% | N/A | 0
A in MTEP11 | Central | AmerenIL | 3022 | 2015-04-02 | 6554 | 2017-06-29 | TX | 2017-03-31 | Sandburg | 345/138 kV transformer | 1 | 345 | 138 | new 560 MVA, 345/138 kV xfmr, 345 kV ring bus, and 138 kV breaker-and-a-half at Sandburg | M5_In Service | 32500000 | Budgetary | 2014 | IL |  |  | 560 MVA |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | Planned | 38200000 | -14.92% |  | 4
A in MTEP11 | Central | AmerenIL | 3022 | 2015-04-02 | 6599 | 2016-10-19 | LN | 2016-05-28 | Fargo |  | 1 | 345 |  | Fargo substation work - add a new 345 kV ring bus | M5_In Service | 12200000 | Budgetary | 2014 | IL |  |  |  | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-15 | Planned | 14500000 | -15.86% |  | -7
A in MTEP11 | Central | AmerenIL | 3022 | 2015-04-02 | 20781 | 2016-10-19 | TEQ | 2016-09-14 | Sandburg |  |  | 138 |  | Area Connection work associated with Sandburg. | M5_In Service | 1500000 | Budgetary | 2014 | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-11-15 | Planned | 1500000 | 0% |  | -2
A in MTEP11 | Central | AmerenIL | 3169 | 2017-03-10 | 5600 | 2017-06-29 | LN | 2017-12-31 | Pana | Austin | 1 | 345 |  | new line - 33.6 miles 345 kV | Under Construction | 72455495 |  | 2014 | IL |  | 33.6 | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 78331104 | -7.501% |  | -11
A in MTEP11 | Central | AmerenIL | 3169 | 2017-03-10 | 6431 | 2016-12-12 | TX | 2016-11-15 | Pana | Transformer | 2 | 345 | 138 | Install 2nd. 345/138 kV Xfmr at Pana Sub., 345 kV breaker-and-a-half arrangement at Pana. | M5_In Service | 42620627 |  |  | IL |  |  | 560 | 560 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-11-15 | M3_Long Lead Materials | 42645696 | -0.05878% |  | 0
A in MTEP11 | Central | AmerenIL | 3169 | 2017-03-10 | 20782 | 2016-12-12 | LNrl | 2016-11-15 | Pana | Area Connection Work |  | 345 |  | Rerouting of existing lines and work at remote ends | M5_In Service | 19500243 |  |  | IL |  |  |  |  | MVP | Shared |  | N | N | Y | Top-Down | A | 2016-11-15 | Planned | 14519558 | 34.3% | Scope Change - Double-circuit line needs to be constructed since existing line was unable to be purchased from ComEd. Actual and estimated material & construction costs are higher than the planning quality estimated costs. | 0
A in MTEP11 | Central | AmerenMO | 2248 | 2015-03-24 | 4160 | 2017-02-22 | LN | 2019-12-15 | Ottumwa | Zachary | 1 | 345 |  | AmerenMOs portion of new line - 345 kV, 36 mile single circuit | Planned | 74000000 | Planning | 2014 | MO |  | 36 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 66000000 | 12.12% | Project development costs are higher than expected and estimated costs for construction and environmental mitigation have increased. | 13
A in MTEP11 | Central | AmerenMO | 2248 | 2015-03-24 | 5187 | 2017-02-22 | SUB | 2019-12-15 | Zachary | Install Transformer | 1 | 345 | 161 | Adair Substation - New 560 MVA, 345/161 kV Transformer, 345 kV ring bus.capability | Planned | 27000000 |  |  | MO |  |  | 560 | 560 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 27000000 | 0% |  | 13
A in MTEP11 | Central | AmerenMO | 2248 | 2015-03-24 | 20771 | 2017-02-22 | TEQ | 2019-12-15 | Zachary |  |  | 161 |  | Area Connection work associated with Zachary Substation | Planned | 10000000 | Budgetary | 2014 | MO |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 9870000 | 1.317% | Project development costs are higher than expected and estimated costs for construction and environmental mitigation have increased. | 13
A in MTEP11 | Central | AmerenMO | 3170 | 2015-04-01 | 5601 | 2017-02-22 | LN | 2019-12-15 | Zachary | Maywood | 1 | 345 |  | Construct new 60 mile, 345 kV Line | Planned | 139000000 | Budgetary | 2015 | MO |  | 60 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-11-15 | Planned | 122000000 | 13.93% | Project development costs are higher than expected and estimated costs for construction and environmental mitigation have increased. | 13
A in MTEP11 | Central | AmerenMO | 3170 | 2015-04-01 | 6603 | 2016-10-19 | SUB | 2016-01-10 | Maywood | Establish 345 kV Sub |  | 345 |  | New Maywood Substation - Establish with breaker-and-a-half arrangement | Under Construction | 34851750 |  |  | MO |  |  | 1793 | 1793 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-01-10 | Under Construction | 31369959 | 11.1% | N/A | 0
A in MTEP11 | West | ATC | 3127 | 2014-09-22 | 5484 | 2017-03-31 | SUB | 2017-09-01 | Cardinal | Substation |  | 345 | 138 | Cardinal substation modifications | M1_Final SPM or OOC | 3745000 | Engineering | 2018 | WI |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-12-31 | M1_Final SPM or OOC | 3990000 | -6.14% |  | -3
A in MTEP11 | West | ATC | 3127 | 2014-09-22 | 20580 | 2016-06-30 | SUB | 2023-12-31 | Eden |  |  | 345 | 138 | Eden Substation modifications | M1_Final SPM or OOC | 19200000 | Engineering |  | WI |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 19200000 | 0% | New facility cost estimates based on ITC/ATC joint ownership. | 0
A in MTEP11 | West | ATC | 3127 | 2014-09-22 | 20581 | 2016-06-30 | SUB | 2023-12-31 | Cardinal |  |  | 345 |  | Cardinal Substation modifications | M1_Final SPM or OOC | 3200000 | Engineering |  | WI |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 3200000 | 0% | New facility cost estimates based on ITC/ATC joint ownership. | 0
A in MTEP11 | West | ATC | 3127 | 2014-09-22 | 20607 | 2016-06-30 | TX | 2023-12-31 | Eden |  |  | 345 | 138 | Eden 345/138 kV transformer | M1_Final SPM or OOC | 6100000 | Engineering |  | WI |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 6100000 | 0% | New facility cost estimates based on ITC/ATC joint ownership. | 0
A in MTEP11 | West | ATC | 3206 | 2013-07-05 | 5955 | 2015-03-30 | SUB | 2018-12-31 | Branch River | substation |  | 345 |  | Construct a new Branch River substation | M1_Final SPM or OOC | 46647000 | Engineering |  | WI |  |  |  |  | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2018-12-31 | M1_Final SPM or OOC | 46647000 | 0% | Cost estimate changed. | 0
A in MTEP11 | West | ATC | 3206 | 2013-07-05 | 5970 | 2014-09-29 | LN | 2018-12-31 | Branch River | Point Beach | 1 | 345 |  | Loop the Point Beach-Forest Juction into the Branch River SS | M1_Final SPM or OOC | 0 | Engineering |  | WI |  |  | 1096 | 1096 | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP11 | West | ATC | 3206 | 2013-07-05 | 5971 | 2015-10-19 | LN | 2018-12-31 | Branch River | Forest Jct | 1 | 345 |  | Loop the Point Beach-Forest Juction into the Branch River SS | M1_Final SPM or OOC |  | Engineering |  | WI |  |  | 883 | 883 | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% | Only the Branch River - Forest Jct facility costs have estimates. | 0
A in MTEP11 | West | ATC | 3206 | 2013-07-05 | 5972 | 2014-09-29 | LN | 2018-12-31 | Branch River | Point Beach | 1 | 345 |  | Loop the Point Beach-Sheboygan Energy Center 345 kV line into the Branch River SS | M1_Final SPM or OOC | 0 | Engineering |  | WI |  | 1 | 1096 | 1096 | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP11 | West | ATC | 3206 | 2013-07-05 | 5973 | 2014-09-29 | LN | 2018-12-31 | Branch River | Sheboygan Energy Center | 1 | 345 |  | Loop the Point Beach-Sheboygan Energy Center 345 kV line into the Branch River SS | M1_Final SPM or OOC | 0 | Engineering |  | WI |  | 1 | 1096 | 1096 | GIP | Shared |  | Y | Y | Y | Externally Driven | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP11 | West | ATC, DPC | 3127 | 2014-09-22 | 20578 | 2016-07-05 | LN | 2023-12-31 | Eden | Cardinal | 1 | 345 |  | New line | M1_Final SPM or OOC | 230900000 | Engineering |  | WI |  | 60 | 1399 | 1399 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 230900000 | 0% | New facility cost estimates based on ITC/ATC joint ownership. | 0
A in MTEP11 | West | ATC, XEL | 3127 | 2014-09-22 | 5626 | 2017-03-31 | LN | 2018-12-31 | Briggs Road | North Madison | 1 | 345 |  | Construct a Briggs Road - North Madison 345-kV line | M1_Final SPM or OOC | 463376000 | Engineering | 2018 | WI |  | 161.8 | 1446 | 1521 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 491035000 | -5.633% | Xcel AFUDC reported | 0
A in MTEP11 | West | ATC, XEL | 3127 | 2014-09-22 | 5627 | 2017-03-31 | LNrb | 2017-02-15 | North Madison | Cardinal | 1 | 138 |  | Reconductor with T2-477 HAWK ACSR | M1_Final SPM or OOC | 3443000 | Engineering | 2018 | WI | 19.9 |  | 272 | 349 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-12-31 | M1_Final SPM or OOC | 6010000 | -42.71% | Materials and construction came in under budget. | -10
A in MTEP11 | West | ATC, XEL | 3127 | 2014-09-22 | 5628 | 2017-03-31 | LN | 2017-11-24 | North Madison | Cardinal | 1 | 345 |  | Construct a North Madison - Cardinal 345-kV line | M1_Final SPM or OOC | 61417000 | Engineering | 2018 | WI |  | 19.9 | 1446 | 1446 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-12-31 | M1_Final SPM or OOC | 71455000 | -14.05% | Materials and construction came in under budget. | -1
A in MTEP11 | West | ATC, XEL | 3127 | 2014-09-22 | 6573 | 2017-03-31 | SUB | 2018-12-31 | Briggs Road (North LaCrosse) | Substation |  | 345 |  | Terminate North Madison - North LaCrosse 345 kV line into Briggs Road, create 345 kV breaker ring bus, and 50 MVAR of 34.5 kV reactors on the tertiary | Planned | 9148000 | Engineering | 2018 | WI |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | Planned | 7300000 | 25.32% | Routing change and equipment specification revision. | 0
A in MTEP11 | Central | DEI | 2202 | 2015-11-02 | 7286 | 2017-03-08 | LNrc | 2018-06-01 | Wabash | Wabash Container | 1 | 69 |  | Reconductor Wabash to Wabash Container section of the 6986 ckt. with 477ACSR @ 100C. | M4_Pre-Construction | 1551000 | Engineering | 2013 | IN | 0.8 |  | 100 | 125 | MVP | Shared |  | Y | Y | NT | Top-Down | A | 2018-06-01 | M3_Long Lead Materials | 625000 | 148.2% | Higher level of detail in latest estimate and upgraded material specs to include steel poles. ROW costs higher than estimated also. | 0
A in MTEP11 | Central | DEI | 2202 | 2015-11-02 | 7287 | 2016-12-01 | LNup | 2018-06-01 | Kokomo Delco | Greentown | 1 | 138 |  | Uprate 397ACSR conductor from Kokomo Delco to Greentown section of 13810 ckt. to 100C | M4_Pre-Construction | 142000 | Engineering | 2013 | IN | 10.22 |  | 179 | 225 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-06-01 | M3_Long Lead Materials | 142000 | 0% | Higher level of detail in latest estimate | 0
A in MTEP11 | Central | DEI | 2237 | 2011-11-03 | 8313 | 2017-06-05 | LN | 2018-11-15 | IL/IN State Line | Sugar Creek | 1 | 345 |  | Sugar Creek 345kV ring breaker addition and 1.5 mile - 3000A - 345kV line to IL/IN state line. | M3_Long Lead Materials | 8809000 | Engineering | 2014 | IN |  | 1.5 | 1793 | 1793 | MVP | Shared |  | N | N | Y | Top-Down | A | 2018-11-15 | M1_Final SPM or OOC | 8809000 | 0% | cost increased due to CIP requirements, added RTU and relay replacements and control bldg not in original scope | 0
A in MTEP11 | Central | DEI | 3379 | 2012-03-23 | 6252 | 406770 | Dist | 2017-08-01 | Shelbyville McKay Rd. | new distribution sub |  | 69 | 12 | Shelbyville McKay Rd. - add new 69/12kV distribution sub in the 6976 ckt. Loop through with 954acsr and a set of 1200A line switches. | Under Construction | 553710 | Engineering | 2010 | IN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 553710 | 0% | cost increase due to: added 14 Poles to be replaced – they had to analyze poles before they could recommend to replace | 2
A in MTEP11 | Central | DEI | 3386 | 2010-09-15 | 6259 | 406770 | LN | 2019-06-01 | Carmel Springmill Rd. | Hortonville | 1 | 69 |  | Carmel Springmill Rd. Sub - Add 3-69kV breakers; straight bus config; build .23 mi 69kV 954ACSS@200C from Springmill to old Springmill Jct. Completes circuit to Hortonville. Change operating mode at Homeplace to close loop from 146th to Springmill. | M1_Final SPM or OOC | 1866000 | Engineering | 2013 | IN |  | 0.23 | 143 | 143 | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2019-06-01 | M1_Final SPM or OOC | 1866000 | 0% |  | 0
A in MTEP11 | Central | DEI, NIPS, Non-MISO | 2202 | 2015-11-02 | 4074 | 2016-12-01 | LN | 2018-06-01 | Reynolds | Greentown | 1 | 765 |  | new line | Under Construction | 318106854 | Engineering | 2018 | IN |  | 69.44 | 6750 | 7080 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-06-01 | M4_Pre-Construction | 318106854 | 0% | 3/18/15: scope increase - $36M for (2) 765kV-150MVAR shunt reactors - one at each substation for voltage control per MISO/DEI/NIPS/AEP joint study recommendations. Scope change also includes taps change at Greentown on two existing 765 xfmrs - from 0.95pu to 0.975pu. | 0
A in MTEP11 | Central | DEI, NIPS, Non-MISO | 2202 | 2015-11-02 | 4073 | 2016-12-01 | TX | 2018-06-01 | Reynolds | Transformer | 1 | 765 | 345 | new transformer | Under Construction | 68619519 | Engineering | 2018 | IN |  |  | 2600 | 3200 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-06-01 | M4_Pre-Construction | 68619519 | 0% | 70% of the increase is just a change in escalation - from 2012 dollars to 2018 dollars. The balance is due to improved estimates as design and ROW work is progressing with contingency allowances decreasing. | 0
A in MTEP11 | West | DPC, ITCM | 3127 | 2014-09-22 | 20577 | 2016-11-04 | LN | 2023-12-31 | Eden | Hickory Creek | 1 | 345 |  | New circuit | M1_Final SPM or OOC | 201661000 | Engineering |  | WI,IA |  | 49 | 1399 | 1399 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 193305000 | 4.323% |  | 0
A in MTEP11 | West | GRE | 2679 | 2010-09-15 | 4696 | 2013-09-25 | LN | 2021-05-31 | Ramsey | Grand Forks | 1 | 230 |  | 230 kV rebuild | Under Construction | 41496024.63 | Planning |  | MN | 81.02 |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2021-05-31 | Under Construction | 41496024.63 | 0% |  | 0
A in MTEP11 | West | GRE | 3454 | 2014-09-12 | 6267 | 2016-06-29 | SUB | 2017-06-13 | Medina | 115 kV breaker station |  | 115 |  | Convert WHCEA?s Median 69 kV distribution substation to 115 kV. Retire the 69 kV portion of the Medina 115/69 kV substation, reconfigure Medina to a straight bus breaker station and re-terminate the existing 115kV lines and the new Median ? Pomerleau Lake | Planned | 1726608.36 | Engineering |  | MN | 0 | 0 | 0 | 0 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-13 | Planned | 1726608.36 | 0% |  | 0
A in MTEP11 | West | GRE | 3454 | 2014-09-12 | 6659 | 2017-06-27 | LN | 2018-12-21 | Pomerleau Lake | Plymouth/Parkers Lake | 1&2 | 115 |  | In and Out tap to Pomerleau Lake substation | Planned | 428949.26 | Engineering |  | MN |  | 0.25 |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-10-27 | Planned | 399999 | 7.238% | Land | 14
A in MTEP11 | Central | IPL | 3273 | 2015-12-01 | 6105 | 2014-12-08 | LNup | 2018-06-30 | Southwest | Stout CT | 1 | 138 |  | Line Survey and Potential Modifications | Planned | 300000 | Planning | 2010 | IN | 2.9 |  | 345 | 345 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-06-30 | Planned | 300000 | 0% |  | 0
A in MTEP11 | West | ITCM | 2248 | 2015-03-24 | 20770 | 2017-02-09 | LN | 2018-11-15 | Ottumwa | IA/MO Border | 1 | 345 | 161 | 345/161kV double circuit line. ITC Midwest portion ~20 miles | M2a_Pre-Project Approval | 40640000 | Engineering |  | IA |  | 20 | 1793 |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 40640000 | 0% |  | 17
A in MTEP11 | West | ITCM | 3127 | 2014-09-22 | 20579 | 2016-11-04 | SUB | 2023-12-31 | Hickory Creek |  |  | 345 |  | Hickory Creek Substation modifications | M1_Final SPM or OOC | 13339000 | Engineering |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2023-12-31 | M1_Final SPM or OOC | 13000000 | 2.608% |  | 0
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6520 | 2016-11-04 | SUB | 2017-12-01 | Huntley (formerly Winnebago) | Substation |  | 345 | 161 | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF. Relocate Winnebago to the new Huntley substation. | Under Construction | 27360000 | Planning |  | IA |  |  | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 27360000 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6521 | 2016-11-04 | TX | 2017-12-31 | Huntley (formerly Winnebago) | transformer |  | 345 | 161 | Add a 345/161kV TRF | Under Construction | 0 | Planning |  | IA |  |  | 450 MVA | 450 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6522 | 2016-11-04 | LN | 2017-12-31 | Lakefield | Huntley (formerly Winnebago) | 1 | 345 |  | Construct 345-161kV double circuit | Under Construction | 119337438 | Planning |  | MN |  | 55 | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 119337438 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6523 | 2016-11-04 | LN | 2017-12-31 | Lakefield | Fox Lake | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 1155888 | Planning |  | MN |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 1155888 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6524 | 2016-11-04 | LN | 2017-12-31 | Lakefield | Fox Lake | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | MN | 23 |  | 276 MVA | 446 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6525 | 2016-11-04 | LN | 2017-12-31 | Fox Lake | Rutland | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | MN | 16.5 |  | 168 MVA | 446 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6526 | 2016-11-04 | LN | 2017-12-31 | Rutland | Huntley (formerly Winnebago) | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | MN | 15.24 |  | 168 MVA | 446 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6527 | 2016-11-04 | LN | 2017-12-31 | Fox Lake | Rutland | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 804097 | Planning |  | MN |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 804097 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6528 | 2016-11-04 | LN | 2017-12-31 | Rutland | Winnebago | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 804097 | Planning |  | MN |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 804097 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6529 | 2016-11-04 | SUB | 2017-12-31 | Lakefield | Substation |  | 345 |  | Add a 345kV terminal at Lakefield including 2 new 345kv bkrs | Under Construction | 5000000 | Planning |  | IA |  |  | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 5000000 | 0% |  | 12
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6530 | 2016-11-04 | SUB | 2017-12-01 | Ledyard | substation | 1 | 345 |  | Construct a new Ledyard (formerly Winnco West) 3-terminal 345kV switch station. | Under Construction | 10980000 | Planning |  | IA |  |  | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 10980000 | 0% |  | 6
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6531 | 2016-11-04 | LN | 2017-12-01 | Huntley (formerly Winnebago) | Ledyard | 1 | 345 |  | Construct 345-161kV double circuit | Under Construction | 47734975 | Planning |  | MN,IA |  | 22 | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 47734975 | 0% |  | 6
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6532 | 2016-11-04 | LN | 2017-12-01 | Huntley (formerly Winnebago) | Ledyard | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 1105632 | Planning |  | MN,IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 1105632 | 0% |  | 6
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6533 | 2016-11-04 | LN | 2018-06-01 | Ledyard | Burt | 1 | 345 |  | Construct 345kV circuit | Under Construction | 41225660 | Planning |  | IA |  | 19 | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-06-01 | M1_Final SPM or OOC | 41225660 | 0% |  | 0
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6534 | 2016-11-04 | LN | 2017-12-01 | Winnco | Fairbault Co | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | MN,IA | 22 |  | 111 MVA | 446 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 0 | 0% |  | 6
A in MTEP11 | West | ITCM | 3205 | 2014-03-31 | 6535 | 2016-11-04 | LN | 2017-12-01 | Winnebago | Fairbault Co | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | IA | 15.13 |  | 178 MVA | 446 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 0 | 0% |  | 6
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6536 | 2016-11-04 | LN | 2018-12-31 | Ledyard | Colby | 1 | 345 |  | Construct 345-161kV double circuit | M1_Final SPM or OOC | 132356067 | Planning |  | IA |  | 61 | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 132356067 | 0% |  | 0
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6537 | 2016-11-04 | LN | 2018-12-31 | Colby | Worth County | 1 | 161 |  | Construct 345-161kV double circuit | M1_Final SPM or OOC | 0 | Planning |  | IA |  | 7 | 200 MVA | 200 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6538 | 2016-11-04 | LN | 2018-12-31 | Ledyard | Winnco | 1 | 161 |  | Retire existing 161kV H frame circuit | M1_Final SPM or OOC | 804096 | Planning |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 804096 | 0% |  | 0
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6539 | 2016-11-04 | LN | 2018-12-31 | Worth County | Colby | 1 | 161 |  | Retire existing 161kV H frame circuit | M1_Final SPM or OOC | 251280 | Planning |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 251280 | 0% |  | 0
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6540 | 2016-11-04 | LN | 2016-12-31 | Colby | Lime Creek | 1 | 161 |  | Construct 161kV circuit | M5_In Service | 226152 | Planning |  | IA |  |  | 400 MVA |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-12-31 | M1_Final SPM or OOC | 226152 | 0% |  | -24
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6541 | 2016-11-04 | SUB | 2017-11-01 | Colby | Substation |  | 345 | 161 | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF | Under Construction | 18930000 | Planning |  | IA |  |  | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 18930000 | 0% |  | 11
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6542 | 2016-11-04 | TX | 2017-11-01 | Colby | transformer |  | 345 | 161 | Add a 345/161kV TRF | Under Construction | 0 | Planning |  | IA |  |  | 450 MVA | 450 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 11
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6543 | 2016-11-04 | SUB | 2017-11-01 | Killdeer | Substation |  | 345 | 161 | Construt a new sub with a 345kV ring bus with 2 line terminals and one 345/161kV TRF | Under Construction | 19380000 | Planning |  | IA |  |  | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 19380000 | 0% |  | 11
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6544 | 2016-11-04 | TX | 2017-11-01 | Killdeer | transformer |  | 345 | 161 | Add a 345/161kV TRF | Under Construction | 0 | Planning |  | IA |  |  | 450 MVA | 450 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 11
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6545 | 2016-11-04 | LN | 2017-11-01 | Colby | Killdeer | 1 | 345 |  | Construct 345-161kV double circuit | Under Construction | 34716345 | Planning |  | IA |  | 16 | 1800 MVA | 1800 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 34716345 | 0% |  | 11
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6546 | 2016-11-04 | LN | 2016-12-31 | Colby | Emery | 1 | 161 |  | Construct 345-161kV double circuit | Under Construction | 0 | Planning |  | IA |  | 16 | 327 MVA | 335 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP11 | West | ITCM | 3213 | 2014-03-31 | 6547 | 2016-11-04 | LN | 2016-12-31 | Colby | Emery | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 804096 | Planning |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 804096 | 0% |  | 0
A in MTEP11 | West | ITCM | 3412 | 2012-01-07 | 6299 | 2016-10-28 | SUB | 2016-07-14 | Fort Madison | Substation | 1 | 69 |  | Add new 69/dist TRF | M5_In Service | 1740000 | Engineering |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-10-07 | M4_Pre-Construction | 1740000 | 0% |  | -3
A in MTEP11 | West | ITCM | 3413 | 2012-01-07 | 6300 | 2013-06-27 | LN | 2015-12-31 | Gladbrook | Gladbrook Tap | 1 | 161 | 161 | Add new 69/dist TRF | Planned | 300000 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 300000 | 0% |  | 0
A in MTEP11 | West | ITCM | 3413 | 2012-01-07 | 6301 | 2013-06-27 | LN | 2015-12-31 | Marshalltown | Gladbrook Tap | 1 | 161 | 161 | Add new 69/dist TRF | Planned | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 0 | 0% |  | 0
A in MTEP11 | West | ITCM | 3413 | 2012-01-07 | 6302 | 2013-06-27 | LN | 2015-12-31 | Traer | Gladbrook Tap | 1 | 161 | 161 | Add new 69/dist TRF | Planned | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 0 | 0% |  | 0
A in MTEP11 | West | ITCM | 3418 | 2012-01-07 | 6307 | 2012-01-07 | LN | 2015-12-31 | Mt Vernon 6420 | 6420 circuit | 1 | 34 | 34 | Rebild ckt 69kV | Planned | 7150000 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 7150000 | 0% |  | 0
A in MTEP11 | West | ITCM | 3422 | 2012-01-07 | 6311 | 2014-06-13 | TEQ | 2015-06-30 | South Broadway | Substation | 1 | 69 |  | Upgrades terminal equipment. Change out existing relays, add new control building, add 69kV bus. | Planned | 852000 | Engineering |  | IA |  |  | 195 MVA |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-06-30 | Planned | 852000 | 0% |  | 0
A in MTEP11 | West | ITCM, MEC | 2248 | 2015-03-24 | 6566 | 2017-02-09 | TEQ | 2018-11-15 | Ottumwa | 345 kV terminal |  | 345 |  | add 345 kV terminal for Zachary line | M2a_Pre-Project Approval | 9360000 |  | 2017 | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-06-01 | M1_Final SPM or OOC | 9360000 | 0% |  | 17
A in MTEP11 | West | ITCM, MEC | 3213 | 2014-03-31 | 6548 | 2016-11-04 | LN | 2017-11-01 | Killdeer | Blackhawk | 1 | 345 |  | Construct 345-161kV double circuit | Under Construction | 57677172 | Planning |  | IA |  | 29 |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | M1_Final SPM or OOC | 57677172 | 0% |  | 11
A in MTEP11 | West | ITCM, MEC | 3213 | 2014-03-31 | 6549 | 2016-11-04 | LN | 2017-11-01 | Killdeer | Blackhawk | 1 | 161 |  | Construct 345-161kV double circuit and transfer existing 161kV conductor | Under Construction | 0 | Planning |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | Under Construction | 0 | 0% |  | 11
A in MTEP11 | West | ITCM, MEC | 3213 | 2014-03-31 | 6550 | 2016-11-04 | LN | 2017-11-01 | Emery | Blackhawk | 1 | 161 |  | Retire existing 161kV H frame circuit | Under Construction | 1457424 | Planning |  | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-31 | Under Construction | 1457424 | 0% |  | 11
A in MTEP11 | West | ITCM, MEC | 3213 | 2014-03-31 | 6557 | 2016-11-04 | LN | 2017-11-01 | Blackhawk | Killdeer | 1 | 345 |  | Blackhawk - Killdeer 345/161 kV double circuit line via Franklin. Includes rebuild of non-MISO 161 kV circuit from Franklin to Emery. | Under Construction | 110626884 |  | 2016 | IA | 63 |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-05-01 | Under Construction | 110626884 | 0% | Contractor bids higher than budgeted. | 6
A in MTEP11 | East | ITCT | 3281 | 2017-06-30 | 6113 | 2017-06-30 | LN | 2017-08-04 | Majestic | Chelsea (formerly Lima) | 1 | 120 |  | Construct new 120 kV line between Majestic and Lima, along with associated breakers and terminal equiment at each termination. | Under Construction | 6500000 | Planning |  | MI |  | 5 |  | 349 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M4_Pre-Construction | 6500000 | 0% |  | 8
A in MTEP11 | East | ITCT | 3285 | 2016-12-20 | 6516 | 2017-03-29 | SUB | 2019-05-01 | Shoal | 33.3 Mvar capacitor |  | 120 |  | Install a 33.3 Mvar Capacitor at Shoal 120kV station as well as two line breakers and a tie breaker. | M4_Pre-Construction | 3430000 | Engineering |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-11-30 | Under Construction | 3430000 | 0% | SSVTs added at Shoal 120 kV substation | 30
A in MTEP11 | East | ITCT | 3285 | 2016-12-20 | 8994 | 2017-03-29 | LNup | 2019-05-01 | Shoal | Custer | 1 | 120 |  | OPGW installation | M4_Pre-Construction | 900000 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2016-11-30 | Under Construction | 900000 | 0% | Overhead Line Design estimate refined. | 30
A in MTEP11 | West | MDU, OTP | 2220 | 2015-09-29 | 4092 | 2016-12-07 | LN | 2019-09-30 | Big Stone South | Ellendale |  | 345 |  | Line (The cost increase associated with the Big Stone South ? Ellendale 345 kV project is associated with the length of the line increasing by approximately 20 miles since MTEP approval.) | Planned | 365000000 | Planning |  | SD,ND |  | 163 | 1800 MVA |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2019-09-30 | Planned | 365000000 | 0% |  | 0
A in MTEP11 | West | MDU, OTP | 2220 | 2015-09-29 | 6382 | 2016-06-27 | TX | 2019-09-30 | Ellendale 345/230 | Transformer |  | 345 | 230 | Substation, Transformer 345/230, Line Reactor | Planned | 30670000 | Planning |  | ND |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2019-09-30 | Planned | 30670000 | 0% |  | 0
A in MTEP11 | West | MEC | 2248 | 2015-03-24 | 6565 | 2017-06-29 | LN | 2018-10-01 | Ottumwa | Iowa border | 1 | 345 | 161 | 345/161 double circuit line; MEC's portion | M2a_Pre-Project Approval | 56000000 |  | 2017 | IA | 22 |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2018-10-01 | M2a_Pre-Project Approval | 38980586.95 | 43.66% | Line length increased from 22 to 29 miles. Higher percentage of the line route is double-circuit construction than originally anticipated. | 0
A in MTEP11 | West | MEC | 3022 | 2015-04-02 | 5989 | 2017-06-29 | LN | 2017-03-28 | Oak Grove | Sandburg | 1 | 345 | 161 | New 345/161 kV double circuit line. Replaces existing Oak Grove to Galesburg 161 kV line | M5_In Service | 60980280 |  | 2016 | IA |  | 32 |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-04-08 | M2a_Pre-Project Approval | 68319117.67 | -10.74% |  | -1
A in MTEP11 | West | MEC | 3022 | 2015-04-02 | 6562 | 2017-06-29 | TEQ | 2017-03-28 | Oak Grove | 345 kV terminal |  | 345 |  | add 345 kV terminal for Sandburg line | M5_In Service | 6558745 |  | 2016 | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-04-08 | M2a_Pre-Project Approval | 2046383.81 | 220.5% | Project scope expanded to include substation security enhancements. | -1
A in MTEP11 | West | MEC | 3022 | 2015-04-02 | 6564 | 2017-06-29 | LNrc | 2017-04-30 | Sub 56 | Sub 85 |  | 161 |  | Reconductor Sub 56-Sub 85 161 kV line with T2- 556.5 ACSR conductor | M5_In Service | 2280352 |  | 2016 | IA | 7.5 |  | 410 | 410 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-04-30 | M1_Final SPM or OOC | 2588989.63 | -11.92% |  | 0
A in MTEP11 | West | MEC | 3205 | 2014-03-31 | 5951 | 2017-01-03 | LN | 2016-12-13 | Obrien County | Webster |  | 345 |  | Obrien County to Webster 345/161 kV double ckt line - Candidate MVP Portfolio #1. Includes rebuild of non-MISO 161 kV circuit from Wisdom to Webster. | M5_In Service | 244590889.32 | with AFUDC | 2015 | IA |  | 122 | 1739 | 1739 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-01 | Under Construction | 244590889.32 | 0% |  | 0
A in MTEP11 | West | MEC | 3205 | 2014-03-31 | 6561 | 2017-01-04 | SUB | 2016-12-13 | Kossuth Co. |  |  | 345 |  | New three-way 345 kV Kossuth County Switching Station near Burt Substation | M5_In Service | 16238014 |  | 2016 | IA |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-07-31 | Under Construction | 16238014 | 0% | Contractor bids higher than expected. | 5
A in MTEP11 | West | MEC | 3213 | 2014-03-31 | 6424 | 2017-01-04 | LNup | 2016-09-30 | Franklin | Butler | 1 | 161 |  | Rebuild Franklin-Butler 161 kV line. | M5_In Service |  | Planning | 2011 | IA | 26.24 |  | 410 | 410 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-09-30 | Under Construction | 0 | 0% |  | 0
A in MTEP11 | West | MEC | 3213 | 2014-03-31 | 6425 | 2017-01-04 | LNup | 2016-12-15 | Butler | Union Tap | 1 | 161 |  | Rebuild Butler-Union Tap 161 kV line. | M5_In Service |  | Planning | 2011 | IA | 15.93 |  | 410 | 410 | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2016-12-15 | Under Construction | 0 | 0% |  | 0
A in MTEP11 | West | MP | 2634 | 2012-12-04 | 6370 | 2016-12-15 | LN | 2016-03-04 | Savanna | Floodwood Tap | 1 | 115 |  | Thermal upgrade of Savanna-9 Line tap | M5_In Service | 5647421 | Engineering |  | MN | 10 |  | 122 | 134 | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-03-31 | Planned | 5647421 | 0% |  | 0
A in MTEP11 | East | NIPS | 3203 | 2011-11-03 | 5949 | 2016-06-30 | LN | 2019-12-31 | Reynolds | Hiple | 2 | 345 |  | new line tap at Burr Oak | Under Construction | 388000000 | Planning |  | IN |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2019-12-31 | Under Construction | 388000000 | 0% | Key drivers include 1. Detailed design and route selection resulted in increased pole size and strength requirements as well as corresponding construction increases and escalation to current year dollars of $72M. 2. Scope increases – CIPS, soil stabilization, 138/12.5Kv line re-routes, sub-station changes and escalation to current year dollars $21M 4. Increased Owners cost. $14M 5. Additional overhead allocations. $10M | 0
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 4116 | 2017-06-15 | TX | 2017-12-31 | Big Stone South 345/230 | Transformer | 1 | 345 | 230 | Transformer #1 345/230/13.8 kV | Under Construction | 2554070 | Construction |  | SD |  |  | 448 MVA | 560 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 4000000 | -36.15% |  | 3
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 6383 | 2017-06-15 | LN | 2017-12-31 | Big Stone | Big Stone South | 1 | 230 |  | Line #1 | Under Construction | 1169618 | Construction |  | SD |  | 1.6 | 550 MVA | 605 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 2000000 | -41.52% |  | 3
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 6384 | 2017-06-15 | LN | 2017-12-31 | Big Stone | Big Stone South | 2 | 230 |  | Line #2 | Under Construction | 1169618 | Construction |  | SD |  | 1.7 | 550 MVA | 605 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 2000000 | -41.52% |  | 3
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 6387 | 2017-06-15 | TX | 2017-12-31 | Big Stone South 345/230 | Transformer | 2 | 345 | 230 | Transformer #2 345/230/13.8 kV | Under Construction | 2554070 | Construction |  | SD |  |  | 448 MVA | 560 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 4000000 | -36.15% |  | 3
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 6588 | 2017-06-15 | TX | 2017-12-31 | Big Stone South Sub | Equipment |  | 345 | 230 | Substation Equipment | Under Construction | 10567324 | Construction |  | SD |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 30000000 | -64.78% |  | 3
A in MTEP11 | West | OTP | 2221 | 2017-06-15 | 6589 | 2017-06-15 | TX | 2017-12-31 | Big Stone 230 | Big Stone 230 |  | 230 | 230 | Substation Equipment | Under Construction | 2433802 | Construction |  | SD |  |  |  |  | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 10000000 | -75.66% |  | 3
A in MTEP11 | West | OTP | 3481 | 2017-03-09 | 6434 | 2017-03-09 | TX | 2017-08-30 | Buffalo 345 kV | Buffalo 115/41.6 kV | 1 | 345 | 115 | Add a second 112 MVA 345/115/41.6 kV transformer instead of a single, larger xfmr and add a four breaker 345kV ring bus | Under Construction | 5600000 | Planning |  | ND |  |  | 187 MVA | 233 MVA | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2017-06-30 | Under Construction | 5600000 | 0% | Control house expansion, site grading and land purchase were not included in original estimate. | 2
A in MTEP11 | West | OTP, XEL | 2221 | 2017-06-15 | 4117 | 2017-06-15 | LN | 2017-12-31 | Big Stone South | Brookings | 1 | 345 |  | Single circuit on double circuit towers | Under Construction | 113370000 | Construction |  | SD |  | 72.1 | 1878 MVA | 2065 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 165000000 | -31.29% |  | 3
A in MTEP11 | East | WPSC | 3331 | 2010-09-15 | 6196 | 2017-03-07 | LNrb | 2016-12-31 | Redwood | Hart | 1 | 69 |  | Rebuild Overloaded Line to 795ACSS | Planned | 1000000 |  | 2012 | MI | 1.77 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1000000 | 0% | Updated in 2015 planning review | 0
A in MTEP11 | East | WPSC | 3335 | 2010-09-15 | 6200 | 2016-09-15 | SUB | 2022-12-31 | Burnips | Substation Upgrade |  | 69 |  | Replace bus work, breakers, relays, and any other necessary components | Planned | 800000 |  |  | MI |  |  |  |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | Planned | 800000 | 0% | Updated budget in 2014 plan review. | 0
A in MTEP11 | West | XEL | 2221 | 2017-06-15 | 6572 | 2017-06-15 | SUB | 2017-12-31 | Brookings County | Substation |  | 345 |  | Termination for Big Stone - Brookings Co 345 kV line and conversion of the existing ring bus to a breaker-and-a-half | Under Construction | 7500000 | Construction |  | SD |  |  | 1792 MVA | 1792 MVA | MVP | Shared |  | Y | Y | Y | Top-Down | A | 2017-09-30 | Planned | 9720000 | -22.84% |  | 3
A in MTEP10 | Central | DEI | 1520 | 2009-09-17 | 2596 | 2017-06-02 | SUB | 2017-09-01 | Durbin | 230/69 substation | 1 | 230 | 69 | Build a new 230 69kv 150mva sub with 2 69kv line terminals | Under Construction | 9167825.75 | Engineering | 2013 | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-06-01 | M3_Long Lead Materials | 9167825.75 | 0% | transition from a generic Planning estimate to a detailed Engineering estimate | 3
A in MTEP10 | Central | DEI | 2143 | 2011-09-27 | 2929 | 2014-09-23 | TX | 2020-06-01 | Frances Creek | bank 2 | 2 | 345 | 69 | Add Frances Creek 345/69kV Bank 2 - 200MVA with LTC | M1_Final SPM or OOC | 6887000 | Engineering | 2009 | IN |  |  | 200 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2020-06-01 | M1_Final SPM or OOC | 6887000 | 0% |  | 0
A in MTEP10 | West | GRE | 2564 | 2017-04-04 | 4566 | 2017-06-27 | LN | 2017-11-08 | Five Points | Le Sauk | 1 | 115 |  | Sartell Disribution Sub, 795 ACSS 115 kV radial line and switch | Under Construction | 1776267.12 | Engineering |  | MN |  | 3 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-11-08 | Under Construction | 1500000 | 18.42% | Land | 0
A in MTEP10 | West | GRE | 2577 | 2016-02-10 | 4588 | 2016-06-29 | SUB | 2021-05-18 | Columbus | Columbus Tap | 1 | 69 |  | New Distribution | Planned | 140000 | Planning |  | MN |  | 0 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2021-05-18 | Planned | 140000 | 0% |  | 0
A in MTEP10 | West | GRE | 2579 | 2010-09-15 | 4590 | 2016-04-27 | SUB | 2020-10-30 | Foster Lake | Foster Lake Tap | 1 | 69 |  | New Distribution | Planned | 140000 | Planning |  | MN |  | 0 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2020-10-30 | Planned | 140000 | 0% |  | 0
A in MTEP10 | West | GRE | 2589 | 2009-11-19 | 4600 | 2016-09-08 | LN | 2023-07-20 | Rich Valley | Rich Valley Tap | 1 | 69 |  | New Distribution | Planned | 115001 | Engineering |  | MN |  | 2 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2023-07-20 | Planned | 115001 | 0% |  | 0
A in MTEP10 | West | GRE | 2670 | 2012-12-04 | 4687 | 2011-07-01 | TX | 2020-04-14 | Schuster Lake | transformer | 1 | 115 | 41.6 | North Perham land acquisition and 115/41.6 kV source | Planned | 4480714.28 | Engineering |  | MN |  |  | 70 |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2020-04-14 | Planned | 4480714.28 | 0% |  | 0
A in MTEP10 | West | ITCM | 3048 | 2009-09-14 | 5266 | 2016-06-28 | LN | 2022-12-31 | Jefferson Co | Perlee | 1 | 69 | 69 | Rebuild Jefferson Co-Perlee line | Planned | 2700000 | Planning |  | IA | 7.38 | 0 | 57 MVA | 57 | Other |  | Condition | N | N | Y | Bottom-Up | A | 2022-12-31 | Planned | 2700000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3053 | 2010-06-28 | 5294 | 2017-06-30 | LN | 2018-12-31 | Keokuk Hydro | Carbide | 1 | 69 | 69 | Build a new Keokuk Hydro-Carbide 69 kV line. | Planned | 1620000 | Planning |  | IA |  |  | 100 MVA | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 1620000 | 0% |  | 24
A in MTEP10 | West | ITCM | 3053 | 2010-06-28 | 5295 | 2017-06-30 | LN | 2018-12-31 | Keokuk Hydro | Messenger | 1 | 69 | 69 | Rebild to doulbe ckt 69kV | Planned | 540000 | Planning |  | IA |  |  | 100 MVA | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 540000 | 0% |  | 24
A in MTEP10 | West | ITCM | 3053 | 2010-06-28 | 5296 | 2017-06-30 | LN | 2018-12-31 | Messenger | Commercial | 1 | 69 | 69 | Rebild to doulbe ckt 69kV | Planned | 540000 | Planning |  | IA |  |  | 100 MVA | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 540000 | 0% |  | 24
A in MTEP10 | West | ITCM | 3053 | 2010-06-28 | 5297 | 2017-06-30 | LN | 2018-12-31 | Commercial | Carbide | 1 | 69 | 69 | Rebild to doulbe ckt 69kV | Planned | 540000 | Planning |  | IA |  |  | 100 MVA | 100 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 540000 | 0% |  | 24
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5279 | 2015-12-30 | LN | 2019-04-16 | Cargil West | PCI | 1 | 69 | 69 | Rebuild 34kV to 69kV and new 69kV section | Planned | 810000 | Planning |  | IA | 6 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-04-16 | Planned | 810000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5282 | 2015-12-30 | LN | 2018-10-01 | PCI | Oak Hill | 1 | 69 | 69 | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 1010000 | Planning |  | IA | 5 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2018-10-01 | Planned | 1010000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5283 | 2015-12-30 | LN | 2019-04-01 | Oak Hill | Marion | 1 | 69 | 69 | Rebuild 34kV to 69kV(operate at 34kV until 69kV/dist subs are ready) | Planned | 1010000 | Planning |  | IA | 8 |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-04-01 | Planned | 1010000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5291 | 2014-06-13 | SUB | 2017-12-31 | Cargil West | Substation | 1 | 69 | 69 | New 69kV/dist sub | Planned | 2160000 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 2160000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5292 | 2014-06-13 | SUB | 2015-12-31 | Emerald Isle | Substation | 1 | 69 | 69 | New 69kV/dist sub | Planned | 2160000 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2015-12-31 | Planned | 2160000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3055 | 2009-09-14 | 5293 | 2014-06-13 | SUB | 2019-12-31 | Oak Hill | Substation | 1 | 69 | 69 | New 69kV/dist sub | Planned | 2160000 | Planning |  | IA |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 2160000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5301 | 2015-12-30 | LN | 2019-12-31 | Moscow | Moscow Tap | 1 | 69 | 69 | Build a new 3.75 mile 69kV tap to Moscow & retire 7 mile 34kV tap. | M1_Final SPM or OOC | 1313000 | Engineering |  | IA | 0 | 3.75 | 77 MVA |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 1313000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5302 | 2015-12-30 | LN | 2019-12-31 | Muscatine Switch Station | Moscow Tap | 1 | 69 | 69 | Tap the Muscatine Switch Station to Magmet T69kV line for new tap to Moscow. | M1_Final SPM or OOC | 0 | Engineering |  | IA | 0 | 0 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5303 | 2015-12-30 | LN | 2019-12-31 | Moscow Tap | Magmet T | 1 | 69 | 69 | Tap the Muscatine Switch Station to Magmet T69kV line for new tap to Moscow. | M1_Final SPM or OOC | 0 | Engineering |  | IA | 0 | 0 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5304 | 2014-06-13 | LN | 2018-12-31 | New Liberty | New Liberty Tap | 1 | 69 | 69 | Build a new 2 mile 69kV tap to New Liberty & retire 9.4 mile 34kV tap. | M1_Final SPM or OOC | 700000 | Engineering |  | IA | 0 | 2 | 77 MVA |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 700000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5305 | 2014-06-13 | LN | 2018-12-31 | Bennett | New Liberty Tap | 1 | 69 | 69 | Tap the Bennett Switch Station to Dixon Jct 69kV line for a new 69kV tap to New Liberty. | M1_Final SPM or OOC | 0 | Planning |  | IA | 0 | 0 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 5306 | 2014-06-13 | LN | 2018-12-31 | New Liberty Tap | Dixon Jct | 1 | 69 | 69 | Tap the Bennett Switch Station to Dixon Jct 69kV line for a new 69kV tap to New Liberty. | M1_Final SPM or OOC | 0 | Planning |  | IA | 0 | 0 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 6418 | 2015-12-30 | LN | 2019-12-31 | Moscow Tap | Moscow | 1 | 34 | 34 | Retire the Moscow 34kV 7 mile tap | M1_Final SPM or OOC | 210000 | Engineering |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-12-31 | M1_Final SPM or OOC | 210000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3057 | 2010-06-28 | 6419 | 2014-06-13 | LN | 2018-12-31 | New Liberty | New Liberty Tap | 1 | 34 | 34 | Retire the New Liberty 34kV 9.4 mile tap | M1_Final SPM or OOC | 282000 | Engineering |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-12-31 | M1_Final SPM or OOC | 282000 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5308 | 2014-06-13 | LN | 2015-06-01 | Palo | Todville REC | 1 | 69 | 69 | New 69kV | M1_Final SPM or OOC | 5160000 | Engineering |  | IA | 0 | 4.5 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2015-06-01 | M1_Final SPM or OOC | 5160000 | 0% | Updated engineering estimate. Increased costs due to ROW issues. | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5316 | 2015-04-13 | SUB | 2016-12-31 | Palo | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5317 | 2015-04-13 | SUB | 2016-12-31 | Shellsburg | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5318 | 2015-04-13 | SUB | 2016-12-31 | Brandon | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5321 | 2015-04-13 | SUB | 2016-12-31 | Walker REC | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5322 | 2015-04-13 | SUB | 2016-12-31 | Lafayette | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | West | ITCM | 3058 | 2009-09-14 | 5323 | 2015-04-13 | SUB | 2016-12-31 | Urbana | Substation | 1 | 69 | 69 | New 69kV/dist sub | M1_Final SPM or OOC | 0 | Planning |  | IA |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 0 | 0% |  | 0
A in MTEP10 | East | ITCT | 2929 | 2017-02-08 | 5098 | 2017-02-08 | LN | 2017-02-07 | Ariel (formerly Holland) | Holland | 1 | 120 |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | M5_In Service | 2800000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-30 | Under Construction | 2800000 | 0% |  | 3
A in MTEP10 | East | ITCT | 2929 | 2017-02-08 | 5099 | 2017-02-08 | LNup | 2017-02-07 | Ariel (formerly Holland) | Wheeler | 1 | 120 |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | M5_In Service |  |  |  | MI |  | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-30 | Under Construction | 0 | 0% |  | 3
A in MTEP10 | East | ITCT | 2929 | 2017-02-08 | 5100 | 2017-02-08 | LNup | 2017-02-07 | Ariel (formerly Holland) | Troy | 1 | 120 |  | Distribution Interconnection to add two new 120/13.2kV transformers at Ariel (formerly Holland). Connects to the Wheeler to Troy 120kV circuit. | M5_In Service |  |  |  | MI | 0.73 | 0.1 |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-11-30 | Under Construction | 0 | 0% |  | 3
A in MTEP10 | West | MP | 2547 | 2009-12-08 | 4557 | 2015-06-10 | LN | 2027-04-01 | Blackberry | Essar Steel Sub (McCarthy Lake) | 1 | 230 |  | Essar new Line and new bay at McCarthy Lake (facility #4558) | Planned | 14000000 | Engineering |  | MN |  | 15 | 632 | 695.2 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2027-04-01 | Planned | 14000000 | 0% | Updated cost to include Blackberry substation work to accommodate a new line entrance | 0
A in MTEP10 | West | MP | 2547 | 2009-12-08 | 5438 | 2015-06-10 | SUB | 2027-04-01 | Blackberry | Substation Equipment |  | 230 |  | line entrance & breaker | Planned | 0 | Engineering |  | MN |  |  | 632 | 695.2 | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2027-04-01 | Planned | 0 | 0% | Moved cost into Blackberry - McCarthy Lake Line (facility #4557) | 0
A in MTEP10 | West | MP | 2761 | 2009-11-13 | 4780 | 2015-06-10 | SUB | 2017-01-31 | Northmet | Substation Equipment |  | 138 | 14 | Substation Equipment & Transformer | Planned | 3242847 | Engineering |  | MN |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-01-31 | Planned | 3242847 | 0% |  | 0
A in MTEP10 | West | MPW | 2934 | 2017-05-26 | 5106 | 2017-05-26 | TX | 2017-06-16 | South 161/69 kV | transformer | 2 | 161 | 69 | Add transformer in parallel with existing 75 MVA transformer | Under Construction | 5400000 | Planning |  | IA |  |  | 134 | 134 | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-01 | Planned | 5400000 | 0% |  | 6
A in MTEP10 | West | NWEC | 3092 | 2009-11-16 | 5410 | 2011-09-16 | LNrb | 2012-06-01 | Lake 26 | Webb Lake |  | 69 |  | Rebuild 34.5KV line to Webb Lake at 69KV with horizontal post construction and #4/0 ACSR | Planned | 425000 |  |  | WI | 2.6 | 0 | 15 |  | Other |  | Condition | N | N | Y | Bottom-Up | A | 2012-06-01 | Planned | 425000 | 0% |  | 0
A in MTEP09 | Central | AmerenIL | 2273 | 2010-04-05 | 4187 | 2016-03-09 | LN | 2020-06-01 | LaFarge | 161 kV Supply to Customer Substation |  | 161 |  | Provide 161 kV supply to customer substation | Planned | 570000 | Engineering |  | IL |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-06-01 | Planned | 570000 | 0% |  | 0
A in MTEP09 | Central | DEI | 2154 | 2011-09-27 | 2942 | 2015-01-12 | SUB | 2019-06-01 | Carmel Rohrer Rd. | distribution sub |  | 69 | 12 | Carmel Rohrer Rd 69/12-22.4MVA sub to looped through the 6989 ckt. at or near the existing Carmel Shell Oil tap | M2a_Pre-Project Approval | 591143 | Engineering | 2008 | IN | 0.4 | 0.4 |  |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-06-01 | M2a_Pre-Project Approval | 591143 | 0% |  | 0
A in MTEP09 | West | ITCM | 2367 | 2009-04-01 | 4360 | 2015-12-30 | LNrb | 2016-04-29 | Anita 161kV | Exira REC | 1 | 34 |  | Rebuild the 34kV line to 69kV (operate at 34kV). | Under Construction | 1250000 |  |  | IA | 5 |  | 39/39 MVA |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-04-29 | Under Construction | 1250000 | 0% |  | 0
A in MTEP09 | West | ITCM | 2367 | 2009-04-01 | 4361 | 2013-06-27 | LNrb | 2016-12-31 | Anita 161kV | Anita-Wiota | 1 | 34 |  | Rebuild the 34kV line to 69kV (operate at 34kV). | Planned | 875000 |  |  | IA | 3.5 |  | 39/39 MVA |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 875000 | 0% |  | 0
A in MTEP09 | West | ITCM | 2367 | 2009-04-01 | 4362 | 2013-06-27 | LNrb | 2016-12-31 | Anita-Wiota | Adair | 1 | 34 |  | Rebuild 1.2 miles of the Anita-Wiota-Adair line. | Planned | 300000 |  |  | IA | 1.2 |  | 39/39 MVA |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | Planned | 300000 | 0% |  | 0
A in MTEP09 | West | ITCM | 2371 | 2009-09-25 | 4383 | 2014-06-13 | SUB | 2016-12-31 | Marengo | new switching station | 1 | 69 |  | Construct a new 3-terminal 69kV switching station at the existing Marengo 34kV sub. This work needs to be completed for 69kV operation. | M1_Final SPM or OOC | 1900000 | Engineering |  | IA |  |  |  |  | Other |  | Condition | N | N | NT | Bottom-Up | A | 2016-12-31 | M1_Final SPM or OOC | 1900000 | 0% |  | 0
A in MTEP09 | East | METC | 662 | 2017-01-05 | 1350 | 2016-10-17 | SUB | 2016-10-13 | Weeds Lake 345/138 kV |  |  | 345 | 138 | Weeds Lake 345/138 kV switching station | M5_In Service | 17841284.4 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 17841284.4 | 0% | Cost change due to unpredicted legal costs related to ROW process | -2
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3592 | 2016-10-17 | TX | 2016-10-13 | Weeds lake 345/138 kV | Transformer |  | 345 | 138 | transformer | M5_In Service | 6665833.2 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 6665833.2 | 0% | Cost change due to unpredicted legal costs related to ROW process | -2
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3593 | 2017-01-05 | LNup | 2017-01-03 | Weeds Lake | BRONCO |  | 138 |  | line extention on BRONCO 12th ST circuit BRONCO side | M5_In Service | 5780000 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 5780000 | 0% | Cost change due to unpredicted legal costs related to ROW process | 1
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3594 | 2017-01-05 | LNup | 2017-01-03 | Weeds Lake | MILHAM |  | 138 |  | line extention on MILHAM to N_AVE circuit MILHAM side | M5_In Service | 5780000 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 5780000 | 0% | Cost change due to unpredicted legal costs related to ROW process | 1
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3595 | 2017-01-05 | LNup | 2017-01-03 | Weeds Lake | 12th ST |  | 138 |  | line extention on BRONCO to 12th ST circuit 12TST side | M5_In Service | 5780000 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 5780000 | 0% | Cost change due to unpredicted legal costs related to ROW process | 1
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3596 | 2017-01-05 | LNup | 2017-01-03 | Weeds Lake | N_AVE |  | 138 |  | line extention on MILHAM to N_AVE circuit N_AVE side | M5_In Service | 5780000 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 5780000 | 0% | Cost change due to unpredicted legal costs related to ROW process | 1
A in MTEP09 | East | METC | 662 | 2017-01-05 | 3597 | 2016-12-13 | SUB | 2016-12-09 | Argenta 138 kV |  |  | 138 |  | Remote relay work to be completed at Argenta 138 kV | M5_In Service | 1067275.2 |  |  | MI |  |  |  |  | BaseRel | Shared |  | Y | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 1067275.2 | 0% | Cost change due to unpredicted legal costs related to ROW process | 0
A in MTEP09 | East | METC | 662 | 2017-01-05 | 8991 | 2017-01-05 | SUB | 2017-01-03 | Milham 138 kV |  |  | 138 |  | Remote relay work to be completed at Milham 138 kV | M5_In Service | 553735.2 |  |  | MI |  |  |  |  | BaseRel | Shared |  | N | N | Y | Bottom-Up | A | 2016-12-15 | Under Construction | 553735.2 | 0% | Cost change due to unpredicted legal costs related to ROW process | 1
A in MTEP09 | East | METC | 2478 | 2017-06-30 | 4466 | 2017-06-30 | TAP | 2020-06-01 | Capital Ave | Battle Creek | 1 | 138 |  | Capital Ave taps the Battle Creek-Verona 138kV circuit #2. | Planned | 89094 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 89094 | 0% |  | 36
A in MTEP09 | East | METC | 2478 | 2017-06-30 | 4467 | 2017-06-30 | TAP | 2020-06-01 | Capital Ave | Battle Creek | 1 | 138 |  | Capital Ave taps the Battle Creek-Verona 138kV circuit #2. | Planned | 89094 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 89094 | 0% |  | 36
A in MTEP09 | East | METC | 2481 | 2016-06-08 | 4470 | 2016-06-08 | TAP | 2018-05-31 | Forest Grove | Campbell | 1 | 138 |  | Forest Grove taps the Campbell-Hudsonville (toward Ransom) 138kV circuit | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2481 | 2016-06-08 | 4471 | 2016-06-08 | TAP | 2018-05-31 | Forest Grove | Hudsonville | 1 | 138 |  | Forest Grove taps the Campbell-Hudsonville (toward Ransom) 138kV circuit | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-05-31 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2482 | 2014-01-31 | 4472 | 2014-12-22 | TAP | 2020-05-31 | Hawthorne | Four Mile | 1 | 138 |  | Hawthorne taps the Four Mile-Pingree (toward Blendon) 138kV circuit | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-05-31 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2482 | 2014-01-31 | 4473 | 2014-12-22 | TAP | 2020-05-31 | Hawthorne | Pingree | 1 | 138 |  | Hawthorne taps the Four Mile-Pingree (toward Blendon) 138kV circuit | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2020-05-31 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2483 | 2017-02-20 | 4474 | 2017-02-20 | TAP | 2017-02-16 | Maines Road | Marshall | 1 | 138 |  | Maines Road taps the Marshall-Blackstone 138kV circuit | M5_In Service | 88193 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-01 | M3_Long Lead Materials | 88193 | 0% |  | 2
A in MTEP09 | East | METC | 2483 | 2017-02-20 | 4475 | 2017-02-20 | TAP | 2017-02-16 | Maines Road | Blackstone | 1 | 138 |  | Maines Road taps the Marshall-Blackstone 138kV circuit | M5_In Service | 88193 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2016-12-01 | M3_Long Lead Materials | 88193 | 0% |  | 2
A in MTEP09 | East | METC | 2485 | 2016-06-08 | 4478 | 2016-06-08 | RLY | 2019-06-01 | Ransom | Buck Creek | 1 | 138 |  | Relay modifications | Planned | 12000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2019-06-01 | Planned | 12000 | 0% |  | 0
A in MTEP09 | East | METC | 2486 | 2016-08-15 | 4479 | 2016-08-15 | TAP | 2018-06-01 | Haakwood | Rondo | 1 | 138 |  | Haakwood taps the Rondo-Vanderbilt section of the Riggsville-Livingston 138kV line. | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2486 | 2016-08-15 | 4480 | 2016-08-15 | TAP | 2018-06-01 | Haakwood | Vanderbilt | 1 | 138 |  | Haakwood taps the Rondo-Vanderbilt section of the Riggsville-Livingston 138kV line. | Planned | 85000 |  |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2018-06-01 | Planned | 85000 | 0% |  | 0
A in MTEP09 | East | METC | 2501 | 2015-02-26 | 4499 | 2015-02-26 | CAP | 2030-06-01 | New site (Wexford prime) |  |  |  |  | Install 25.2 MVAR capacitor | Planned | 1524194 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2030-06-01 | Planned | 1524194 | 0% |  | 0
A in MTEP09 | East | METC | 2501 | 2015-02-26 | 4500 | 2015-02-26 | CAP | 2030-06-01 | Keystone |  |  |  |  | Install 50.4 MVAR capacitor | Planned | 740323 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2030-06-01 | Planned | 740323 | 0% |  | 0
A in MTEP09 | East | METC | 2501 | 2015-02-26 | 4501 | 2015-02-26 | CAP | 2030-06-01 | Plum |  |  |  |  | Install 25.2 MVAR capacitor | Planned | 435484 |  |  | MI |  |  |  |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2030-06-01 | Planned | 435484 | 0% |  | 0
A in MTEP09 | West | MP | 2759 | 2009-11-13 | 4782 | 2015-06-10 | SUB | 2017-12-31 | Laskin | Substation Equipment |  | 115 | 46 | Substation Transformer | Planned | 1500000 | Engineering |  | MN |  |  | 28 |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 1500000 | 0% | Cost increase due to scope changes - bus upgrades required in addition to transformer replacement | 0
A in MTEP09 | Central | Vectren | 2466 | 2017-06-30 | 4430 | 2016-06-30 | SUB | 2019-06-01 | Roesner Rd 138/12kV Substation |  | 1 | 138 | 12.47 | New 138/12kV Substation for load growth | M2a_Pre-Project Approval | 3000000 | Budgetary |  | IN |  |  | 16/20 |  | Other |  | Distribution | N | N | NT | Bottom-Up | A | 2019-06-01 | M2a_Pre-Project Approval | 3000000 | 0% |  | 0
A in MTEP09 | East | WPSC | 2736 | 2010-01-06 | 4758 | 2017-03-07 | LNrb | 2016-12-31 | East Bay | South Boardman Distribution | 1 | 69 |  | Rebuild Overloaded Line | Planned | 7500000 |  | 2012 | MI | 15.93 |  | 143.4MVA | 143.4MVA | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2016-12-31 | Planned | 7500000 | 0% | Updated estimated cost in 2015 planning review | 0
A in MTEP09 | East | WPSC | 2770 | 2009-02-03 | 4832 | 2015-09-15 | TAP | 2017-12-31 | Hersey | Gilmore | 1 | 69 |  | Gilmore Taps the Hersey to Vestaburg 69kV circuit | Planned | 250000 | Planning |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-12-31 | Planned | 250000 | 0% | Updated budget in 2014 plan review. | 0
A in MTEP09 | East | WPSC | 2770 | 2009-02-03 | 4833 | 2015-09-15 | TAP | 2017-06-01 | Gilmore | Vestaburg | 1 | 69 |  | Gilmore Taps the Hersey to Vestaburg 69kV circuit | Planned | 250000 | Planning |  | MI |  |  |  |  | Other |  | Distribution | N | N | Y | Bottom-Up | A | 2017-06-01 | Planned | 250000 | 0% | Updated budget in 2014 plan review. | 0
A in MTEP08 | Central | DEI | 1899 | 2011-09-27 | 3795 | 2017-03-08 | LNrc | 2017-02-24 | Macy | Rochester Metals Jct | 1 | 69 |  | Reconductor Macy to Rochester Metals Jct section of 6957 circuit with 477ACSR - approx 9.1 miles | M5_In Service | 4707000 | Engineering |  | IN | 9.1 |  | 100 |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | Under Construction | 4707000 | 0% | increased costs due to new steel pole standard construction | 2
A in MTEP08 | Central | HE | 1929 | 2008-01-10 | 3808 | 2011-01-11 | SUB | 2012-09-01 | Georgetown Primary |  | 1 | 138 |  | Rebuild | Planned | 1250000 |  |  | IN |  |  | 2000 AMP |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2012-09-01 | Planned | 1250000 | 0% |  | 0
A in MTEP08 | West | ITCM | 1744 | 2009-09-25 | 3546 | 2017-03-10 | LNrc | 2018-12-31 | Maquoketa | Grand Mound | 1 | 161 |  | Reconductor | Planned | 12800161 | Planning |  | IA | 14.5 |  | 326/326 MVA |  | BaseRel |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 10150000 | 26.11% | Updated planning estimate with engineering estimate in 2016 dollars. | -12
A in MTEP08 | East | METC | 1448 | 2006-10-25 | 2452 | 2015-09-29 | Dist | 2019-12-31 | Simpson 138kV |  |  | 138 | 12.5 | Install a second distribution transformer at Simpson (Simpson) | Planned | 2200000 |  |  | MI |  |  |  |  | Other |  |  | N | N | Y | Bottom-Up | A | 2019-12-31 | Planned | 2200000 | 0% |  | 0
A in MTEP08 | West | NWEC | 2011 | 2009-11-16 | 3992 | 2009-11-16 | LNrb | 2011-06-01 | Frederic | Lewis |  | 69 |  | Rebuild the 34.5Kv system between Frederic and Lewis sub at 69KV with 477ASCR and horizontal post construction. | Planned | 350000 |  |  | WI | 2.8 | 0 | 31 |  | Other |  |  | N | N | Y | Bottom-Up | A | 2011-06-01 | Planned | 350000 | 0% |  | 0
A in MTEP08 | West | NWEC | 2012 | 2009-11-16 | 3993 | 2009-11-16 | LNrb | 2011-09-01 | Falun | Penta |  | 69 |  | Rebuild the 34.5Kv system between Falun and Penta sub at 69KV with 477ASCR and horizontal post construction. | Under Construction | 538000 |  |  | WI | 4.3 | 0 | 47 |  | Other |  |  | N | N | Y | Bottom-Up | A | 2011-09-01 | Under Construction | 538000 | 0% |  | 0
A in MTEP08 | West | NWEC | 2013 | 2009-11-16 | 3994 | 2009-11-16 | LNrb | 2011-06-01 | Penta | Siren Tap |  | 69 |  | Rebuild the 34.5Kv system between Penta sub and Siren Tap at 69KV with 477ASCR and horizontal post construction. | Planned | 175000 |  |  | WI | 1.4 | 0 | 15 |  | Other |  |  | N | N | Y | Bottom-Up | A | 2011-06-01 | Planned | 175000 | 0% |  | 0
A in MTEP08 | West | NWEC | 2016 | 2009-11-16 | 3997 | 2011-09-16 | LNrc | 2013-01-01 | Frederic | Coffee Cup |  | 69 |  | Reconductor 69KV line with 477ACSR | Planned | 100000 |  |  | WI | 2 | 0 | 84 |  | Other |  |  | N | N | Y | Bottom-Up | A | 2013-01-01 | Planned | 100000 | 0% |  | 0
A in MTEP08 | West | NWEC | 2018 | 2009-11-16 | 3999 | 2009-11-16 | LN | 2011-06-01 | Eureka Tap | Centuria |  | 69 | 12.47 | Build new 69KV line to Centuria and build Distribution Sub | Planned | 1200000 |  |  | WI | 0 | 4 |  |  | Other |  |  | N | N | Y | Bottom-Up | A | 2011-06-01 | Planned | 1200000 | 0% |  | 0
A in MTEP08 | Central | Vectren | 1782 | 2014-09-30 | 3572 | 2017-03-31 | SUB | 2024-12-31 | Northeast Sub Bus reconfig | Substation | 1 | 138 |  | Rebuild existing straight bus with more reliable breaker and half scheme | Withdrawn | 8000000 | Budgetary |  | IN |  |  |  |  | Other |  | Reliability | N | N | Y | Bottom-Up | A | 2024-12-31 | M2a_Pre-Project Approval | 8000000 | 0% |  | 0
A in MTEP08 | Central | Vectren | 1784 | 2014-09-30 | 3574 | 2017-03-31 | SUB | 2025-12-31 | Jasper#3 Sub Exp-Victory Line | Victory | 1 | 69 |  | Extend existing Victory line to new term at existing sub | M2a_Pre-Project Approval | 3625000 | Budgetary |  | IN |  |  |  |  | Other |  |  | N | N | NT | Bottom-Up | A | 2019-12-31 | M2a_Pre-Project Approval | 3625000 | 0% |  | 72
A in MTEP08 | Central | Vectren | 1788 | 2014-09-30 | 3578 | 2016-12-21 | SUB | 2016-10-28 | St. Wendel Sub | Mohr Rd Sub | 34 | 69 |  | New 69kV line from St. Wendel Sub to Mohr Rd Sub | M5_In Service | 2581000 | Budgetary |  | IN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2016-12-31 | M2a_Pre-Project Approval | 2750000 | -6.145% |  | -2
A in MTEP08 | Central | Vectren | 1789 | 2014-09-30 | 3579 | 2017-06-30 | SUB | 2019-12-31 | Boonville Sub | Boonville Pioneer Sub | 56 | 69 |  | New 69kV line from Boonville Sub to Boonville Pioneer Sub | M2a_Pre-Project Approval | 6300000 | Budgetary |  | IN |  |  |  |  | Other |  | Reliability | N | N | NT | Bottom-Up | A | 2018-12-31 | M2a_Pre-Project Approval | 1400000 | 350% | Revised scope and estimate | 12
A in MTEP08 | West | XEL | 675 | 2008-06-30 | 1364 | 2016-12-21 | LNup | 2016-12-16 | Westgate | Scott County | 1 | 115 |  | upgrade line | M5_In Service | 14000000 |  |  | MN | 20.1 |  | 194 MVA |  | Other |  |  | N | N | Y | Bottom-Up | A | 2017-06-15 | Planned | 14000000 | 0% |  | -6
A in MTEP06 | Central | AmerenIL | 739 | 2006-03-17 | 1432 | 2012-10-12 | LN | 2020-11-01 | Line 4561 Tap | Franklin County Power Plant | 1 | 345 |  | 345 kV connection (new ring bus) to new generation | Planned | 6410900 | Engineering |  | IL |  |  |  |  | Other |  |  | N | N | Y | Bottom-Up | A | 2020-11-01 | Planned | 6410900 | 0% |  | 0
A in MTEP03 | Central | SIPC | 81 | 2011-04-22 | 60 | 2016-02-03 | LN | 2016-10-01 | Power Plant | Carrier Mills 161kV |  | 161 |  | 25-mile 161kV transmission line from Southern Illinois Power Cooperative's power plant to a new 161/69kV substation | Under Construction | 9200000 |  |  | IL |  | 25 |  |  | Other |  |  | N | N | Y | Bottom-Up | A | 2016-10-01 | Under Construction | 9200000 | 0% |  | 0
A in MTEP03 | Central | SIPC | 81 | 2011-04-22 | 5339 | 2015-11-09 | LN | 2016-10-01 | Carrier Mills | 161/69 kV transformer |  | 161 | 69 | New 161/69kV substation located north of Carrier Mills, IL | Under Construction | 1000000 |  |  | IL |  |  |  |  | Other |  |  | N | N | Y | Bottom-Up | A | 2016-10-01 | Under Construction | 1000000 | 0% |  | 0
Note on U2: Upgraded or on existing rights of way